Intervention Summary
## Title: UNDP Human Development Initiative (HDI) Programme

What support has the UK provided?
DFID provided £5.0 million in January 2011 to support The UNDP Human Development Initiative during the final year of its programme. DFID had been a core contributor to HDI between 2004-2008 providing £4.0m. On completion of our funding DFID remained engaged with HDI and created an informal donor group which engaged heavily with the UNDP on the findings of DFID’s PCR and Independent Assessment missions. Other donors supporting the Initiative include Danida, SIDA and UNDP who together provided an equivalent amount and the size of the programme totalled £10.3m The primary purpose of the programme is to empower 128,000 vulnerable households through strengthened village groups to improve their food security and increase their incomes. This was to be achieved through the delivery of 4 Outputs. The programme was implemented by UNDP through the Integrated Community Development Programme (ICDP) and Community Development in Remote Townships Programme (CDRT). In addition the UNDP Policy Unit. Microfinance (MF) programme is implemented through Pact. / Although agreed funding was for one year only (Jan-Dec 2011) a request for a No-Cost Extension was received in November 2011. While the ICDP and CDRT projects had completed all programme-related field activities on target and as planned, there were delays in implementing the pilot studies, the M&E evidence system and commissioned studies essential for government policy advocacy which were to form the basic building blocks in the design of the next phase 2013-2015. DFID approved the no-cost extension until end of May 2012 to enable the programme to complete remaining activities.

Why was UK support required?
Despite vast natural resources, Burma is one of the least developed countries in the world. After decades of armed conflicts, economic mismanagement and an oppressive military regime, chronic poverty is widespread and the country is off-track to achieve the MDGs. / UNDP has been implementing the Human Development Initiative (HDI) in Burma since 1994, providing support to poor people in 20% of Burma’s townships through a community-centred approach. HDI activities have addressed food insecurity and community infrastructure (including water & sanitation, schools and health posts). / The 4th phase of the UNDP Human Development Initiative started in 2003 and was due to complete at the end of 2010. However, in January 2011 UNDP extended their programme for a final year and the core funding remaining was insufficient to cover their resource needs. To avoid precipitous withdrawal of programmes from entire townships, DFID agreed to contribute £ 5,0m to support the final year of the programme / The Independent Assessment Mission (concluded that the Microfinance and Integrated Household Poverty Assessment components demonstrated strong impact, but that HDI has weaknesses in some other areas (specifically community infrastructure) and therefore should not “continue in its current form”. It was critical of UNDP interpreting its mandate too widely and undertaking a range of activities without a strategic rationale. It was impossible for the UNDP and it was impossible for them to provide adequate technical staff and resources were spread too widely over too many sectors, therefore limiting the impact in each one. With lobbying from the HDI donor group, which DFID leads, UNDP agreed that HDI would prioritise activities – primarily around raising household income. / By appraising different HDI activities, DFID has had an opportunity not only to allocate its own funds to areas of greatest potential impact, but also to influence the direction of HDI as a whole. Despite its flaws, HDI remains important because of its access to large areas of Burma, including ethnic minority border areas, and its potential to increase knowledge of the challenges in rural Burma.

What are the expected results?
The intended impact of the HDI programme is the reduction of extreme poverty and hunger in Burma. The expected outcome of the programme is that 128,000 poor and vulnerable households (in the project area) are empowered through strengthened village groups to improve their food security and increase their incomes. / The results are to be measured against (4) outcome indicators – / Increased food production of 22,800 poor and vulnerable households in the project area from agriculture, livestock, fisheries and forestry / Village community groups strengthened to implement village development priorities; / Increased access to formally managed financial / Pilot studies, M&E evidence systems and commissioned studies are used in government policy advocacy and to inform programme development / services for poor households Average number of food secure months by 768,000 beneficiaries, / This represents a far fewer but a more intensive set of activities in communities and the M&E unit has been augmented and linked to these Outputs