### Logframe Supplementary Relief and Recovery for the Delta (Revised October 2010)
PROJECT TITLE (max. 50 characters)		Component One and Two – IDE emergency agricultural inputs & Humanitarian ‘surge’
GOAL	Indicator	Baseline + year	Milestone 1	Milestone 2	Target / January 2011
To improve the quality of life and reduce vulnerability of poor people in the Delta	Food Security / Reduction in Household Debt Levels / Increase in household livelihood / assets	Previous season recall / (240,000 farming households and 140,000 landless labour households affected – Periodic Review 2 identifies Delta areas with high levels of malnutrition) / Baseline to be determined by follow-up Social Impacts Monitoring / 100,000 fishing boats lost. / 85% of seed stock destroyed. / 50% of buffalos lost / List of assets of households assisted			Increased home rice food stocks / Increased nutrition; protein and caloric intake of household / Reduction in household debt from previous season / New household livelihood assets (over 1 year)

		Monitoring of farm households through follow-up household surveys by IDE, FAO and other agencies, Delta Livelihoods Working Group and other partners. PONREPP Periodic Review data, other relevant monitoring assessments

PURPOSE (max. 250 characters) / To provide humanitarian assistance to meet emergency and recovery needs of the poorest communities affected by Cyclone Nargis	Indicator	Baseline + year	Milestone 1	Milestone 2	January 2011	Assumptions
	Increase in paddy yields / No. of household shelters – re-habilitated/repaired				An average increase on 2008 levels of 10 to 15 baskets of paddy per acre in the Delta resulting from relief assistance / 33,080 / households provided with shelter assistance	Seeds, farm machinery, diesel and fertilizer are available and delivered on time for the planting deadline. / There will not be any ad-hoc, unforeseen market related interventions that damage farm gate prices and lower farm incomes. / Shelter materials available and price stable.
		Source
		Partner evaluation reports, village visits, field reports
	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year / January 2011
	Number of households benefiting from relief assistance				80,000 households
		Source
		Partner evaluation reports
INPUTS - TOTAL (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£5 million			£5 million	100
INPUTS (HR)	DFID (FTEs)
	0.6

OUTPUT 1	Indicator	Baseline + year	Milestone 1	Milestone 2	Target / January 2011	Assumptions
Livelihoods relief assistance delivered to help Cyclone Nargis-affected farming communities’ crops to be sustainably restored and improved / (Note: output 1 is not only IDE component)	Number of households directly assisted with relief support / Number of Households receive Fishing Gear + Number of households receive / Livestock replacement	None			79,813 Households provided with livelihoods relief assistance Including… / 35,000 landless households received 50 KG of rice / (75 % of food aid recipients are women) / 9 villages received community grants the construction of footbridge and jetty replacement benefiting 10,000 households / Fertilizer package delivered to 22,200 farm households and delivered with advice on best practice environmental / 12,000 Farm Households (Cash transfer for farm labours) / Provision of Fertilizer to 613 farm households (Action Aid) / 14,418 Households including…. / Action Aid: Cash grant 736 HH, Cash Grant for SHG 900 HH, Cash grant for fish processing 74, Provision of sees/fruit trees 1935, Buffaloes 120, Households who farming animals vaccinated 384, Boats 80, Livelihoods for PwD 100. / ACTED (250 fishing boats, 1000 fishing gears, 200 buffalos, 500 piglets. / Mercy Corps (105 Buffalos, 75 power tillers, 150 pigs, 120 goats, 130 fishery rehabilitation grants, / Pyoe Pin: Agri inputs: 415 HHs, Fishery inputs 181 HHs, Livestock inputs: 672 HHs, Cash grant & revolving fund: 3047 HHs) } / UNDP 1,364 households receiving livelihoods grants	Supply chain will allow for procurement of sufficient relief items and inputs at the appropriate time. / The operating environment remains conducive for access and delivery. / Targeting strategy ensures assistance is delivered to those in need.
		Source
		Project reports from ‘livelihoods’ partners; / DFID field missions
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
30%
		Source				RISK RATING
		As above				Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£2,130,000			£2,130,000	100
INPUTS (HR)	DFID (FTEs)
	0.33

OUTPUT 2	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
Safer, more durable shelter for the targeted communities / * Disaster risk reduction best practice fully integrated	Number of households directly assisted with relief shelter rehabilitation / Number of households directly assisted with NEW shelter / Local resource for Disaster Risk Reduction	130,000 households(across Delta) in need of adequate shelter / 2009 / N/A			30,550 repaired / {[IDE 30000 + AAM 400 + SCF 150} / 2,550 New houses / (IOM 1000, ActionAid 250, ACTED 300, Mercy Corps 300 and Save the Children 700) / 100 carpenters (IOM) + 120 skilled labours (Save) trained on build back safer technique and / distribute 1000 hand-crank radio (IOM)	There is sufficient thatch, sheeting, timber available to meet demand, and procurement can be managed so as not stimulate price increases. / The operating environment remains conducive for access and delivery. / Targeting strategy ensures assistance is delivered to those in need.
		Source
		UN-Habitat, Myanmar, April 2009 report / Project reports from IDE, SCF, IOM, Action AID, FAO / DFID field missions
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
30%
		Source				RISK RATING
						Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£2,430,000			£2,430,000	100
INPUTS (HR)	DFID (FTEs)
	0.034
OUTPUT 3	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
Support to co-ordination, monitoring and evaluation of recovery programming; identifying and seeking to address programming gaps.	No of products (analytical papers, tools) prepared and shared and impact of these on funding, gap filling and co-ordinated programming				Annual Analytical Assessment	That there is sufficient funding for recovery programming to allow aid effectiveness measures to deliver improved pro-poor results.
		Source
		Recovery Co-ordination Centre data – including Periodic Review, partner agencies reports and assessments. DFID verification
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
30%	Recovery Co-ordination Centre and field hubs are fully operational		Recovery coordination centre is fully operational (2009 Oct)		Recovery coordination centre is fully operational
		Source				RISK RATING
		DFID verification				Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£370,000
INPUTS (HR)	DFID (FTEs)
	0.34

OUTPUT 4	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year	Assumptions
The implementing partners receive the technical advice and inputs for programme delivery and PONREPP implementation	Delivery of programmes, partner/stakeholders feed-back. / PONREPP prioritised Action Plan delivered / PONREPP conference outcome – results in additional donor commitments to recovery / Advice to donor and other colleagues on recovery policy and programming policy delivered in timely way. / Partners/stakeholders feed-back on quality of advice and inputs.				New funding commitments made to PONREPP / Action Plan elaborated, signed-off and published.
		Source
		360 degree reporting. Programme reports
IMPACT WEIGHTING	Indicator	Baseline + year	Milestone 1	Milestone 2	Target + year
10%
		Source				RISK RATING
						Low
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£70,000			£70,000	100
INPUTS (HR)	DFID (FTEs)