Project Summary
## Forest Governance Markets and Climate programme

What support will the UK provide?
How much funding does the UK expect to provide? / £60,000,000 for the four years of spending period from June 2011 to July 2015, as part of a ten-year programme for up to £250,000,000, the maximum expenditure and end point being subject to project performance and progress. / Period of funding? / August 2011 to September 2021

Why is UK support required?
What need are we trying to address? / Deforestation and forest degradation harm biodiversity, contribute to climate change and increase poverty. 13 million hectares of forest (an area the size of England) is lost in total each year. Evidence suggests that for every million hectares of forest destroyed, up to a billion tonnes of C02 (equivalent) are lost into the atmosphere; and the standing forest that is lost can no longer remove greenhouse gases from the atmosphere. / In addition, 1.2 billion poor people depend on forests – fuel, fodder, wood and food – for their livelihoods.[1] Forest clearance (deforestation) and illegal logging (forest degradation) and its related trade also deprive forest-dependent people of their livelihoods. 100 million cubic metres of timber is illegally logged each year, most of it in tropical developing countries, and around 5 million hectares of forest is degraded as a consequence[2]. Illegal logging is often the first and critical step towards forest clearance for agriculture and plantations. / Much of forest clearance is legal and contributes to economic development. However, a substantial proportion contravenes national regulations and laws. Illegal forest clearance occurs regardless of the conservation or livelihood values of forests involved. / What will we do to tackle this problem? / This programme will coordinate efforts with the EU Forest Law Enforcement Governance and Trade action plan, as part of a global effort to tackle deforestation. It is one element of the UK’s broader initiative on international forestry and climate under the International Climate Fund. It will be implemented as part of broader UK efforts under International Climate Finance (ICF) to reduce emissions from deforestation and forest degradation (REDD+). / This programme will support governance and market reforms that reduce the illegal use of forest resources and benefit the poor. It will achieve this by combining “demand-side” actions in European and other consumer countries, and “supply-side” actions in producer countries. These will result in reductions in the consumption and production of illegal timber and other illegally-sourced commodities that drive illegal forest clearance and deforestation, such as soybean, palm oil, beef and leather. / It will provide some of the key enabling conditions and foundations or “readiness” for effective investment in REDD+ and in itself it will reduce emissions from deforestation and degradation. / It tackles illegal logging and associated trade (a priority in the Coalition Agreement) in alignment with European and global efforts. It enables compliance with the new EU Timber Regulation that UK must fully implement by end 2012. / Illegal logging is most likely to persist or increase where governance is poor, where forests have timber values that attract attention of markets and where alternative economic opportunities are lacking. These circumstances are found in some regions of many countries, but are particularly prevalent in Central and West Africa, some countries of the Amazon basin and Central America, and the Pacific. These circumstances are also found in parts of Russia, especially in the Russian Far East. / Who will be implementing the project? / DFID, working with DECC and Defra, will implement the programme as part of a coordinated effort with the EU. A Forest Governance Facilitator will be contracted and responsible for oversight of the overall programme. / Are any other donors supporting this (or similar) efforts? / EU, USA, China, Japan support similar efforts.
[1] Sustaining Forests: A World Bank Strategy. World Bank (2002)
[2] Illegal Logging and Related Trade – Indicators of the Global Response. Chatham House (2010)

What are the expected results?
What will change as a result of our support? / The ten-year programme will contribute to a global effort that will help protect up to 39 million hectares of forest over the next 25 years and contribute to the greater sustainability of food production. / By reducing deforestation and degradation the programme will contribute to efforts that avoid emissions of up to 33 billion MT CO2e at the very low cost of under £2 a carbon tonne (the current European price being £13). / Timber that is legally logged in accordance with national laws will increase forest taxes providing up to £13 billion of revenue to cash-strapped exchequers in developing countries. / The programme will help protect the livelihoods of tens of millions of poor people dependent on forests for their livelihoods by reducing illegal logging. It will give them a greater say in what happens to their forests and reduce the likelihood of conflict over forest tenure. Clear and secure forest tenure can enable forest dependent communities to double their incomes. / Similarly improved legislation, and monitoring of legal compliance with respect to other commodities, will lead to increases in incomes for 50 million farming men, women and children, and improved working conditions for 10 million plantation and ranching workers employed in the palm oil, soy, beef and leather sectors. / With illegal logging and forest clearance reduced, livelihoods protected, and carbon emissions avoided the programme will deliver a benefit-cost ratio of £52 for every £1 invested in the intervention (52:1). Even using conservative calculations and assuming that costs per unit of progress rise over time, the investment represents exceptional value for money. / What are the planned outputs of the project attributable to UK support? / Outputs from the programme will be: / producer and processing countries with effective multi-stakeholder institutions for overseeing, implementing, enforcing and monitoring legal, policy and market reforms and actions that control illegally sourced timber and other agricultural commodities; / compliance with public rules and policies, as well as private business standards in consumer countries, that discourage trade in illegal timber and other commodities sourced from illegal forest practices; / knowledge and momentum for change, based on sound evidence, amongst the public, NGOs, private sector and governments; / coherence between programmes on forests and deforestation at national and international levels. / How will we determine whether the expected results have been achieved? / UK will focus its support in up to 10 forest producer countries and help them put in place legality assurance systems that monitor, track, audit and verify the legal origin of timber, wood products and commodities, such as palm oil, soy, beef and leather. This will inspire consumers with confidence that the products they purchase are legally sourced from these countries. / By the end of the programme key European and at least 6 other consumer countries will be operating effective public procurement and /or import due diligence systems for timber and these commodities. The number of businesses and financial investors working in timber and these other commodity markets that demonstrate compliance with legality, as well as sustainability standards will double. / The forest area under non-state control will increase by over 10% and decisions about forest tenure, rights and forest land allocation will be transparent and accountable to citizens, including local and indigenous communities. / At least 11 international and bilateral initiatives designed to deliver Reduced Emissions from Deforestation and forest Degradation (REDD+) will build on the approaches that strengthen forest law enforcement governance and trade (FLEGT) developed through this programme. FGMC will maximise the effectiveness of broader overall UK support for REDD+.. / The EU will publish progress on its website (most recent December 2010) and periodic independent assessments will build on the methodology developed by the 2010 independent assessment by Chatham House - Illegal logging and related trade: Indicators of the global response (http://www.illegal-logging.info/).

Strategic Case

A. Context and need for DFID intervention / Context / Over a billion poor people depend on forests for their livelihoods – wood, fuel, fodder and food.[3] One third of the world’s largest cities rely on water flows regulated by forests for their drinking supply.[4] The world’s trees store about 289 gigatonnes of carbon and remove greenhouse gases from the atmosphere.[5] Forests also contain more than half of land-based plant and animal species. / But 13 million hectares of forest (equivalent to the size of England) are lost a year[6]. This deprives people of their livelihoods, erodes biodiversity and contributes to global warming and climate change. Deforestation contributes about 17% of human-induced greenhouse gases emitted globally[7], greater than the amount emitted by the transport sector. In many developing countries it contributes to between 60% and 70% of national emissions. / A substantial proportion of this deforestation is due to illegal clearance and illegal logging. Illegal logging results worldwide in $15 billion of revenue loss every year.[8] More than 100 million cubic metres of timber is illegally logged each year, most of it in tropical developing countries, and around 5 million hectares of forest is degraded as a consequence. That is equivalent to about ten times the annual timber harvest of the UK. In 2008 five major consumer countries, including the UK, imported illegally sourced wood products worth US $8.4 billion.[9] / Illegal logging is often the first and critical step towards forest clearance for agriculture and plantations (and in some cases mining). International trade in agricultural commodities is growing very rapidly with demand in food expected to rise by 70% by 2050. Demand for bio-fuels is projected to double in the next 10 years.[10] Global consumption of soybeans for human food and animal feed has increased by 60% since 2000/01, and that of palm oil by 85%.[11] / Much of forest clearance to meet these demands is legal and contributes to economic development. However, a substantial proportion, at least a third, contravenes national regulations and laws. Illegal forest clearance occurs regardless of the conservation or livelihood values of forests involved. / Both illegal logging and illegal forest conversion are products of wide-scale market and governance failure. The major portion of the value of tropical forests is as public goods that society as a whole benefits from, but for which society currently does not necessarily pay to receive.[12] For example, forests provide regulating ecosystem services such as carbon storage, biodiversity, soil erosion protection, pollution control, and water purification. Market failure means that these public goods are often not priced in markets and grossly undervalued relative to the private goods (timber, land, etc.) that can be realised by cutting them down. This makes it privately rational for a farmer to destroy a hectare of forest in order to create pasture for beef cattle worth US$ 200 –$500 a hectare a year even though that same hectare is theoretically worth US$1,000 –$2,000 as sustainably managed forest for timber or US$ 1,500 – $10,000 as a carbon storage asset.[13] / Governance failure means that the rules and regulations put in place to guide forest use and protection are routinely ignored or bypassed, or are ambiguous or inadequate. Improved regulation is required to correct the market failure. The most difficult challenges to achieving governance and market reforms that reduce the illegal use of forest resources arise in relatively poor countries with weak formal governance arrangements. / In these countries forest resources are relatively easy to capture, and are dispersed (compared, for example, to "point source" resources such as oil and minerals). There are, therefore, multiple stakeholders with competing interests in their use. Competition is increasing with the growing value of forest products (driven by export markets and domestic demand, and potentially by climate finance), and increasing scarcity. The result is often violent conflict, and widespread corruption. In some parts of the world illegal logging also funds militias. / Poor communities are the first to suffer from the loss and degradation of local forests caused by illegal activities, and from the conflict and corruption associated with them. This provides one of the main rationales for DFID involvement. Degradation and deforestation causes a loss of $1.9 trillion to $4.5 trillion per year in ecosystems goods and services. Poor people heavily depend on these and suffer disproportionate losses from their depletion. For example, the Amazon forest alone provides 10 million poor forest dwellers with between $500 million and $1 billion a year from the fish they catch in forest river basins, and the gums, oils and other goods they harvest for cash.[14] In Africa 80% of poor people rely on wild plant medicines.[15] In seasons when crops are not harvested or there is drought, wild foods from forests act as “safety nets” for the poor. / To drive change requires a complementary policy mix. First, imperatives (laws and regulations). Second, capacities (the ability in the state and beyond in civil society and markets) to enforce them and provide good forest governance. Third, different financial incentives.[16] / This programme will not directly provide financial incentives – it will not make direct payments for reductions in emissions from deforestation or for reductions in illegal logging. It will not directly implement or apply international forest carbon accounting systems and forest carbon monitoring technologies that will be needed for sustained REDD+ finance to flow. UK will support other programmes in these areas, and will aim for coherence between the two. / This programme will focus on changing “imperatives” and building “capacities” for improving forest legality and the forest governance measures or “safeguards” that change key market incentives and help ensure the integrity[17] of schemes for delivering REDD+ finance. / The programme will do this by addressing three problems. First, market failure that encourages illegal logging and illegal forest clearance for agricultural commodity production. This requires action by producers and consumers of illegal timber and other commodities. Second, government failure, specifically the weak regulation of logging, forest clearance, and the trade in illegally sourced forest commodities. The bulk of the programme is directed at improving public and private business standards and the enforcement of these in producer and consumer countries. Improvements in forest governance in producer countries will lead to reduced illegal logging and illegal clearance. / Third, the programme will address the inequitable distribution of resources that results from illegal logging and illegal clearance, mainly indirectly by favouring the delivery of public goods as mentioned above; but also directly, by tackling the associated corruption and “rent-seeking” that disproportionately affects the poor, and constrains the effective and efficient collection and distribution of forest revenues. Maintenance of the ecosystem services, clarification and improvement in the rights and tenure, and improvements in the distribution of forest revenues, will benefit large numbers of poor people living and around forests, and who depend on them for a significant proportion of their livelihood. / It will build on the good progress in improving forest governance in recent years made through DFID’s successful Forest Governance and Trade Programme (£25 million from 2006 to 2011). This has supported action on two fronts: action in producer countries where timber is illegally logged; and action to change the behaviour of consumer countries to eliminate the market for illegal timber. / Evidence for the efficacy of acting on both demand and supply of illegally logged timber – an approach championed by UK over the past 10 years – is contained in a major independent and rigorous assessment of impact by Chatham House, which has been internationally acclaimed.[18] / UK strategic priorities / This programme contributes to UK strategic priorities. Coalition statements and departmental business plans highlight UK’s continued commitment to tackling illegal logging, deforestation and related trade in coordination with the EU. British business and NGOs are engaged in this endeavour. Prominent international champions, including the Prince of Wales, are supportive of efforts to tackle illegal logging and reduce deforestation. / It will help deliver UK government’s International Climate Finance (ICF) commitment, recognising that forest governance is an essential requirement to reduce deforestation and degradation (and the emissions they cause), as well as helping to build confidence for business investment. / An independent review of options to deliver REDD+ (Reduced Emissions from Deforestation and forest Degradation plus carbon stock enhancement from afforestation, reforestation and forest management), commissioned by the UK government, also identifies forest governance in developing countries as one element in getting “ready” for REDD+.[19] An increasing number of countries with, for example, support of the Forest Carbon Partnership Facility (FCPF) to which UK contributes, have prepared national “REDD+ Readiness Packages”. Many of these have identified weaknesses in forest governance as a constraint in achieving effective emissions reductions and for forest investment. / In June 2010 at the G8 Summit, the UK committed to “prevent, curb and eradicate illicit activities”, including the “illicit trade in timber”, and highlighted the links between illegal logging and conflict. Three-quarters of forests are in areas of fragile states, or regions at high to medium risk of becoming failed states.[20] The programme will contribute to governance of forests in fragile states. / The programme also contributes to DFID’s Business Plan, which sets out a vision and priorities to 2015, and includes, under actions to combat climate change, a specific action to tackle illegal logging and deforestation. It also contributes to actions in DECC and Defra’s Business Plans. . / In addition the programme will help meet Millennium Development Goal 7 by reducing the area deforested; has implications for food security and hunger (Millennium Development Goal 1). / Key policies / This programme will contribute to the EU FLEGT Action Plan - European Union Forest Law Enforcement, Governance and Trade. This is part of a broader global effort to tackle the problem, involving the private sector and civil society. / All European Member States are subject to the FLEGT Regulation, whereby the EU enters into forest law enforcement governance trade treaty agreements or FLEGT voluntary partnership agreements (VPAs). Treaties place binding obligations on all parties to improve forest governance and verify legality of forest allocation and fiscal regimes, as well as the commerce of forest products. Actions are negotiated, agreed and taken by the developing producer country and the EU; with some support to key actions by developing countries financed by the EU. / The FLEGT VPA process is finely designed, involving 5 stages: (1) Initiation; (2) Negotiation; (3) Ratification; (4) Systems development or transitional implementation; and (5) Implementation. The UK Forest Governance and Trade programme has helped design and test the VPA process in Ghana, Cameroon, Liberia and Indonesia. (See section A in the Management Case for details of activities at different stages of the FLEGT treaty process.) / The combined actions so far by five producer countries, two timber processing countries, and five consumer countries, directly and indirectly as a result of the EU FLEGT action plan, have influenced the broader trade regime and reduced the trafficking in illegally harvested timber products by 22% since 2002.[21] / There is some, but limited, evidence of graft and illegality linked to timber and pulp and paper produced from plantations established by clearing natural forest. Over the past decade 5.5 million hectares of timber plantations have been established worldwide, mainly on agricultural land (afforestation) and mostly in Asia, with three-quarters of this area planted to native tree species.[22] / The EU Timber Regulation will apply from March 2013,[23] with similar consumer country regulation in USA, and being explored by China, Japan and Australia. This makes the first sale of timber in UK and Europe that has been illegally logged elsewhere, an offence. It covers pulp and paper amongst timber and wood products. / By requiring under the FLEGT and EU Timber Regulations that timber imports are from legal sources, the UK creates economic incentives to improve forest governance. / As a consequence the number of developing countries (producer and processor) formally communicating with the European Commission to express “interest” in working with the FLEGT Action Plan has increased from 8 to almost 30 developing countries. The Commission anticipates that support by the EU will need to expand to €1.5 billion over the next 10 years. / The FLEGT Action Plan also provides some of the essential requirements for REDD+. First, it will reduce emissions “leakage” by helping ensure that activities taken by one country to tackle illegal logging and the drivers of deforestation do not lead to “displacement” of illegal logging, poor practice and related trade to other countries. Second, by providing broad-based support to a range of countries on market compliance it will ensure no unfair trade advantage to any single country. / Actions that countries take under FLEGT will also contribute to REDD+, as these: / can provide assurance of legal compliance in their forest sectors and the drivers of forest loss (many of which are based on illegal activities); / transparently disclose information including of their forest-related finance, revenues and benefit sharing mechanisms; / build effective national and sub-national multi-stakeholder institutions and processes; / establish independent third-party monitoring, reporting and verification (MRV) of legal compliance and forest governance, including of the clarity and security of the rights and tenure of forest dependent people; / harmonise points of delivery and decision-making in country. / DFID intervention / The success and significance of DFID’s contribution so far is widely recognised and solidly based on evidence. Its strengths have been its ability to draw on in-house expertise and external networks in the forest sector; to work effectively across UK government; to address the nexus between trade, consumer and development issues; to operate effectively at global, EU and country level; and to respond quickly and flexibly to a rapidly evolving situation. / The proposed new programme outlined here – the Forest Governance, Markets and Climate programme (FGMC) – builds on these strengths. Without continued and expanded DFID support there is a significant risk that the benefits achieved to date, especially through supply side measures to improve forest governance under FLEGT initiatives, will not be sustained; that the growing demand for Voluntary Partnership Agreements will not be effectively met; and that the potential benefits for poor people dependent on forests will not be secured. / The programme will finance private sector specialist expertise and non-government organisations to work with governments in a range of areas: development and roll-out of FLEGT legality assurance systems; timber and agri-business standards and compliance systems; forest fiscal policy (fee, tax, tariff and revenue regimes) and revenue transparency; traceability and chain-of-custody systems; concession allocation and auction; decentralised benefit sharing; independent observation, monitoring and audit; special envoy capacity on treaty issues; specialist legislation; forest land and revenue allocation and distribution; alternative rural and forest livelihoods; company-community contracts related to forestry; community forest tenure and market access forest products and forest-risk commodities; local civil society capacity building in the above areas of expertise, including of local indigenous and forest communities. / Links to REDD+ under the UNFCCC / REDD+ stands for Reduced Emissions from Deforestation and Degradation - with deforestation referring to forest clearance, degradation to heavy logging, and the “plus” referring to increased carbon stocks from forest management, afforestation and reforestation. / During the 2007 Conference of Parties of the United Framework Convention on Climate Change (UNFCCC) in Bali, forests and deforestation became part of the international climate change negotiations for the first time. / Financial incentives are starting to flow to help developing countries reduce emissions from deforestation and degradation (‘REDD’). In May 2010 a pluri-country partnership involving more than 60 countries emerged to focus on actions taken to deliver REDD+ and their financing. The UK is investing in the Forest Carbon Partnership Facility (FCPF) and Forest Investment Programme (FIP) both administered by the World Bank as part of this effort. / The extent to which the private carbon market will grow, and include “forest carbon” is still unclear. These initiatives are unlikely to be effective without sound forest governance that is currently lacking in some REDD+ partnership countries. / Since there is uncertainty about how the mechanisms for financing REDD+ will develop, this programme will not be prescriptive in the way it works. However, it will help deliver REDD+ in three ways: / by feeding lessons on forest law enforcement governance and trade, particularly on relevant actions agreed under specific FLEGT country voluntary partnership agreements (VPAs), to those who represent UK on the participant committees of REDD+ instruments through the programme’s cross-government Oversight Committee. / by promoting dialogue on rights, forest resources and emissions reductions. / by reducing rampant illegal logging and forest clearance in developing countries, it will help them build the foundations for delivery of credible REDD+.
B. Impact and Outcome / The programme will contribute to global impacts of poverty reduction, biodiversity conservation and climate protection through improved management of forests. This will be measured by the deforestation rate in developing countries, and by the value from forests accruing to forest-dependent people in developing countries. / The main outcome of the programme will be reduced illegal use of forest resources and benefits for the poor from governance and market reforms. This will be measured by an index of policy and governance indicators;[24] the quantity and value of illegally sourced timber and other commodities; and the proportion of forests not administered by government, but under private and community tenure. Recognising the rights of local communities and indigenous peoples to manage and benefit from forest lands is critical for poverty reduction, and there is reasonable evidence for this. / There is good evidence from the past decade that market and governance reforms can lead to significant reductions in illegal logging.[25] The direct causal links between illegal logging, forest degradation, deforestation, and biodiversity loss and greenhouse gas emissions, are also good. By contributing to reduced forest degradation and conversion the programme will directly contribute to biodiversity conservation and to slowing climate change.[26] The approach used by this programme - strengthening compliance with existing national laws and changing consumer behaviour- will contribute cost effectively to reducing carbon emissions.[27] / There is some evidence that legalising logging leads to additional forest revenues.[28] By increasing revenue flows from forest taxes, royalties and fees the programme will increase the resources available to local and central government for public services. However, evidence of trickle down benefits from forest revenues to the poor is not as strong.[29] / There is also good evidence that (a) the overall impact of illegal commercial-scale forest operations are negative for poor people, and (b) the poor are significantly dependent on forest ecosystem services, and more dependent than other groups.[30] It follows that reductions in illegal commercial-scale logging and clearance, and the maintenance of forest extent and quality, will benefit forest-dependent people and local communities. / The benefits will be direct and indirect. The programme will improve access and rights to forests for local people. There is evidence that where people have secure rights over trees, this has in some cases increased household incomes by 60% and in others, where rights to precious woods have been assigned, double their incomes.[31] The programme will support local people to have a say on decisions about forest allocation. Where rights are contested, the programme will help countries develop clear legality. This will give less powerful groups a basis for resolving disputes. The programme will also reduce the impact of corruption and conflict on poor people. It will ensure that the benefits from forests are shared more equitably by tracking revenue distribution where there are legal mechanisms for benefit-sharing, and promoting such mechanisms where they do not yet exist. Greater transparency will enable poor people to see how forest revenues are distributed and used. It will enable poor people to better organise themselves and to identify problems and solutions that are in their interest. / In some cases the enforcement of forest regulations can be coercive and negatively impact poor people. Rules may “criminalize” rural people employed in the extraction or processing of forest products or other agricultural commodities. The programme will actively support poor people, who are deprived of their livelihoods by poor forest governance, to make their case. It will also support investigation into best practice where rules benefit poor people. It will provide context-specific evidence on how changes in forest governance that tackle illegal logging and illegal clearance affect different groups. / Overall, there are strong grounds for arguing that poor people will benefit directly and indirectly from a reduction in illegal logging and illegal commercial-scale agricultural clearance, and from associated improvements in forest governance. However, strong direct evidence of these links is lacking. Filling this evidence gap will be a priority for the programme, with substantial budget allocated to evidence gathering, capacity building based on best practice example, and monitoring. / There are also positive lessons from the last several years of work on illegal logging. Both Brazil and Indonesia have taken strides by overhauling their legislation, although there is much still to be done. The programme will extend lessons from carrying out forest sector and timber legality reviews to other sectors and forest-threatening commodities, such as beef, leather, soy and palm oil; as well as lessons from the design and application of timber legality assurance systems. Working on these aspects in these sectors is innovative. Existing evidence of impact from changing standards in these “newer” sectors is still limited and evidence gathering in its infancy.The programme will work to strengthen the evidence base.
[3] Sustaining Forests: A World Bank Strategy. World Bank (2002)
[4] The role of forest protected areas in supplying drinking water to the world's biggest cities.  N Dudley and S Stolton. in Ed. Ted Tryzna. The Urban Imperative.  Californian Institute of Public Affairs. (2005)
[5] FAO Global Forest Resource Assessment. FAO (2010)
[6] Global Forest Resources Assessment. FAO (2010)
[7] IPCC AR4 SPM (2007)
[8] Combating illegal logging and corruption in the forest sector, World Bank. (2006)
[9] op cit.. Chatham House (2010). Estimates based on detailed analysis of production, import and export trade data and a wood balance analysis in a range of countries. The methodology used is described in detail and is the most detailed and provides the best estimate to date.
[10] Global Biofuels Outlook, 2010-202. Hart Energy Consulting; Defra Foresight Project draft findings.
[11] Oilseeds: World Markets and Trade. USDA (2010)
[12] The Economics of Ecosystems and Biodiversity (TEEB). UNEP. (2010)
[13] At Loggerheads? Agricultural Expansion, Poverty Reduction, and Environment in Tropical Forests. Chomitz, K.M. et al. The World Bank (2007). p.23. Where in the range depends on carbon density, price and arbitrage.
[14] The Economics of Ecosystems and Biodiversity (TEEB), UNEP. (2010)
[15] Making African Forests Fit for Climate Change. International Union of Forest Research Organizations: IUFRO. (2010)
[16] Rainforest Foundation Briefing. “McREDD”. Dyer and Counsell. (2010); Governance, Government, Markets and the Transition to a Low Carbon Economy. Gouldson. (2010).
[17] REDD+ Integrity: Addressing governance and corruption challenges in schemes for Reducing Emissions from Defrorestation and Forest Degardation (REDD). U4 Report No 1. Buffin et al. CMI. (2011)
[18] Illegal Logging and Related Trade – Indicators of the Global Response. Chatham House. (2010)
[19] Funding for Forests: UK Government Support to REDD+. PWC/Climate Works/IUCN/Winrock. (May 2011)
[20] PROFOR (2011). Forests and Fragile States -World Bank and US Fund for Peace indices
[21] Op.cit.Chatham House. (2010)
[22] Op.Cit. FAO (2010)
[23] Council Regulation (EU) No 2173/2005 of 20 December 2005 on the establishment of a FLEGT licensing scheme for imports of timber into the European Community; Commission Regulation (EC) No 1024/2008 of 17 October 2008 laying down detailed measures for the implementation of Council Regulation (EU) No 2173/2005 on the establishment of a FLEGT licensing scheme for imports of timber into the European Community; Council and Parliament Regulation (EU) No 995/2010 of 20 October 2010 laying down obligations of operators who place timber and timber products on the market.
[24] Illegal logging and related trade: indicators of the global response. Chatham House (July 2010)
[25] op cit. Chatham House (2010); and a Chronology of 48 documents (1996-2010), which have arisen from and influenced the FLEGT Action Plan (attached to EU FLEGT December 2010 progress report).
[26] Stern Review on the Economics of Climate Change. HMG OCC. 2006; Eliasch Review on Climate Change: Financing Global Forests. HMG OCC. 2008
[27] op cit.. Chatham House (2010)
[28] op cit.. Chatham House (2010) p.98
[29] Poverty Reduction Through Commercial Forestry. Mayers, J. Yale University Research Paper (July 2006)
[30] Op.cit TEEB/UNEP., Ch.3, p.34 and 37. This provides economic valuations of a range of scientifically proven ecosystem services and goods, combining experimental and household survey data in various regions.
[31] In the Sahelien parklands, tree species such as Faidherbia albida, baobab and karité provide income of up to $325 per year for households, together with food, fodder and fertilizer if farmers are allowed to benefit from them and cultivate them. Ref “To Stop Discriminating against Farm Trees”. ICRAF. (2009); Household incomes increased by 60% when Nepalese communities had access to forest resources - Community Forestry for Poverty Alleviation: How UK Aid has Increased Household Incomes in Nepal’s Middle Hills. Nepal Livelihoods and Forestry Programme. DFID/GoN (2008). Peasant farmers doubled incomes when they planted mahogany in Bolivia. Economic Analysis of Small Farm Mahogany Cultivation. Bolivia. CIAT (1994). According to Klooster in “Community-Based Forestry in Mexico: Can it reverse processes of degradation?" Land Degradation and Development. 10(4): 363-379(1999), one Mexican community saw its share of timber profits rise 600% after becoming an independent, legal enterprise, even after doubling wages. Community forestry concessions in remote Guatemala provided profits of $100 to $2000 a year per family. Larsen et al. Tenure Rights and beyond: Community Access to Forest Resources in Latin America.CIFOR. (2008)

Appraisal Case

A. Determining Critical Success Criteria (CSC) / CSC Description Weighting (1-5) / 1 Partnership between EU and developing countries ensures integrity and credibility of the legality assurance systems that are developed 4 / 2 Local ownership of a process that is voluntary and respects sovereignty of each country helps sustain the outcome 4 / 3 Independent observation or verification of reporting against indicators ensures transparency and accountability 5 / 4 Flexible approach that draws on local and external resources provides timely, well targeted technical and financial support to a range of stakeholder; and is responsive to emerging imperatives 4 / [scale: 1 = limited importance; 5= very important] / Four factors are critical to ensuring the integrity of processes and outputs, and the sustainability of the institutions and systems that are put in place. Lack of clarity around rules, roles and responsibilities in the forest sector and of decisions on forest land allocation to other commodity production is common, with evidence that independent monitoring or observation can lead to significant improvements and systemic change. The way current DFID’s Forest Governance and Trade programme is delivered and facilitated has been critical to the success of such initiatives. The new programme will draw lessons from that in its management.
Feasible options / The programme design appraised 3 options: / 0 – No further action (the counterfactual). / 1 – Address illegal logging and related timber markets. / 2– Expand action on legality assurance and supply chain management / systems for timber to also address other commodities, which drive / deforestation and are sourced from illegally cleared forest land / Large-scale programmes investing REDD+ finance might be a fourth option, including direct investment in productive activities by communities, such as tree planting (afforestation) or logging conducted in a sustainable manner that maintains ecosystem services in the long term or non-forest based livelihoods that reduce the pressure on forests or payments for ecosystem services, including for carbon, that result in a switch over time from logging of carbon-dense and biodiversity-rich natural forests to wood production in a smaller area of intensively managed forest plantation. Options for UK support to REDD+ will be the subject of a separate programme appraisal and design alongside, to be considered in conjunction with this proposed FGMC programme. Changing the financial incentives for forest conservation is hugely important. As long as it remains privately rational and profitable for a commercial enterprise to clear forest, and as long as it is able to do so in the absence of effective regulation or control, forests will be destroyed, legally or illegally. That said, large-scale REDD+ programmes are only just starting, and it remains to be seen how effective these will be. Action on FLEGT has already demonstrated that it can reduce illegal logging in several countries - and therefore forest degradation and deforestation – and has potential elsewhere. Restricting the market in illegally sourced forest commodities, and improving forest governance, also changes incentives in favour of forest conservation. Given the scale of the challenge involved in reducing degradation and deforestation, it makes sense to pursue both REDD+ finance and FLEGT. / The “zero option” was rejected. The EU FLEGT Action Plan has increased the international and national profile of illegal logging and is producing results. DFID’s Forest Governance and Trade (FGT) programme, which ends in 2011, has developed an important network and reputation for UK on the issue of illegal logging. / If DFID withdrew, global action to address illegal logging would slow rather than stop. However, for DFID to end its engagement, progress under the EU FLEGT Action Plan, in which UK has made a significant political investment, would be compromised. Without UK’s example internationally in investment in skills, knowledge and support in key developing and processing country partners, this would significantly reduce the ability of the EU more broadly to respond effectively. It would call into question UK’s domestic commitment to implementing the new EU Timber legislation. / This would also slow and undermine the credibility of the international climate change initiative on REDD+, where the need to engage multiple stakeholders in governance processes is critical. Without DFID, less attention to social aspects would increase the vulnerability of poor and disadvantaged populations in a number of forest rich but fragile states. / A variation of the zero option – to continue work as under the Forest Governance and Trade (FGT) programme at the current scale – was considered and also rejected. Such a programme could maintain some of the demand-side momentum for reducing the consumption of illegal timber in the UK and other developed consumer countries, but could only provide significant support for supply-side measures in two producer countries. It would be very unlikely that sufficient EU support would be available to negotiate and implement effective VPA’s in all the producer and processing countries that have expressed interest in entering the FLEGT treaty process, with consequent risks to the FLEGT programme and to the momentum against illegal logging that now exists. / This option would only be able to provide limited support for the necessary coherence between FLEGT and REDD, and could do little to begin addressing the major threat to forests represented by the expansion of agricultural commodities. / Appraising options 1 and 2 informed the decision on whether the scope of the programme should be narrowly focused or broadened. / <Option 1 – description - how will it work – theory of change> / Option 1 continues and expands the support DFID has provided under the Forest Governance and Trade (FGT) programme over the past five years to tackle the problems of illegal logging in developing countries and the associated trade in illegal timber. / The four outputs proposed are consistent with the need to combine UK’s choice and influence internationally with the need to support change in countries. A single approach is unlikely to be effective. The key to success will be the combination of approaches that underpin the “theory of change” behind the outputs and outcome from this intervention: / A focus on legality and law enforcement that reinforces sovereignty; / The power of the market to change the dynamics of the debate (indiscriminate markets help sustain poor governance); / Processes involving multiple stakeholders that help tackle deep-rooted governance issues and coalitions of interest that help maintain momentum; / A formal legal framework (bilateral country treaties and an international (EU) action plan) to ensure integrity of measures. / Both demand- and supply-side market measures willencourage the trade in verified legal timber, and discourage the trade in illegal timber. Output 1 represents the major supply-side intervention. Under this output support for the negotiation and implementation of FLEGT voluntary partnership agreements is expanded to at least 10 countries, with UK providing focused support in up to 10. These will include one or more processing countries that have become increasingly important as conduits for illegal timber imports to the EU and other developed economies. / In each country the programme will deliver effective institutions, involving multiple stakeholders, to oversee, implement, enforce and monitor legal, policy and market reforms and actions. The most visible of these will be the establishment of Legality Assurance Systems guaranteeing that timber has been harvested legally and products are “FLEGT-compliant”. Other actions supported will include clearer and enforceable laws; improved government enforcement; greater transparency; independent monitoring and verification of compliance; and policies supported by business and civil society. / Legality compliance and associated forest governance reforms in producer countries will not happen without demand-side measures to restrict the consumption of illegal timber. These measures are of two types. First, promoting the development and implementation of a package of public and private measures that discourage the trade in illegal timber (Output 2). These include consumer country legislation (notably the EU Timber Regulation, 2010), public sector procurement policies, and private sector initiatives that encourage responsible business practices. Second, providing and communicating sound evidence that enhances common understanding among the public, private sector, NGOs and governments, thereby maintaining the momentum for action (Output 3). / Recent international progress on REDD+ means that a further output is now required: coherence between forest-related programmes at national and international levels (Output 4). Mutually supportive and informed FLEGT and REDD+ are required in order to maximise achievement at purpose level. There is a high risk that individual programmes will – if uninformed by and uncoordinated with other programmes – underachieve or even undermine each other. [32] / The package of supply-side and demand-side measures, within a framework that ensures their integrity, supported by and coordinated with finance for REDD+ and with an emphasis on action-research on approaches that benefit poor people, engagement with the broad spectrum of different political interests around forests, and implementation that learns from monitoring and evaluation, will achieve the outcome of the programme: reduced illegal use of forest resources and benefits for the poor from governance and market reforms. This will contribute to the desired impact: poverty reduction, biodiversity conservation and climate protection through the improved management of forests. / <Option 1 – existing evidence of impact> / A range of forces influences the trajectories of deforestation - commodity prices, road access, labour wages, agricultural and wood processing technologies, and policies and institutions. However, there is credible evidence that the principal public policy concerns, including institutions for more secure tenure and better law enforcement that balance equity, environment and production interests around forests (a contested and valuable piece of real estate ), can account for a third or half of this influence.[33] There is also evidence that innovative institutional approaches to establish checks and balances, transparency, monitoring and participation, such as those promoted by the past Forest Governance and Trade (FGT) project, has impacts.[34] Evidence for the efficacy of using a combination of demand-side and supply-side measures within a partnership process to address the illegal logging and governance problem, is contained in a major study commissioned by the current DFID forest governance and trade programme: Illegal Logging and Related Trade – Indicators of the Global Response (Chatham House, 2010). The report revealed an improving situation in almost all aspects of the response in almost all countries studied. Illegal logging has fallen by 50-75% in Indonesia, Cameroon and the Brazilian Amazon. The report, based on two years of work, collated information from a range of different sources, including trade data, surveys, interviews and was peer reviewed. It attributes a significant part of progress in reducing illegal logging and deforestation so far to the quality of policy design and implementation in the producer and consumer countries studied. Imports of illegally sourced wood to consumer countries are also down 30% from their peak. However, the report emphasised that the problem was far from solved, and that the response needed to be continued and expanded. / Further evidence of the performance of VPA processes to date comes from independent mid term and annual reviews of the Forest Governance and Trade (FGT) programme; some initial studies of the negotiation process in Ghana; internal DFID documentation of VPA negotiations in Ghana, Liberia, Indonesia, Malaysia and Congo Brazzaville; and discussions with EU officials and country level facilitators directly involved in supporting VPA processes in those countries. More systematic and independent lesson learning is needed and will be a priority for the new programme. / Evidence of the positive impacts on poor people from reduced illegal logging is that these are indirect. A number of local studies have confirmed the costs borne by forest-dependent communities as a result of illegal logging and associated weak governance.[35] There is good evidence of the contribution of forests directly to the livelihoods of poor rural households.[36] Reduced illegal logging can reasonably be assumed to lead to reduced costs, and increased forest-derived benefits, for poor people. One of the priorities of the new programme will be to provide better evidence on this issue. / There is some evidence that reducing illegal logging will increase government revenues. A World Bank study in 2002 calculated that illegal logging results in revenue losses of at least $10-15 billion per year.[37] The Chatham House study found some evidence that additional revenues were already being captured as a consequence of the fall in illegal logging.[38] / Option 1 is categorised as grade A (high potential opportunity) with respect to climate change and the environment. The Chatham House report highlighted the potential for a reduction in illegal logging to contribute directly and cost effectively to reducing carbon emissions by reducing forest degradation and deforestation. The evidence for the significant contribution of reduced forest degradation and conversion to addressing climate change is contained in the Stern and Eliasch reviews.[39] / Option 2 involves all the components of Option 1, but further expands the scope of the programme to include agricultural commodities other than timber. / There is strong justification in pursuing Option 2, not least to strengthen the link between forest governance and the drivers of deforestation as part of the REDD+ agenda, in other words, to reduce emissions from deforestation as well as degradation. / Work to address other illegally sourced commodities follows the same intervention logic as for timber, but is at an earlier stage. The premise is that there are similarities in the institutional (both governance and market) factors that drive illegal timber and those that push agricultural commodities to be grown on illegally cleared land, and hence similarities in the approach required to address both. Currently the use of voluntary private standards and corporate social responsibility is the main approach to improving the sustainability of the production and supply chains of palm oil, soy, beef and leather. Impacts so far have been patchy. This was the case with timber a decade ago. / The programme will apply a similar mix of demand-side and supply-side measures focussed on legality and involving action by governments, in order to reduce and eventually eliminate the illegal forest conversion associated with large-scale agricultural commodity production. This will have a greater and wider impact on the scale and pattern of forest conversion than the voluntary private initiatives currently in train. / This programme under Output 1 (stakeholder processes and action in producer countries) will work to lift some of the institutional and governance barriers that prevent oil palm farmers (including small-scale) from accessing finance to improve their production systems without illegally clearing forests and inhibit soy and beef producers from maintaining legal forest reserves on their farms. It will focus on clarifying jurisprudence and information on land and forest conversion, where this is a major barrier to investments in legal and sustainable production. / The programme will explore the feasibility of innovations such as pre-titled land leases or swaps. There are moves to try and pilot this in palm oil in Indonesia. It will help key commodity sectors in different countries to assess and review the "sector's legality" as a first step to identifying where unclear or poor legislation actually enables illegal practice or constrains business. Improving labour conditions, particularly where gang and women labour is employed, will be another key element. / The programme will also improve knowledge amongst farm and agro-commodity businesses, and help aggregate local producers into organisations that can better meet mandatory market standards. It will support them to comply with rules and requirements for accessing existing credit; and help establish institutional arrangements for new finance lines (including REDD+ farm funds), linking remoter farmers to these products. It will help farmers and businesses with legal, environmental or sustainability assessments (legality assurance) along their production, processing and marketing chains where this brings market advantage and reduces their risks. This will benefit about forest dependent communities, and about 50 million farming men, women and children, as well as and 10 million or more plantation and ranching workers and employees.[40] / Work on soy, palm oil, beef and leather under Output 2 will include actions by consumer countries that reduce the demand for illegal sourcing of these commodities by increasing public, business and political awareness and hence helping businesses meet legal standards enshrined in public procurement policies; import legislation; and voluntary standards by private business. The US and some EU member states have these for illegal timber and work has started on the legal aspects of voluntary sustainability standards, with The Netherlands leading the way by starting to track the legality and sustainability of palm oil entering its ports. / Under Output 3 the programme will carry out research, analysis and knowledge sharing on palm oil, soy and beef commodity sectors initially to scope the scale of illegal agricultural conversion and the potential of different demand and supply side actions. The UK government is already mapping the UK palm oil supply chain.[41] This is similar to the approach first adopted by DFID in addressing illegal logging in the late 1990’s and early 2000’s. Research and outreach on illegal logging, and support to pilot approaches in train, was essential for building the evidence base for action and in fostering the level of awareness and support among the public, private sector and politicians. / The programme will consider how the markets for agricultural commodities that drive deforestation vary regionally. Palm oil is a major driver in South Asia and is starting to drive large scale forest clearance in Africa. Soy, sugar and beef are major drivers in Latin America. In some countries shrimp markets drive deforestation, particularly of mangroves, with un-shaded plantation cocoa and coffee, as well as livestock production and biofuels, playing a role in parts of Africa. / The programme will focus initially on palm oil, soy and beef where there are significant first attempts to review legality and pilot legal compliance of production in these sectors in developing countries, and where there is already progress in establishing voluntary business standards which try and build consumer confidence in these commodities. / Different agricultural commodities drive illegal forest conversion in different regions and so impacts of successfully tackling this problem would be concentrated in those countries. Tackling illegal logging of timber has wide-ranging impacts in all forest producer countries. The structure of the timber industry is very different from that of palm oil, for example, with timber extraction carried out by more and more fragmented enterprises, whereas palm oil production and processing involves fewer operators, although there is less information on the intermediary investment involved. The programme will support study of the agricultural commodity industry and trade (as was done for the timber trade a decade ago) in order to tailor the approach it uses. / It will also compare the experiences in both timber and other sectors, such as palm oil, of tracking a commodity that is segregated and has differing degrees of visibility in the end product that reaches the consumer. For example, oil palm is processed into a great range of first stage products and end products and is less visible to the consumer than many processed wood products. / There may be costs associated with reducing agricultural commodity production on illegally cleared land in terms of employment for poor people and smallholder incomes. In this case the programme will help countries legalise land conversion or develop economic activities on already degraded or cleared land. The nub of the programme will be to ensure that countries and markets, businesses and consumers have sufficient evidence on which to base decisions on production and purchase, and transparent processes by which to take these decisions. It will help countries develop sound policies, due processes and transparent systems that allow them to decide legitimately how much forests to convert to other uses and how much to keep. / Output 4 (coherence with other forest and deforestation related programmes) will review programming and policy in the agriculture sector and related market and infrastructure development. Modifying a range of agricultural policies can reduce deforestation at the same time as contributing to food security, for example, subsidies for intensification of productivity and pricing of commodities grown on legally cleared land; policies that encourage growers to combine arable crop with tree farming and consumers to purchase legally produced palm oil or beef grown on farms that respect legal forest reserves; and clearer titling of degraded land and more rational land use plans. The programme will build links between stakeholders working on forest governance with those working in other sectors to review key elements of policy in the palm oil, soy, beef and leather sectors. / The core approach of the programme is to achieve a combination of “demand-side” actions in consumer countries and “supply-side” actions in producer countries. These will result in reductions in the consumption and production of illegal timber and agricultural commodities grown on illegally converted forest, and to improvements in the governance of forest resources in producer countries that benefit poor people. The impact of this will be to improve the management of forests with benefits for poverty reduction, biodiversity conservation and climate protection. / Broadening the scope of the programme to cover other forest-threatening commodities such as beef, soya and oil palm is innovative. It extends the positive lessons from the last decade of work on illegal logging, and meets a strong demand from environmental and development NGOs and local communities to address the threat posed by agricultural commodities. / Option 2 shares the same evidence base for illegal timber as does Option 1. However, because the issue of agricultural commodities grown on illegally converted forest land has not yet been widely addressed, the existing evidence on this issue from previous interventions or research is limited, with some initial legality scoping of legality in palm oil carried out in Indonesia.[42] The approximate scale of the problem is known. Deforestation is running at 13 million hectares per year.[43] Large-scale and medium-scale agriculture accounts for around half of this.[44] Two studies suggest that a half or more of this clearance contravenes national regulations and laws.[45] / As was the case with timber before the FLEGT Action Plan, current work on other commodities concentrates on voluntary initiatives to improve the sustainability of their production through private certification standards and corporate social responsibility. Most of these initiatives are aimed at the higher standard of sustainability rather the initial lower standard of legality. Although some progress is being made,[46] evidence of far reaching changes in practice on the ground from such certification initiatives is still limited, except insofar as increasing interest demonstrates a growing momentum around the issue. However, two initiatives in Brazil – the Soy Moratorium and government action on illegal deforestation for cattle development – have successfully reduced deforestation pressure by addressing illegal conversion.[47] / Because of the innovative nature of option 2, there is limited evidence relating to the poverty impact of improved practices in agro-commodity production stemming from this approach. As with illegal logging, there is good evidence of the negative impact of existing illegal social and environmental practices associated with agricultural commodity production, which the programme would hope to undo or mitigate. For example, in Indonesia there have been 260 registered violent conflicts around palm oil plantations specifically. Here and in other countries legal frameworks for such plantations (and not just palm oil) enable companies to create monospsonistic relations with mills, develop labour employment schemes that indebt or force labour, and involve unclear leasing or titling processes.[48] On the other hand, large numbers of rural people are employed in the production and processing of forest and agricultural commodities, albeit often on very poor terms and conditions. Improving the evidence on the poverty impacts of restricting the illegal expansion of commodity production will be one of the priorities of the programme. / Option 2 is categorised as having “high” potential opportunity for positive impact on climate change and the environment based on a “medium” level of evidence. In addition to the impacts following from a reduction in illegal logging (or forest degradation), reducing the illegal clearance of forests will directly reduce deforestation with potentially a greater impact on mitigating climate change than just tackling degradation or illegal logging. However, the evidence base for the degree of impact from taking this approach is not so strong. / Option Evidence rating Climate change and environment category (A, B, C, D) / 1 Address illegal logging and related timber markets Medium A (High opportunity) / 2 As above + action to address other illegally sourced commodities Medium overall; Weaker evidence on approaches to tackle agro-commodity driven illegal forest clearance A (High opportunity for impacts on illegal degradation in all countries; Medium and focused in fewer countries for other commodities)
	C. Appraisal of options / Option 2 is recommended: that the programme addresses illegal logging and related trade while broadening its scope to address other commodities, such as palm oil, soy, beef and leather, which are sourced illegally. / The economic case and value for money / The economic case is robust for Option 1 (address illegal logging only) even with full costs and conservative benefits.[49] A medium impact scenario, which assumes that illegal logging leads to deforestation but half of clearance is diverted elsewhere, gives a benefit-cost ratio of £38 for every £1 invested in the intervention (38:1), and an internal rate of return (IRR) of 218%. / Incremental costs and benefits for the base case have been discounted over a twenty-five year period (2011-2035) using a discount rate of 3.5%[50]. The Internal Rate of Return (IRR) – the discount rate which gives a Net Present Value (NPV) of zero[51] – has also been calculated. Discount rates are higher in partner countries, typically between 8% and 15%[52]. Sensitivity analysis was therefore carried out using two higher discount rates. These and the IRR’s show that the results are insensitive to the choice of discount rate for all except the most pessimistic scenarios. / If timber logged illegally is logged legally in the same location or elsewhere, and taxed, the governments concerned benefit from additional forest revenues collected. The net present value of the additional forest revenue captured by developing country exchequers is estimated at between £2 and £13 billion over the period to 2035 depending on the impact achieved. / Twelve alternative forest degradation and deforestation scenarios were developed to appraise the economic impacts of reducing illegal logging. Avoiding illegal logging of between 126 and 272 million cubic metres of timber by 2020 will protect between 6 and 14 million hectares of forest from degradation (medium and high scenarios). This leads to reduced forest degradation and deforestation, with consequent environmental benefits in terms of ecosystem services, notably carbon storage. Tackling illegal logging alone averts the loss of 70 tonnes of CO2e emissions per hectare of natural forest and avoids the loss of other forest goods and services valued at £15 per hectare.[53] If illegal logging leads to deforestation, which is often the case, these losses increase by a factor of 12. The scenario for the central case for Option 1 assumes that a reduction in illegal logging will protect 22 million hectares from deforestation by 2035, averting the loss of 845 tonnes of CO2 e emissions per hectare and the loss of £182 per hectare of other forest goods and services. Poor people dependent on forests benefit directly and indirectly from the forest ecosystem services retained if illegal logging is controlled. / The cost per tonne of CO2 averted is less than £3.50 under all the medium scenarios (and under £10 under the most pessimistic scenario). This compares with a current market price for European Emission Allowances (EUA) of around £13 per tonne, and a shadow carbon price of between £25[54] – £50[55] per tonne CO2. / Carbon dioxide was conservatively valued at the current market price for European Emission Allowances (£13 per tonne). The economic model[56] was also run using higher shadow carbon prices of £25 per tonne (Defra[57]) and £50 per tonne (DECC[58]), and using the inflated 2010-2050 series of traded carbon prices provided by DECC which rise from £14 per tonne in 2011 to £103 per tonne in 2035.[59] / Option 2 will generate the same benefits as Option 1, and additional benefits from a reduction in illegally-sourced agricultural commodities. Forest loss is currently 13 million hectares per year, around half of which is due to clearance for medium/large scale agriculture. Without the programme, deforestation and agricultural clearance is assumed to halve by 2030. This is midway between the EU target (zero by 2030) and an unchanged rate of forest loss.[60] / In addition to reducing illegal logging, Option 2 averts the illegal conversion of between 9 and 26 million hectares of forest to beef, soya bean and palm oil over the period to 2035 (low and high scenarios). The scenario for the central case averts the illegal clearance of 17 million hectares of forest by 2035. Assuming half of illegal forest clearance is diverted onto degraded land, this option avoids the loss of 845 CO2e emissions per hectare of natural forest that is not cleared, as well as the loss of a further £182 per hectare of forest goods and services. However, if cash crops are diverted onto degraded land, there may be some displacement of subsistence crops. Nonetheless any benefits that might be lost by subsistence farmers from large scale agricultural land acquisition of degraded land may not outweigh the lack of compensation to those losing resources from natural forest cleared for large scale plantations. It is worth noting that there is an ample area (446 million hectares) of non-cultivated land globally, including in Africa, suitable and available for cropping, and which is non-forested, non-protected and populated with less than 25 persons/km2 (or 20 ha/household). This is equivalent to almost one third of globally cropped land (1.5 billion ha).[61] Nonethelessthere will be increased competition for land in the future. Even taking into account expected agricultural yield increses, estimates suggest that the world in 2050 will require expansion of agriculture onto 120-200 million hectares of land, including on current trends, an additional 12 million hectares of oil palm.[62] The programme will ensure that poor people are not disadvantaged by measures to control illegal large-scale agricultural conversion. It is also assumed that agricultural yields or productivity increase on legal commodity enterprises (i.e. there is more intensified production) and that this also helps reduce pressure on forests and avoid forest conversion. / The economic case for Option 2 tackling illegal logging and forest clearance from other commodities) is stronger than the case for Option 1. A medium impact scenario (deforestation with diversion) has a benefit-cost ratio of 52:1, and an IRR of 234%. The most pessimistic scenario (low impact, degradation with diversion) has a benefit-cost ratio of 12:1 and an IRR of 65%. The cost per tonne of CO2 averted is less than £ 0.5 under all the medium scenarios (and under £1 for the most pessimistic scenario). / Total incremental costs of £3.8 billion over the next ten years are based on a maximum UK cost of £250 million[63] (See Financial Case), together with further associated private sector contributions, as well as from inputs from the EU, China, USA, Japan and other countries. / The total of £3.8 billion in incremental costs compares with a Chatham House estimate of £1 billion to £3 billion spent over the past decade on efforts to prevent illegal logging, including efforts by Japan and USA. The next ten years will need a similar global effort to continue the reduction in illegal logging (79% of costs) and the start of a global effort to begin the reduction in illegal large-scale agricultural clearance (21% of costs). / The economic case for the programme is relatively insensitive to these estimates of global costs. Costs would need to increase by a factor of 12 to more than £45 billion for 2011-2020 for the worst case Option 2 scenario to reduce to merely break-even. / A conservative market price of £13 per tonne CO2 is used. There is a good case for using a higher shadow carbon price of £25 – £50 per tonne CO2. Using the higher of these gives a benefit-cost ratio of 38:1 and an IRR of 23% for the worst case Option 1 scenario, and a benefit-cost ratio of 47:1 and an IRR of 136% for the worst case Option 2 scenario. / Key governance, political and social appraisal issues[64] / Political economy and corruption / Governance of the forest sector in many poor countries is a microcosm of broader governance problems. Political competition for forest resources revolve around informal, personalised relations between political and economic elites. In some countries stability relies on the creation of economic rents from forests in exchange for political and financial support. Bureaucratic capacity, judicial oversight and democratic accountability are weak, and there are few incentives and opportunities for collective action by less powerful groups. / The result is systemic corruption; exclusive private benefits for a few; weak incentives to protect the livelihoods and rights of poor people or to create public goods (especially public goods such as emissions reductions and protection of biodiversity that are relatively intangible and long-term); and weak capacity to manage competing private interests or the balance between public and private interests. / Particular opportunities for corruption include payments from timber companies to members of the military, politicians and senior officials to obtain timber concessions or approvals for timber processing, and to avoid the payment of fines, fees and taxes (so-called "grand" corruption); and bribes paid to more junior officials and military personnel, for example to provide false documentation relating to harvesting, movement, or export of timber, or to overlook non-compliance with formal regulations (so-called "petty" corruption). / The programme will help countries and organisations toput in place measures to gather evidence, publish information, strengthen judiciary and enforcement capacity that reduce the bribery or extortion, which has major impacts on revenue collection, with a focus on bringing significant cases to book that, by their example, will change behaviour more widely, and on those that negatively impact low income households. Paying small bribes can represent a higher share of poor people’s total income than for better off households or enterprises. Poor smallholders may be asked to pay bribes in exchange for “permission” to clear forest land for smallholder soy production or to rear a few cattle. / Unclear legality and transparency / There is often a lack of clarity about the legal framework governing the use of forests, and about benefit sharing arrangements, tenure and use rights; an uneasy mix of customary and statutory law; and widespread non-observance (and often lack of legitimacy) of formal legal provisions. Where enforcement does take place it may be arbitrary, or coercive. / In some countries, weak central government control over local authorities, or high levels of autonomy for decentralised regions lead to divergent laws and policies between national and sub-national levels of government. / By helping countries clarify the definition of legality and establish a legality assurance system, the programme helps a country shed light on the way it allocates its forests to different uses and in whose benefit. It helps countries place this information in the public domain. / Drivers of change / This programme will build on two drivers of change. First, NGO and private sector backing, which has already driven changes in the main consumer markets (principally the US and EU), and provided incentives for producer countries (including Indonesia, Cameroon and the Brazilian Amazon). / Second, skilful design of voluntary partnership agreements (VPAs) under the EU FLEGT action plan which has created locally driven, multi-stakeholder processes in producer countries that bring together government, business and civil society actors, enabling them to reach a common understanding of forest governance problems and identify shared interests in addressing them. The process already has local “ownership”: it is voluntary, and respects the sovereignty of the country which must reach its own definition of "legality" (the focus on “legality”, which is much easier to define and verify than “sustainability”, has facilitated agreement). / These drivers bring reputational pressure to bear on governments and business. They create shared government and private sector interests in secure or improved access to key markets. They align these interests with civil society concerns to protect the environment and the interests of forest dependent and indigenous communities. All stakeholders benefit from increased organisational capacity, stimulated by the demands of the FLEGT treaty negotiation and implementation process and supported by external assistance. / But looking ahead, the scope for relatively “easy wins” is diminishing: tackling less tractable aspects of the illegal logging problem, including harvesting by small-scale concessionaires for the domestic market, or over-cutting in licensed areas, requires a more thorough overhaul of government policy and regulation. Hence the importance of treaties or VPAs in the approach. / Treaties or Voluntary Partnership Agreements (VPAs) as an approach / Voluntary Partnership Agreements (VPAs) have the potential to increase transparency and accountability, and to achieve a better balance between public and private goods, more equitable distribution of private benefits, and more civic ways of managing conflicting interests. But the gains to date remain fragile, and implementation by countrieswill bring different challenges from the negotiation and agreement of actions. In many poor producer countries civil society is weak and fragmented, and there are significant constraints within the forest service and government more generally in terms of capacity to design and implement effective policy. This is why a major element of the new programme (Output 1) will build on the experience of DFID’s Forest Governance and Trade project, to support, in addition to negotiation, the implementation of a growing number of VPAs. / Implementation of a credible legality assurance system is a priority, and involves a direct challenge to the private interests driving corrupt behaviour arising from allocation of timber concessions, movement of wood products and imposition of fees and taxes. The VPA, as a formal treaty, imposes concrete obligations on signatories, with related monitoring requirements. Reporting against indicators must be independently verified and transparent, and covers tax compliance, legality (including the processes by which forests are allocated), as well as community forest use and rights, where this issue is covered in national legal frameworks. / The VPA process also offers the potential to move beyond the narrow issue of legality of exports to the EU, and to secure broader improvements in forest governance. For example: the annexed chapter in the agreement identifies the need for future reforms to the legal framework; and the VPA "do no harm" provision provides an entry point to pursue community rights. / Evidence, research and stakeholder participation / In addition to supporting negotiation of a growing number of new VPAs, DFID assistance through the programme will support broader EU efforts to strengthen implementation, in two main ways. It will provide funding, access to research and policy ideas based on experience elsewhere (for example on how to tackle small-scale logging for the domestic market), and support for strengthening technical and organisational capacity. / Experience under the Forest Governance and Trade project highlights the importance of a flexible approach able to draw on local as well as external resources to provide timely and well targeted access to technical and financial support for a range of stakeholders including very local level community based organisations, NGOs, parliamentarians, and the private sector as well as government. / The process of negotiating and implementing a FLEGT VPA involves all affected parties, including a wide range of stakeholders from grassroots organisations, to local NGOs, domestic and exporting market associations and companies, as well as government bodies. However, the relative capacity and bargaining power of different groups varies. / This programme will build the capacity of associations representing remoter, smaller and fragmented businesses and interests, including those that involve large numbers of poor people (e.g. carpenter furniture-maker or women bark-stripper associations). It will enable social civil society and trade networks to help their local developing country peers represent and communicate their members’ interests better. / As the programme extends to other commodities it will help smallholder bodies participate in national structures such as palm oil boards and soybean federations. / Role of EU in ensuring integrity / It can help sustain the active interest and engagement in VPA implementation of government, business and civil society stakeholders by using the EC’s leverage as a treaty partner to protect the integrity of the process, and in particular by helping to strengthen civil society participation. / Continued, active engagement of all stakeholders is crucial: for example monitoring of timber allocations and the legal arrangements governing them requires civil society to remain alert and involved; addressing the problem of chainsaw logging for the domestic market requires sustained pressure on government from business, and civil society. The EU, with DFID support, has a critical role to play in ensuring that broader forest governance reforms, including those that could benefit poor people, stay on the agenda. The EU also plays a key role in trade and climate related policy, where particular competencies are shared between the European Commission, Parliament and Member States. / Applying the approach to other commodities beyond timber / From a political economy perspective, there are a number of similarities between timber and internationally traded agricultural commodities such as beef, soy and palm oil. There is increasing awareness of the link between these commodities and deforestation, and the implications for climate change; and increasing NGO pressure on the private sector and governments in consumer and producer countries. / Investment decisions will be easier, raising capital and finance easier and marketing of agricultural commodities easier, if business and consumers know that products have been legally sourced and produced on forest land that was not cleared illegally. / A recent evaluation by the World Bank on forests and low carbon development[65] concluded that a strategy for beef and bean in the Amazon reliant only on voluntary private sector initiative had been problematic and difficult. A combination of pressure from buyers, independent monitoring of enforcement, NGO engagement and clear government legal framework combined with national sanctions for non-compliance proved more effective. / Some of the same contextual problems apply as for illegal logging, for example the increasing importance of emerging markets such as China. These similarities suggests that there is potential for applying some of the demand and supply side measures that have played a part in reducing illegal logging to addressing the issue of deforestation linked to production of agricultural commodities. But addressing commodities involves additional challenges, including the fact that commodities have greater economic importance, involve more stakeholders, and can have more complex trade regimes and supply chains. / Tens of millions of poor people are employed as smallholders and in agro-industry related to livestock, soy and palm oil (with over 15 million people in the oil palm smallholder sector alone[66]) but there are significant variations between commodities and regional markets. For example, soybean cultivation and its processing into animal feedstock employ less labour than oil palm cultivation and palm oil processing. The programme will help communicate best practice (e.g. improved seed stock, inter-cropping, cover crops, small-scale mills, and mobile card harvest schemes to guarantee employment, small-scale mills) that benefit small farmers, including “loose fruit” schemes that give special palm fruit cutting rights to women.[67] / Palm oil, soy and beef enterprises that establish themselves illegally are less likely to follow labour and employment laws, particularly when it comes to protection for labour gangs employed in burning to clear land or herbicide spraying or harvesting. In some cases gang labour in illegal activities suffers near “slavery” conditions.[68] The programme will help ensure that labour laws are understood and applied. / The programme will support analysis on the dynamics of land conversion in different countries, and the characteristics of associated markets. It will help review the legal steps and procedures which act as barriers to market entry for smallholders or which “criminalize” those who engage in the market. / Palm oil, soy and beef markets include significant smallholder supply and production sectors. Establishment costs for commodity production are reduced by illegal forest clearance, particularly for large scale but capital-intensive producers. In addition, commodity production that results from opaque and speculative deals is less likely to employ existing communities than legally established business. Indeed the former tends to result in eventual dispossession, particularly of forest dependent people whose social organisation is less recognised by formal political and legal institutions. The programme will promote business partnerships involving small holders and communities that bring benefits and employment into the local area. / Forest dependant peoples / More than 1 billion poor people depend to varying degrees on forests for their livelihoods, with many more depending on the ecosystem services they provide. About 60 million indigenous people are almost wholly dependent on forests. Some 350 million people who live within or adjacent to dense forests depend on them to a high degree for subsistence and income.[69] Many of these practice swidden[70] agriculture, tree farming and wild food gathering. Forests provide the basic goods and services for sustainable livelihoods and guard against vulnerability. / The predominant social impact of forest degradation and deforestation is on the security and well-being of the poor. Case studies in Brazil, Indonesia and India found that ecosystem services and non-market goods accounted for between 47% and 90% of the total income of the poor.[71] Illegal logging deprives poor people of this income and their livelihoods. / Revenue collection and distribution / The FLEGT treaty or VPA agrees binding actions that benefit poor people; for example, the percentage of tax revenues that are collected and redistributed. The programme will ensure that laws and rules on benefit-sharing with communities are communicated to poor people and are understood by them. It enables them to scrutinise systems, and identify problems and solutions that are in their interest. / Forest tenure, rights and gender / The programme, through the VPA, resolves problems of implementing existing regulations on community or village forest use and rights. Where a country’s legal framework does not include such regulations, the programme allows stakeholders to place community tenure and use rights on the agenda as well as other rules that protect the role of forests for social welfare purposes. Furthermore roles, rights and access to forest resources and markets are very different for men and women (gender-differentiated) and vary greatly from culture to culture. This programme will support women, men and minority ethnic groups to air their views about which tenure and legislative arrangements best meet their needs. / The majority of the world’s forests (between 70-80%) are under State as distinct from private or community control. Forest land is highly, although not effectively, regulated.[72] Research from countries like Mexico, China and Bolivia indicate that secure forest tenure has led to increased revenues to local people from forests including timber harvests.[73] / It will support poor people so they are able to have a say about their rights and their responsibilities in relation to forests in such a way that it benefits their livelihoods. In some countries there are regulations that control the planting of trees on farms. The programme will focus on the process of defining legality where there are provisions for modification to regulations that control or forbid the harvest of trees or tree products by small farmers and communities even if they own the land. This will increase income earning opportunities and reduce the hurdles in taking such products to market. The programme will monitor whether these modifications are implemented, complied with, and their impacts on poverty. / Alternative livelihoods / A VPA treaty cannot include any liability for the EU to pay for decommissioning or for compensating non-legal operators. Nor does it oblige the EU to provide expanded alternative livelihoods development projects in the event of major sector restructuring arising from legal reform (although REDD finance from elsewhere may). However, the programme will actively help countries develop evidence-based policy prescriptions that increase benefits to the poorest from the forest sector, and where the sector requires restructuring, help develop options that would generate alternative livelihoods outside the forest sector. / The programme will contribute to establishing poverty baselines and poverty reduction impact assessments, as well as providing legal advisory services to more vulnerable groups. This will enable governments and other stakeholders, including forest communities, associations of chainsaw operators and tree farmers, to calculate the costs and benefits of legal reform, contest decisions and pilot alternative livelihood approaches where appropriate. / Safeguards, winners and losers / Successfully addressing illegal logging will create losers as well as winners and may incur costs for some of the rural poor, for example, in countries which have large informal chainsaw industries, such as Ghana and Cameroon, which may not be “legalised”. The VPAs include a social “do no harm” safeguard with mandatory obligations on both parties to monitor the impacts on poor people and on these groups, thereby creating an incentive to formalise them within the legal framework. The programme will help the EU and countries find solutions to the illegal logging problem that are “equitable and just” and “do not have an adverse impact on poor people.”[74] / It will also build and strengthen different stakeholder groups, particularly of small businesses, women and poorer communities engaged in forest activities, so that they are able to negotiate and implement changes that benefit them. It will strengthen civil society and governments so they can effectively monitor the direct and indirect impacts of the changes in legality of logging in the countries concerned, and design and implement measures which mitigate negative impacts and maximise positive impacts for poor people. / The illegal conversion of forest land for agriculture can also have positive and negative impacts for poor people. The EU FLEGT action plan acknowledges the need to differentiate between the activities of small-scale farmers trying to earn a livelihood and large-scale commercial enterprises, which, sometimes in partnership with politicians, use power and influence to avoid due diligence, seek legal loopholes or circumvent the law, in order to clear large areas of forested land. The programme will focus on the latter in the way it helps countries tackle illegality. / Many of the same issues that apply to illegal logging also apply to large-scale illegal conversion: the limited information available; the importance of forests to the poor; the costs to the poor of forest degradation and conversion; the existence of winners and losers in any legal reform and the struggle for depleting and valuable resources such as forests; and the importance of better understanding and an effective multi-stakeholder process. / The programme will provide more rigorous analysis of the scope and scale of illegal clearance and how this impacts on those dependent on forests and small farmers on the one hand, and on agro-industry, on the other. / Impacts on the environment / Illegal logging causes environmental damage. It contributes to the loss of biodiversity and to the illegal exploitation of wildlife. Unregulated logging can significantly increase the vulnerability of forests to fires; and aggravates the impact of flooding and sedimentation on neighbouring areas. / Illegal logging is environmentally damaging, for example, it often flouts rules (laws) on species limits, i.e. which trunk diameter sizes or tree species to cut and leave; or on reduced impact logging techniques; continuous canopy cover planning; maintenance of seed or “mother” trees; and forest gap and wildlife management. Maximum environmental damage is obvious, for example, where illegal timber is taken from national parks; or where timber theft is associated with large scale clearance that ignores environmental impact assessments and involves, for example, unplanned bulldozing of roads and disturbance to major drainage or river systems. / On balance, despite a lack of global data, it is safe to assume that reducing illegal logging has and will be environmentally beneficial. As indicated in the economic analysis above, conservative assumptions still generate significant ecosystem benefits. / While illegal logging may or may not be a contributory factor in deforestation (although evidence suggests that logging trails open forest up to agricultural clearance in some countries), this is not in doubt for illegal clearance for agricultural commodities. The environmental costs of large-scale illegal forest conversion are substantial. Around half the deforestation in the eight countries accounting for 75% of global deforestation is due to medium to large scale beef/soya/oil palm conversion.[75] The percentage of clearance that was illegal is not known. However, two studies in Brazil and Indonesia put the figure at 48 - 82%.[76] / As with illegal logging, it cannot be assumed that averting illegal clearance means that legal clearance will not take place in the same location or elsewhere, although with different environmental impacts. The increasing demand for agricultural commodities makes this inevitable. However, this programme will ensure that legality review provides opportunities to specify environmental standards more clearly, and create policy incentives, for example, for higher biodiversity in plantations with forested corridors to facilitate wildlife movement and reduced agro-chemical applications. / However, even if the effect was merely to divert a portion of the illegal clearance without changed management from high value primary forest to lower value primary forest, secondary forest, or degraded land, the environmental benefits would be substantial. The constraint imposed by the improved regulation of new clearance will also encourage higher yields and intensification on existing agricultural land. / Building linkages between FLEGT and REDD+ / The Forest Governance Markets and Climate (FGMC) programme builds “FLEGT-REDD+linkages”. There are two aspects of governance in relation to markets and climate and described by the EU as “FLEGT-REDD+ linkages”. One is the governance of REDD+. This covers the broad area of governance around carbon emissions financing schemes and monitoring systems, as well as of significant economic sectors that involve deforestation like mining, agriculture, infrastructure, energy, and a country’s whole national spatial land use plan. The second is a subset or microcosm of economy-wide governance and focuses on governance of the forest sector and forest-related markets or FLEGT. / The governance aspects of “REDD+ readiness” involve inclusive and effective stakeholder participation in cross-sector planning and implementation; government coordination across different sectors and levels of government on REDD+; transparent and accountable systems for managing and distributing REDD+ finance and benefits; effective and transparent monitoring and independent national oversight bodies for REDD+ (particularly of REDD+ financing or accounting schemes and carbon monitoring); creation of REDD+ carbon baseline data; reporting on public and private finance for REDD+. / FLEGT links to REDD+ by establishing clear roles, rights, regulations and responsibilities around forest concession allocation, tenure and conversion, including agriculture and plantation leasing; reform of national forestry taxation systems and formalisation of ownership or profit rights from forest; addressing rents from land uses that replace forests (e.g. palm plantations); improving the standards and behaviour of the markets and trade that drive these processes; strengthening civil society, community and private sector accountability institutions, independent monitoring, as well as statutory oversight institutions; building the capacity of state prosecutors, formal anti-corruption institutions, judges, law enforcement agencies, court officials, trade and customs inspectors. / By building linkages between FLEGT and REDD+, the programme will ensure that delivery of REDD+ is sustainable and credible. It will do this by helping businesses, countries and regions to: / Review the legal frameworks for their forest, palm oil, soy and beef sectors, focusing on laws governing forest allocation and conversion to improve their clarity and coherence; / Review their forest tenure arrangements and labour standards, including on farms; / Map their commodity trade and supply chains in relation to “forest-risk”; and market roadshow their certified and legally licensed products; / Apply community mapping approaches where appropriate; / Develop standards and traceability systems, which provide assurance that commodities sourced from forest sectors and others that drive forest loss are legally compliant along the complete producer-to-purchaser supply chain; / Ensure traceability technologies are appropriate and cost effective, particularly in countries and remoter areas where infrastructure is weak or private sector poorly developed; and that they take into account product segregation during harvest, processing and shipment; / Ensure legal and forest governance compliance is audited and independently verified or monitored, including by third-parties (whether private or non-government), including the monitoring of commodities from sources where forest dependent peoples; tenure are clear and secure; / Transparently disclose information on logging and deforestation, as well as forest-related finance, revenue collection, benefit-sharing and fiscal systems; where relevant coordinate with Extractive Industries Transparency Initiative (EITI); / Cross-check information on “harvested wood products” and traded forest products, used in Tier 1,2 and 3 systems for forest carbon emissions (REDD+) monitoring reporting and verification (MRV) (as per guidance of the Intergovernmental Panel on Climate Change (IPCC)), for integrity against illegal logging and related trade datasets; / Build effective national and sub-national forest-related multi-stakeholder institutions, forums and processes; and support approaches that are participatory and consultative involving communities, smallholders and companies / Create integrity in oversight bodies, linking those for FLEGT with those being established for REDD+, and fully embed these and their related implementation committees into key national institutions; / Harmonise points of delivery and decision-making in country. / In countries which have agreed implementation of FLEGT Legality Assurance and disclosure Systems (LAS) focused on timber, wood and paper (TLAS), the programme could broaden these to other commodities or goods, depending on the different nature of trade regimes (domestic, regional) and the location and nature of the drivers of deforestation (soy, palm oil, beef, leather). / The programme will not be prescriptive about expansion to further countries or regions and will coordinate with the EU donor Working Group on FLEGT-REDD (which includes Norway and Switzerland). / Given the range of potential options for broader UK support to REDD+, this programme may vary its own approach in different countries to complement REDD+ action. This might range from high-level political intervention through UK REDD+ to stipulate progress on implementation of FLEGT as part of any REDD+ partnership, to negotiating a new VPA with a REDD+ country where there are EU trade links, linked to UK support for REDD+ planning (Phase 1), to expanding the FLEGT approach to other commodity areas where other drivers are more prevalent, or trade links with the EU less clear. / The way that the two programmes come together in-country, and the manner in which they are presented by the UK government, will vary on a case-by-case basis, and be elucidated through the engagement with individual partner countries. For example, where there is further UK bilateral or multilateral investment in countries to reward reductions in deforestation and degradation (REDD+), this programme may work to incorporate progress on implementation of FLEGT as part of any high-level REDD+ partnership. The programme could also expand the approach to improving FLEGT to other commodities, goods or services beyond palm oil, soy, beef and leather, where other drivers are more prevalent, or if market links with the EU are less responsive. It will engage with third-party countries or regions that, via their private sector or business and markets, have the potential to reduce deforestation and illegal logging outside or across their own borders. / In conclusion, FGMC is a challenging and ambitious programme. Although the issue is complex, it uses an approach that is in essence simple and has worked. The programme design directly addresses the major risks, and builds on existing experience and momentum. The potential benefits are very large. Retaining the ability to evolve the programme, and to respond rapidly and flexibly in a very dynamic context, will be critical to success.
	D. Comparison of options / Option 1 / Address illegal logging and related timber markets Option 2 / As option 1 plus action to address other illegally sourced commodities / CSC Weight (1-5) Score / (1-5) Weighted Score Score Weighted Score / 1. Partnership between EU and developing countries ensures integrity and credibility of the legality assurance systems 4 4 16 4 16 / 2. Local ownership of a process that is voluntary and respects sovereignty of each country helps sustain the outcome 4 4 16 5 20 / 3. Independent observation or verification of reporting against indicators ensures transparency and accountability 5 5 25 4 20 / 4. Flexible approach that draws on local and external resources provides timely, well targeted technical and financial support to a range of stakeholder; and is responsive to emerging imperatives 4 4 16 5 20 / Totals 73 76 / [scale: 1 = limited importance; 5= very important] / Overall both options are influenced to a similar degree by the four critical success criteria, but the balance between criteria varies slightly between Options. Option 2 is as Option 1 – the programme addresses illegal logging and related trade - while broadening its scope to address commodities other than timber, such as palm oil, soy, leather and beef, which are sourced illegally. Domestic sovereignty is sensitive with respect to decision-making on forests, and even more so with respect to national food security. Compliance and assurance systems are important under both options. EU partnership and independent observation are critical to successfully tacking illegal logging, but less critical where the programme expands its work from timber to other agricultural commodities where the market drivers are less clear. The latter component of the programme is innovative and subject to higher uncertainty, hence a flexible approach will be even more important than if illegal timber alone were tackled.
	E. Measures to be used to assess value for money / The economic cost-benefit analysis provides some time-weighted metrics that indicate the worth of the benefits from the programme relative to the money spent on it.[77] The total incremental environmental, climate change and social benefits are higher for the recommended Option 2 with a benefit-cost ratio of 52:1. / The discounted net present value of the additional forest revenue captured by exchequers in developing country is estimated at up to £13 billion, if illegally-logged timber is harvested legally. / The risk assessment (in the Management Case) indicates how the programme, under this option, better mitigates the risks that threaten successful delivery of the programme. The programme is less dependent on a single commodity market; it responds to both the increasing global demand for food and the growing threat to forests from agricultural commodity production. This means there are better synergies with other finance to help countries deliver REDD+ where drivers of deforestation beyond illegal logging matter. / The programme is likely to contribute more effectively to the overall goal of reduced deforestation protecting up to 39 million hectares of forest by 2035 with increased value of forests accruing to poor forest-dependent people (jobs, timber, non-timber forest products and ecosystem services excluding carbon services) worth at least £182 a hectare. / Carbon emissions reductions as a result of reduced deforestation will be of 845 CO2e a hectare at a cost of under £2 a tonne of carbon. / There are better synergies with other finance to help countries deliver REDD+ where drivers of deforestation beyond illegal logging matter.
[32] The Environment and Global Governance: Can the Global Community Rise to the Challenge? (2011) Uma Lele, Aaron Zazueta, and Benjamin Singer. They argue that “Changes in the Environmental Architecture include… proliferation and fragmentation of aid efforts, increased verticalization of financial instruments and bilateralization of multilateral aid…[ As a consequence there is a need to develop approaches that counter the current trend of] donors being in the driving seat at the cost of weakened and overstretched local capacity; …global programming that is increasingly deficient in their strategic relevance in relation to ground realities; …weak monitoring and evaluation and weak contribution of evaluation to knowledge generation; …a huge funding gap;… incoherence in policies, procedures and approaches of different international programmes; …and increasing finance to international consultancies and less to local capacity building,”
[33] Reduced Emissions from Deforestation and Degradatio: The Truth and Consequences. Kaimowitz, D. (2011)
[34] Op Cit. At Loggerheads?.Agricultural Expansion, Poverty Reduction and the Environment in Tropical Countries. Chomitz, K.M. et al. The World Bank (2007). Ch. 5.
[35] Crime and Persuasion: tackling illegal logging, improving forest governance. Pye-Smith, C. DFID. (2007) (Based on field research in Indonesia, Ghana and Cameroon.)
[36] Op.Cit. The Economics of Ecosystems and Biodiversity (TEEB), UNEP.(2010)
[37] Sustaining Forests: A World Bank Strategy (2002)
[38] Illegal Logging and Trade. Chatham House (2010) p.98
[39] Op.cit Stern Review on the Economics of Climate Change. HMG OCC. (2006); Eliasch Review on Climate Change: Financing Global Forests. HMG OCC.(2008)
[40] Assuming impact on 3% of employees or farm families working on 45m ha soy farms in developing countries requiring 30-60 person-days/ha; on 5m ha oil palm plantations in Indonesia and Africa requiring 40 person-days/ha; on 200m ha tropical pastures near forest frontiers requiring 3-5 person-days/ha.
[41] Mapping and Understanding the UK Palm Oil Supply Chain-EV0459. DEFRA-funded research.
[42] Legality and palm oil in Indonesia: Workshop notes (November 2010). Multistakeholder Forestry Programme. Roby et al.; Bridging the information gap: Combating illegal logging in Indonesia. (2009). David Brown and Fred Stoll. WRI
[43] Global Forest Resources Assessment. FAO (2010)
[44] #### The Cost of Avoiding Deforestation. M. Grieg-Gran. IIED (2008) written for the Eliasch Review.
[45] Indonesia – Swallow et al (2007). Brazil – Eating Up the Amazon – Greenpeace (2006)
[46] Over 3 million metric tonnes of oil palm was certified by the Roundtable on Sustainable Oil Palm (RSPO) in 2010 out of a total world production of 45 million metric tonnes.
[47] Climate Change and the World Bank Group. IEG (2010)
[48] Sawit Watch, October 2010
[49] Economic Analysis for FGMC. Flint. DFID. (2011).
[50] The Green Book. HM Treasury.
[51] Appraisal of Projects in Developing Countries – a guide for economists. Overseas Development Administration, HMSO (1988).
[52] Theory and Practice in the Choice of Social Discount Rates for Cost Benefit Analysis – a Survey. Asian Development Bank ERD Working Paper No. 94 (2007).
[53] Valuation techniques applied to tropical forest environmental services. G. Lescuyer (2007). The estimate is based on data from Cameroon and includes non-timber forest products (NTFPs), watershed benefits, option values and non-use values.
[54] The Social Cost of Carbon and the Shadow Price of Carbon. DEFRA (2007)
[55] DECC recommended a short-term non-traded price of £60 per tonne CO2 in 2020, and £70 in 2030 with a range of +/- 50% for valuing carbon in policy appraisal. Carbon valuation in UK policy appraisal: a revised approach. DECC (2009)
[56] Economic appraisal for FGMC. Michael Flint (2011)
[57] The Social Cost of Carbon and the Shadow Price of Carbon. Defra (2007).
[58] DECC recommended a short-term non-traded price of £60 per tonne CO2 in 2020, and £70 in 2030 with a range of +/- 50% for valuing carbon in policy appraisal. Carbon valuation in UK policy appraisal: a revised approach. DECC (2009)
[59] http://www.decc.gov.uk/en/content/cms/statistics/analysts_group/analysts_group.aspx
[60] Around half of the deforestation in the eight countries accounting for 75% of global deforestation is due to medium to large scale beef/soya/oil palm conversion. Source: The Cost of Avoiding Deforestation. M. Grieg-Gran. IIED (2008) written for the Eliasch Review.
[61] Rising Global Interest in Farmland: can It Yield Sustainable and equitable benefits? Deininger and Byerlee. World Bank. (2011)
[62] Foresight. The future of food and farming. The UK Government Office for Science. (2011)
[63] UK government will only scale up well-performing projects. Indicative cost spreadsheet: FLEGT Action Plan to 2020. EC. (2010)
[64] Political Economy and Governance appraisal for FGMC. Unsworth, DFID (2011); Social and Environmental appraisals for FGMC. Hobley and O’Reilly. DFID. (2011)
[65] Independent Evaluation Group/IEG/WB, September 2010
[66] Roundtable on Sustainable Palm Oil. (2010) www. RSPO.org
[67] Towards better practice in smallholder plam oil production. Vermeulen and Goad. IIED. (2006)
[68] Palm Oil and Vulnerable Groups. Sawit Watch. 20 December 2010.
[69] World Bank –Sustaining Forests: World Bank Forest Strategy. (2002)
[70] Farming using a combination of controlled fire and forest fallow-crop rotation
[71] op.cit.TEEB/UNEP, Ch.3, p.37
[72] From Exclusion to Ownership. Rights and Resources Initiative. (2008) Sunderlin et al.; Global Forest Resource Assessment/FRA. FAO. (2010)
[73] Op.cit. Rights and Resources Initiative. (2008) Sunderlin et al.
[74] EU FLEGT Action Plan (2005)
[75] #### The Cost of Avoiding Deforestation. M. Grieg-Gran. IIED (2008) written for the Eliasch Review.
[76] Op.cit. Swallow et al (2007); op.cit. Greenpeace. (2006)
[77] Following some basic principles from “Project appraisal and planning for developing countries.” I.M.D. Little and J.A. Mirrlees. (1974). See excel spreadsheet for Economic Analysis: FGMC. (2011)

3. Commercial Case (HELD BACK UNTIL NO LONGER COMMERCIALLY SENSITIVE)

A. Procurement / Direct and indirect costs
B, C, D. Procurement process, competition, market response and cost drivers
E. Programme management of contract and supplier performance

D. Indirect Costs
E. Capacity and capability

Financial Case

A. How much will it cost / DFID will contribute up to £250,000,000 to this fully developed 10 year planning framework from Auust 2011 to 2020, subject to need and performance, with £60,000,000 allocated in the first 4 years from August 2011 to September 2015, / The four year budget can be accommodated within the programme aid framework and conforms to priorities within DFID’s current Business Plan. Decisions to scale up finance beyond 4 years are be subject to project performance. / This programme is part of a collaborative global endeavour with the EU effort coordinated under the EU Forest Law Enforcement Governance and Trade (FLEGT) Action Plan. The latter will work with 20 to 30 developing countries and cost over €1 billion over ten years. UK will contribute focused support to up to 10 countries. [Total costs are laid out in the Appraisal Case] / The annual breakdown of total programme budget costs over the first four and total ten year period are described against each direct and indirect cost component in the Commercial Case and in Tables 1F and 2F below. / UK’s focused bilateral support to partner developing countries is provided directly and indirectly and ranges between an estimated £1.6 million and £5.2 million yearly per country. Costs vary depending on whether a country is categorised as “small” or “large”, with “low” or “medium” level of local capacity, and the stage it has reached in the FLEGT process (Consensus Building, Negotiation, Systems Development, Implementation). / Over 90% of budget is allocated to activities in developing countries and against each Logframe Output as follows: / 74% cost to Output 1 to create effective multi-stakeholder institutions and operational VPAs or legality assurance systems in up to 10 FLEGT producer countries. / 2% cost to Output 2 to develop public policies and private standards with compliance in consumer and processing countries. / 20% on Output 3 to increase evidence, knowledge and build momentum for change. / 2% on Output 4 to strengthen coherence between programmes on forests and deforestation at national and international levels / 2% on programme facilitation, monitoring and evaluation. / Table 1F: Annual Budget over 10 years (2011-2020) - Forest Governance Markets Climate Programme (Rounded £ ‘000) / 2011 / £’000 2012 / £’000 2013 / £’000 2014 / £’000 2015 / £’000 2016 / £’000 2017 / £’000 2018 / £’000 2019 / £’000 2020 / £’000 / 9,100 15,900 18,000 17,000 39,000 36,800 36,100 36,000 25,000 17,000 / Table 2F: Summary Budget- Forest Governance Markets Climate Programme (HELD BACK UNTIL NO LONGER COMMERCIALLY SENSITIVE)
B. How will it be funded and aid framework implications / The programme will require at least £60,000,000 expenditure over the first four year period 2011/12 to 2014/15; and a total remainder of up to £190,000,000 from 2015/16 to 2020/21 subject to performance review. / It will require administrative resources of 1 full time equivalent (FTE) A1 Forestry Adviser made up of part of a FTE in Brussels and 0.5 FTE in DFID London together with 0.5 FTE B grade administrative staff in DFID’s Climate and Environment Department to steer the programme. / Overall facilitation and logistical support to the programme is provided within the programme budget. / If the programme were to finance UK seconded or detached experts to the EU or partner countries from the programme budget, these would be contingent liabilities to DFID’s administrative budget.
C. How will funds be paid out / (DETAILED FIGURES HELD BACK UNTIL NO LONGER COMMERCIALLY SENSITIVE) / EU multi-donor Facility / Over the first 4 years the programme will disburse £X million (max. £X million over 10 years) of co-finance to the EU FLEGT Facility multi-donor fund hosted by the European Forestry Institute working with the EU. The EC, France, The Netherlands, Germany and Finland may also consider contributing finance or in-kind to the facility. This Facility is a twinned FLEGT-REDD Facility. / This will be an initial 4 year arrangement with option for extension, and disbursed against six-monthly financial reports on the basis of progress against approved annual work plans. / In-country assistance via EU delegated management, bilateral and joint financing arrangements / Over 4 years the programme will provide £X million (max. £X million over 10 years) of direct and indirect assistance to about 10 countries to help them implement actions agreed under FLEGT Voluntary Partnership Agreements. Payments will be clearly laid out in each individual arrangement, normally against twice yearly tranches, and in accordance with the joint financing arrangement used (described in Commercial Case). / In the main this will be technical assistance via bilateral, EU delegated management or joint financing arrangements or via the service providers, including those sourced through the Framework Agreement or others. In the event that DFID’s fiduciary risk assessment (including an assessment of risks in the forest sector), indicates a country has sufficient fiduciary safeguards in place that allow DFID to provide aid through national or local government systems (and where a performing forest governance reform programme is in place, DFID may provide sector financial aid to the partner country, preferably as reimbursement for specific agreed deliverables. / Technical Forest Governance and Trade Service Provision Framework / Over 4 years the programme will allocate at least £X million (max. £X million over 10 years) to a Forest Governance and Trade technical service provision framework through which a range of specialist service providers (private and not for profit) can be procured to provide training, policy development and technology expertise. This may increase if country partnerships are not implemented though direct financial aid. / In countries where risks of channelling financial aid through government systems are assessed as substantial or high (see DFID’s How To note on Managing Fiduciary Risk (2009)), the programme will provide technical assistance through third-parties, which can also develop build-operate-transfer (B-O-T) systems. In this case the Framework may be used to provide more substantial contracts as part of FLEGT partnerships in the component above and deliver some of the budget outlined in paragraph 229 above. / Forest Governance and the Drivers of Deforestation Call for Proposals / Over 4 years the programme will allocate up to £X million (max. £X million over 10 years) in individual grants to proposals from about 10 not-for-profit organisations each year. Payments will normally be quarterly against quarterly reports, and follow DFID accountable grant procedures. The allocation of finance between private and not-for-profit organisations is a working allocation and will be kept under review. / Programme facilitation, monitoring and evaluation / Over 4 years the programme will allocate £X million (max. £X million over 10 years) to overall programme facilitation, monitoring and evaluation / The annual cost of facilitation with M&E will be £X million a year, including the programme facilitator, logistical support as well as fees, travel, office costs and subsistence. External M&E consists of two-yearly independent assessment and annual review. The Facilitator will be contracted for a period of 3 years, with option for extension.
D. How will expenditure be reported and accounted for / The programme Facilitator will provide the DFID Lead Adviser and Project Officer with a consolidated six-monthly update of progress, activities and financial expenditure across the programme for all the programme components. This will highlight key development impacts as well as financial disbursements and inputs. The six-monthly financial report will include a consolidation of: / The financial report provided by the European Forestry Institute to the EU Steering Committee on its activities and expenditure on the Facility. The European Forestry Institute will provide annual audit statements of its consolidated reports, and six monthly invoices to DFID. / financial reports from the Crown Agent Bank (CAB) on delegated cooperation, joint financing and financial aid country arrangements / financial reports of contracts issued under the service provision framework arrangement / financial reports of grants disbursed to civil society under calls for proposals / own contractual expenditure. / The facilitator will ensure that each individual arrangement sets out clearly eventual ownership, intellectual property and use of any assets, including technology, which is acquired or developed under the arrangement. / The DFID Project Officer (Senior Forestry Adviser) will chair an inter-departmental government Oversight or Steering Committee, made up of DECC , Defra and, when required, arms-length agencies, such as Animal Health, Forestry Commission. The Facilitator will present a consolidated financial and progress report to this Oversight Committee at its bi-annual meeting. Together with inputs from other government departments it will form the basis of UK’s report to the EU. (See Management Case) / The European Commission leads the overall appraisal of the EU FLEGT Action Plan and requests 2-yearly reports from Member States on their contribution to the Action Plan through the Council Working Party on Forests. / The Facilitator will work closely with DFID, formally meeting with the lead adviser monthly.

Management Case

A. Oversight / The organigram below lays out the overarching governance of the programme. Development of the programme demonstrates the importance of working across UK government departments on forest governance. Defra leads on implementation of demand-side measures, including the EU Illegal Timber Regulation, public procurement and other policies that promote sourcing by the UK of sustainable and legal products. DECC leads on climate change policy and climate change strategy and negotiations, and supports the linkages between REDD+ and FLEGT. DFID leads on implementation of development measures in forest producer and processing countries and international forestry with the aim of reducing poverty.. Key EU contacts include DG DEVCO, DG CLIMA, and DG ENV. / The UK cross-government Working Group on International Forestry and Climate (WGIFC) provides broader oversight on policy and programming coherence on international forestry and climate, including REDD+ and the implications of international forestry for domestic forestry. A specific Steering Committee will be drawn from the WGIFC and provide oversight of this programme. The Steering Committee will be chaired by the DFID Senior Forestry Adviser, and include members from Defra, DECC and the Forestry Commission. The Committee will meet at least twice a year to approve and review the programme’s annual work plan, drawn up by the Programme Facilitator in consultation with government departments and other stakeholders. It will also review the programme’s progress against its outcome and outputs, and recommend adjustments to implementation priorities in light of monitoring reports. A small non-government reference body will provide feedback to the Steering Committee, and be made up of three representatives from the UK trade or private sector, the not-for-profit sector and the public citizenry. / There has also been extensive consultation on the proposed intervention during design, with wider stakeholder involvement. The principles of consultation and partnership will be pursued under the programme. The Committee may establish special sessions to consider specific aspects of the programme, to which it may invite other specialist agencies or local partners. / The Committee will establish a voluntary technical expert or advisory group, which will feed into Committee meetings and comment on reports from the Committee. / The Committee will be responsible for formal reporting to the EU FLEGT Action Plan through the European Council Working Party on Forests, the FLEGT Legislative Committee and the EU “FLEGT-REDD linkages” Donor Working Group. / The processes under the EU FLEGT Action Plan are premised on the need for broad stakeholder agreement to the principles and details enshrined in each Voluntary Partnership Agreement or treaty. The value of the commodities and forest products covered by each agreement will have negligible value on the EU market without stakeholder engagement in and support of each stage of the process. Developing country partners drive their own stakeholder processes defining the roles and responsibilities of different actors in negotiation, monitoring and oversight of implementation, sometimes sitting on the formal Joint Implementation Committees established under the treaties. In addition, stakeholders in consumer and processing countries participate in multi-stakeholder delegations to discuss progress under FLEGT. / The two tables below (Tables 1M and 2M) demonstrate how the programme enables parties to take a stake in both the formal FLEGT treaty or partnership process and in additional activities around the treaty. / The programme and the FLEGT process engage with numerous types of stakeholders. On the producer and processor side they include poor forest dependent people in developing countries, and their associations; as well as representatives of smallholder oil palm, soybean and cattle producers. They include governments in consumer, producer and processor countries, involving ministries of forestry, agriculture, industry, justice, finance and law enforcement agencies. They also include a range of organisations along the supply and consumer chain - to name a few these might include logging companies, oil palm plantations, beef and leather companies, gang harvest labourers, chainsaw operators, furniture-maker associations, saw mills, veneer plants, palm oil refineries, financial investors, trade federations, including DIY retailers and supermarkets in Europe; and a range of NGOs working on rights, environmental issues and in development. / Table 1M: Formal stakeholder engagement in FLEGT treaty process / FLEGT VPA Stages Sequence of formal actions over time / 1. Initiation First contact / Provide information / Build consensus in country / Stakeholders organise / High level request for entry to EU / 2. Negotiation Open the formal bilateral negotiation between EC & partner on VPA Annexes and Agreement text / Establish representation & participation at the negotiating table / Negotiations amongst stakeholder groups / Negotiations within stakeholder groups / Routine negotiations / Timetable of preparatory actions negotiated / Review of legality negotiated (laws, roles, responsibilities institutions) / Awareness raising amongst key institutions & stakeholders implicated in implementation / VPA initialled / VPA signed in producer country & EU / Parliamentary discussion & approval in EU and producer country / Legality Assurance System (LAS) agreed, namely… / Clear definition of legal timber agreed / System agreed to track & control timber, forest revenues, etc Principles & methods of information disclosure, observation, independent national audit, social safeguards agreed / Institutions to facilitate, enforce & monitor implementation endorsed & agreed / Reform action plan annexed / 3. Transitional implementation / (Systems development) Government institution to verify compliance with laws endorsed / Tracking systems improved/created / Licensing authority created / Independent auditor selected / Joint implementation meetings planned / Actions in annexed prioritised; time-bound plan generated / Legal reforms implemented; new regulations drafted / Awareness raising underway / Monitoring and oversight bodies established with stakeholder representation / More transparent public reporting / 4. Implementation FLEGT licences issued / Independent Monitor functioning / Timber controlled at EU borders / Periodic independent assessment of mutual effort (EU & partner) / Bi-annual national audit of LAS / Progress check against action or implementation plan / Reformed legal framework enforced / Stakeholder oversight operational and sustained / Transparency measures in place / Table 2M: Opportunities for broader stakeholder engagement / FLEGT VPA Stages Additional FLEGT activities supported / 1. Initiation Assess ex-ante poverty & wealth; create country baseline / Assess potential to address illegal forest land clearance / Support analysis of stakeholders affected, using ex-ante poverty assessment / Deepen & broaden civil society (NGO & private sector), government, parliament representation, debate & analysis / Assess scope of agreement beyond EU to other export markets, and domestic trade / Establish different stakeholder interests / 2. Negotiation Strengthen business, trade, community & government organisations / Strengthen stakeholder representation& capability / Develop stakeholder coalitions / Systematically review (with specialist inputs if required) ambiguous, incoherent, out-of-date laws & bodies / Shed light on forest land allocation procedures & fiscal regimes / Improve revenue/tax regimes; & systems for revenue collection, sharing, re-distribution / Generate evidence base to clarify policy goals & coherence within/ across sectors / Assess legality against policy delivery / Disseminate information so laws, procedures & roles better understood more broadly / Engage private sector in review of legality & systems / Analyse inefficiencies in production, transport & processing to increase competitiveness / Identify alternative livelihoods; how to remove barriers to market for smallholders with trees & artisan operators / 3. Transitional implementation / (Systems development) Build-operate-transfer systems & traceability technology to reduce administrative transaction costs & corruption / Build monitoring systems that track poverty effects, including revenue tracking systems / Overhaul legality; simplify procedures / Make forest tenure & land allocation procedures clearer, including for communities dependent on forest livelihoods / Focus on stakeholder process that manages conflict / Involve domestic & regional producers & consumers to increase their confidence in quality of products produced, sourced & traded / 4. Implementation Independently assess mutual effort amongst EU and partner country every 2 years / Annually audit quality of national LAS / Publish progress against action plan / Promote south-south cooperation & learning amongst FLEGT countries & business enterprises / Monitor overall changes in control over forest resources (administration by state/ communities/private owners) / Establish governance & MRV institutional building blocks for future finance (forest sector reform investment, REDD or adaptation finance) / UK Oversight Committee / FC I Defra | DFID (Chair) | DECC / NGO Rep | Trade Rep / Programme Facilitation / Facilitator | Administrator / Monitoring & Evaluation / EU FLEGT Facility / Funding to partner countries / Service provision framework / Not-for-profit grants / EU FLEGT+ Action Plan / Council FLEGT / Working Party I Legislative / on Forests & I Committee / FLEGT Donor Working Group / EU Assessment / Member States’ Reports
B. Management / The programme will be managed by the Senior Forestry Adviser and part time by the Project Officer in DFID’s Climate and Environment Department, in liaison with the Livelihoods Adviser in the Growth and Agriculture Department. / A DFID forestry adviser recruited as Seconded National Expert (SNE) to the European Commission DEVCO (Sectoral Policy and Coherenace/Sustainable growth: Unit C3 (Climate change, forests, water, environment, biodiversity)) in Brussels provides direct quality assurance of the EU FLEGT Action plan. This post is competitively placed out to EU Member States every 4 years. / Facilitation and logistical support to the programme is provided within the programme budget. (see Commercial Case above)
C. Conditionality / N/A
D. Monitoring and Evaluation / The programme will be reviewed annually and independently against outputs and targets described in the Logical Framework. Reviews will seek feedback from key stakeholders, including the Commission, Member States, partner countries and civil society. Significant budget is allocated to M&E and impact assessment by the programme (both in the facilitation component and within the civil society and service provision components), which will actively contribute to broader M&E by the EU and by individual developing countries. Scale up of the programme beyond its first four years will be subject to a report on performance. The programme and its management arrangements may be modified at that stage in the light of experience. / The European Council Working Party on Forests will periodically call for Member States to report on the progress each has made to the overall FLEGT Action Plan (most recent report December 2010). The Commission will publish results on its website. / EU FLEGT legislation commits the EU and producer countries to “monitor the evolving impact of the FLEGT Action Plan on forest sector stakeholders, forest-based industries, governments and local communities in the EU and producer countries”. The legal treaty agreements (VPA) with each country commit parties to “assess the social, economic and environment impacts of the agreement in country, including on indigenous and rural poor communities, improve understanding of their livelihoods and take steps to mitigate any adverse impact.” / UK, through this programme, will work with the Commission and Member States during 2011/12 to establish an impact monitoring framework under the EU FLEGT Action Plan. The Commission issued TORs[78] in November 2010 to assess the strengths and weaknesses of 9 different impact indicators (listed below), and relevant data-sets and methodologies to track their progress. / DFID will commission independent monitoring, as well as periodic assessment at two levels: country and global. This multiple level of monitoring will capture changes in tow areas: (a) markets and trade, as well as (b) governance reforms in individual countries and their contribution to progress of the global effort. The recently published common “Framework for Assessing and Monitoring Forest Governance[79] provides a range of criteria (accountability, effectiveness, efficiency, equity, participation and transparency) against which improvements in policy and legal institutions, planning and decision-making, and implementation of enforcement and compliance. Annex B of the 2010 Chatham House report lays out an initial checklist of governance questions compatible with this framework. Tables 1M and 2M above lay out the sequencing of country level ex-ante assessments and other M&E activities. The European Commission has commissioned specific work to determine results indicators against the overall EU FLEGT Action Plan will monitor its progress. / Indicators proposed by EU / Deforestation and degradation (National and global Forest Resource Assessments. Satellite measurement of deforestation relatively cheap. Degradation more costly and requires ground truthing) / Forest condition (Biodiversity proxy. Costly ditto above) / Livelihoods of rural poor; Poverty (World Bank PROFOR Poverty-Forests Linkages Assessment Toolkit. National HIES. Site specific assessments. Perception surveys) / Institutional effectiveness, including accountability, transparency, quality of legal framework (Assessments by Chatham House of 12 “ideal policy” list; by FERN of civil society platforms; by Global Witness of CSO ways of working changes) / Costs of doing business (Reduced corruption proxy. WB, WRI, TI governance tools) / Government forest revenue and re-distribution (Tracked and gathered by VPA process) / Institutionalisation and strength of civil society voice (Includes quality of participation and extent to which stakeholders believe they have been able to influence decisions and processes. Perception surveys.) / Volume and direction of illegal and legal trade (Chatham House assessment methodology) / The 2010 independent impact assessment[80] by Chatham House, commissioned by DFID, of the efforts to tackle illegal logging over the past 10 years establishes some of the country and global baselines for the next 10 years of work (included in separate country fact files as well as the final report). The programme will expand the number of countries assessed. the report also lays out a 12 areas to monitor, tracked by compiling answers on impact through a 51-question survey, perceptions surveys as well as a methodologically complex but rigorous comparison of trade and production data, or market monitoring. The report recommends that future periodic impact assessments use and build on its methodology. / The methodology tested a series of standardised indicators and verifiers over a period of 2 years. It developed precise definitions of what was to be measured, and discarded indicators that proved to be unreliable or too difficult or costly to measure. It developed a credible model or typology in terms of markets and country actors. / Twelve key policy areas are evaluated. The 51 questions used to evaluate policy response are available in Appendix B of the Chatham House report. These determine whether national policies exist in producer and consumer countries; the quality of their design and implementation; and scores policy response over regular time periods. An expert perceptions survey complements this with survey confidence levels of +/- 15%. In the future an assessment of informal institutions will also be carried out. / Two methods to estimate illegal logging and related trade volumes are used: wood-balance analysis and import-source analysis. This approach might be tested to assess other commodity trade. / The assessment methodology provides guidance on levels and quality of resource required to carry out the evaluation or assessment: 2 international researchers, 1 specialist researcher, 1 editor/coordinator, 10 local partner country researchers, 17 person expert advisory panel, and 7 independent peer reviewers (including from main countries). / An evaluation check will be carried out in the first year of the programme and programme information will be reviewed regularly to ensure that adequate baseline, counterfactual and monitoring data are or will be available. A major independent impact assessment will be carried out in 2018/19.
E. Risk Assessment / The programme faces four key risks and will take measures to mitigate them. / Risk A / The illegal timber trade is changing in nature, involving less-discriminating consumer markets, domestic markets in producer countries, and an increasing proportion of illegal wood arriving in Europe via processing countries (China, Vietnam and Thailand). As some countries clean up their illegal logging and related trade, there is also greater likelihood of diversion of logging activities with companies and individuals moving their illegal logging and trade activities elsewhere. / Mitigation measure A / Demand-side pressure will continue to drive change. The programme will help exert this by sharing experience on consumer and procurement legislation. It will develop strong alliances, knowledge transfer and lesson learning with major emerging economies. It will coordinate with NGOs that raise awareness of reputational risk; and help countries and businesses strengthen their reputations. The programme will combine its focused support to up to 10 country agreements for improved forest governance with support to regional cross-border approaches, for example the Mekong Basin. / Risk B / There is the raised expectation globally of large amounts of REDD+ finance as a result of the climate change negotiations. There is a risk that large volumes of carbon finance will divert attention away from forest law enforcement, governance and trade, particularly if countries, which do not tackle rampant illegal logging, receive REDD+ finance. / Mitigation measure B / The programme will help organisations and countries make the case that law enforcement and forest governance will be decisive to delivery of credible REDD; and of the need for better coordination between FLEGT and REDD+ strategies at EU and country level. This is explicitly addressed by Output 4. There is good potential for synergy: the long-term success of REDD+ depends on addressing issues of legality, tenure and forest governance in producer countries. / Risk C / The growing demand for agricultural land for domestic and export food and fuel markets is an increasingly powerful driver of both legal and illegal logging and deforestation. / Mitigation measure C / Option 2 specifically addresses this risk. The programme will explore the application of demand- and supply-side measures, and a similar focus on legality, which contributed to reducing illegal logging. These agro-commodity markets share some similarities with timber: increasing awareness of the link to deforestation; increasing public, NGO, private sector and government attention in sensitive consumer countries; and a number of voluntary private sector certification initiatives. / Risk D / A larger and more geographically dispersed programme will be less easy to tightly manage, and be less flexible and responsive than the previous DFID programme (these factors were identified as key elements critical to past success). / Mitigation measure D / (see Management and Commercial Case) / Table 3M below sets out a matrix describing the likelihood of each risk occurring against the importance of its impact. The programme is unlikely to face “killer risks”. / Table 3M: Risk Matrix / Impact / Probability High Medium Low / High KILLER RISK BOX C. Demand for farm land drives legal deforestation / Medium A. Countries targeted less sensitive to market pressure / B. REDD carbon finance diverts attention from forest governance D. Programme management unresponsive to emerging political opportunities / Low
F. Results and Benefits Management / The Logical Framework attached to the Business Case is described below – its impact, outcome, four outputs and relevant indicators. The Logframe provides initial baselines and expected targets which have milestones over the ten-year period of the intervention. Costs are assigned to each output. / The Impacts, to which the programme contributes, will be improved management of forests for poverty reduction, biodiversity conservation and climate protection. / The Outcome of the programme will be governance and market reforms that reduce the illegal use of forest resources and benefit the poor. / The number of countries scoring “good” against their overall policy response will increase against the baseline established by Chatham House, as will the number of countries that are rated, rising from 1 of 5 countries scored as good[81] to 7 out of 10 countries by 2020. / Chatham House study provides a baseline and a detailed list of 50 or so actions against which countries will be scored, including, for example, a monitored action plan to tackle illegal use of forest resources with high level government bodies coordinating the plan; consistent, coherent and unambiguous forest laws and regulations; successful challenges by civil society that lead to government action when laws are not complied with or enforced; sanctions against corrupt behaviour; and transparency in information and financial management. / These actions, when combined with effective mechanisms to detect instances of illegal timber and other commodities, goods or services entering the supply chain, as well as enforcement alerts about illegal shipments, will lead to a reduction in the harvest and sale of products that are illegally sourced, in the case of illegal timber a reduction from 100 million to 40 million cubic metres. / Greater transparency and formalised systems for resolving overlapping property rights and clearly defined, documented and secure rights and tenure arrangements, combined with strong global advocacy and actions on the ground, will reduce the forest controlled by the State and increase the area controlled by private actors, firms, communities and indigenous people from a baseline of 26% of total forest estate to 38%. / Output 1 / A range of activities will encourage and assist producer and processing countries to develop and sustain effective multi-stakeholder institutions. / By 2020 ten countries will have joint implementation, monitoring and oversight bodies with stakeholder representation operational. The EU and routine independent audit will ensure their continued integrity. Many of these activities are laid out in the tables describing formal and informal stakeholder engagement and sequence of actions supported by the programme during the FLEGT process in section A of the Management Case. / These include the establishment of Legality Assurance Systems (LAS) for timber and commodities that access the EU market. Each country (i) agrees a clear definition of legality, (ii) has a system that verifies compliance with legality definition and has controls along its timber and other commodity supply chains, (iii) issues legality licenses for shipments to EU Member States, and (iv) endorses independent monitoring of the well-functioning of the LAS system by a third party. / Output 2 / The programme will engage broadly with private sector, civil society and governments to promote compliance in consumer countries with public rules and policies, as well as private business standards, that discourage trade in illegal timber and other commodities, goods or services sourced from illegal forest practices. / This includes engagement with major financial investors, with the number specifying and reporting on compliance with rules and standards rising from 8 to 15. / The number of consumer countries with public procurement and/or import due diligence systems in place will rise from 8 to 33 countries for timber and from 1 to 5 countries for other commodities. / Output 3 / Increased knowledge and momentum for change will be critical to success. The programme will support activities that generate sound evidence, knowledge and common understanding among the public, NGOs, private sector and government to drive and support progressive change; and ensure momentum is sustained. Public awareness of illegal logging and other drivers of deforestation, with the number of related media coverage items sustained at 1,500 annually will be assessed independently every two years. / The number of visits to the illegal forest commodity information website will increase from 141,583 to 160,000 visits annually and the establishment of at least 5 additional franchised websites. / Output 4 / Coherence between programmes on forests and deforestation at national and international levels is key to overall value for money of the programme and beyond. This cuts across the delivery of all programme efforts. It ensures programme is active generally in ensuring that FLEGT and REDD+ programmes and projects at country level and internationally mutually inform each other and build on shared stakeholder platforms. It is presented as a separate Output with indicators to enable specific monitoring of progress, and to mitigate the risks for REDD if FLEGT fails, and the risks for FLEGT if REDD+ finance creates perverse incentives that undermine FLEGT. / Of the total countries under the FLEGT Action Plan (between 30-40), about 5 will manage pilots under the World Bank administered Forest Investment Programme (FIP); 5 will be pilots for the Bank administered Forest Carbon Partnership Facility (FCPF); 6 are pilots for UN-REDD; with 4 countries managing at least two multilateral REDD pilots. Other bilateral REDD initiatives are being financed in a range of countries by Norway, potentially UK, USA Germany, Japan, The Netherlands, Australia and Finland. The programme will work with the global CIFOR REDD monitoring initiative, the World Resources Institute (WRI) and the Rights and Resources Initiative (RRI) to ensure that lessons and evidence on forest governance and trade inform other projects and help deliver credible REDD, with coordination increasing from amongst 2 to 10 initiatives internationally and in all 5-10 countries directly supported by the programme actions and approaches on the ground coordinated. / Option 2 follows the same intervention logic for the other agricultural commodities that drive illegal forest clearance. The premise is that there are similarities between illegal timber and agricultural commodities grown on illegally cleared land, and similarities in the approach required to address both.
[78] TORs for Indicator Options Analysis: EU FLEGT Facility, European Forestry Institute (EFI)
[79] Framework for Assessing and Monitoring Forest Governance. The Program on Forests (PROFOR) and FAO. (2011)
[80] Illegal logging and related trade: Indicators of the global response; Lawson and MacFaul, Chatham House, July 2010) http://www.illegal-logging.info/
[81] Scored above 75% in at least each of four out of 12 policy areas