Business Case

for

Building Resilience and Adaptation to Climate Extremes and Disasters Programme (BRACED)

Impact of natural disasters since 1992[1].
[1] UNISDR (June 2012) http://www.unisdr.org

For funding under the UK’s International Climate Fund (ICF)

Climate and Environment Department 2013

Intervention Summary	4
What support will the UK provide?	4
Why is UK support required?	5
What are the expected results?	8
II. The Strategic Case	10
A. Context, problem and need for intervention	10
What has been the impact of climate extremes?	10
What are the impacts on nutrition?	12
How do climate related disasters affect women?	13
	13
What countries and regions are at most risk?	14
The Sahel as an example of a region at risk	15
Where should BRACED work?	17
B. The Response	17
How do we build resilience to climate extremes?	17
How does combining Disaster Risk Reduction and adaptation help build resilience?	18
What policy and institutional links are needed to sustain and build resilience?	18
Why is government intervention needed to help build resilience to climate extremes?	19
What are the consequences of not intervening?	20
C. Policies, Strategies and Programmes	21
How does this programme link to International Climate Fund (ICF) priorities?	21
How does this programme link to DFID’s overall response to the HERR and action on DRR?	21
How does BRACED contribute to HMG strategy on the Sahel?	21
What are the links to Future Fit?	22
What are the links to DFID global, regional and country humanitarian and DRR initiatives? / What are the links to DFID’s research programmes?	22 / 23
What are other development agencies doing?	23
What are others doing in the Sahel?	24
D. Impact and Outcome	26
What results will BRACED achieve?	26
What will BRACED do?	28
	30
Component B: Scaling up DRR and Adaptation in DFID focal countries	30
Component C: Building evidence on adaptation and DRR	33
Component D: Development of national and international capability and capacity extremes	35
What types of activities will be supported?	35
III. Appraisal Case	39
A. Approach and Evidence	39
B: The case for investing in DRR and adaptation	42
C. Appraisal of Delivery options	50
D. Appraisal of Management options / E. Summary of appraisal recommendations	65 / 72
IV. Commercial Case	76
A. Procurement/commercial requirements for BRACED	76
B. How we expect the market place will respond to this opportunity?	78
C. How does BRACED use competition to drive commercial advantage for DFID?	78
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this?	79
E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention?	79
V. Financial Case	81
A. Who are the recipients of all proposed payments?	81
B. What are the costs to be incurred directly by DFID?	81
C. What are the costs to be incurred by third party organisations?	81
D. Does the project involve financial aid to governments?	81
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin?	81
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting?	81
	82
H. How will expenditure be monitored, reported and accounted for?	83
I. Are there any accounting considerations arising from the project?	84
VI Management Case	85
A. What are the Management Arrangements for implementing the intervention?	85
B. What are the risks and how these will be managed?	88
C. What conditions apply (for financial aid only)? / D. How will progress and results be monitored, measured and evaluated?	89 / 89

List of Acronyms	93
Glossary of terms / List of boxes, figures, tables	94 / 96
References and Notes	100
Annexes
Summary of studies on the efficiency and net benefits of disaster management / BRACED Climate and environment assurance note / Rapid review on the potential of NGOs to build resilience to climate extremes and disasters / Scoring of management options for BRACED / BRACED theory of change / BRACED Logframe

BRACED INTERVENTION SUMMARY

What support will the UK provide?
BRACED is a two phase programme. In its first four year phase from August 2013 the UK will provide up to £140 million from the International Climate Fund (ICF). Of this £110 million will be to deliver interventions in up to 10 countries, including in the Sahel, that are at risk of climate extremes (e.g. droughts, storms, floods and landslides), and to build the evidence on how to do this at scale to influence policy and institutional changes. This is expected to benefit up to 5 million people, especially women and children, by building their resilience to climate and weather extremes (See definitions in Box 1). / This will be achieved through: grants to NGOs and their partners (local government, UN agencies and private sector) to scale up proven technologies and practices in the Sahel and DFID focal countries at most risk; research and evaluation to build the evidence on what works globally on adaptation and Disaster Risk Reduction (DRR); and, development of national and international capacity on response to climate related disasters. Up to £30 million will be allocated for the last element for which a separate business case will be developed. / Box 1: Definition of climate and weather extreme events / The term ‘Climate extreme’ is in this Business Case to collectively refer to extreme weather and extreme climate events following the terminology used by the Intergovernmental Panel on Climate Change (IPCC). The distinction between extreme weather events and extreme climate events is not precise and is related to their time scales. The terms are often used interchangeably. / An extreme weather event is typically associated with changing weather patterns, that is, within time frames of less than a day to a few weeks. / An extreme climate event happens on longer time scales. It can be the accumulation of several (extreme or non-extreme) weather events (e.g., the accumulation of moderately below average rainy days over a season leading to substantially below average cumulated rainfall and drought conditions). / What is called an extreme weather or climate event will vary from place to place in an absolute sense (e.g., a hot day in the tropics will be a different temperature than a hot day in the mid-latitudes), and in time period. / Some climate extremes (e.g., droughts, floods) may be the result of an accumulation of moderate weather or climate events (this accumulation being itself extreme). Compound events, that is, two or more events occurring simultaneously, can lead to high impacts, even if the two single events are not extreme per se (only their combination). Not all extreme weather and climate events have extreme impacts. / In this business case we refer to climate extremes based on the above definitions which are taken from the 2012 IPCC “Special Report on Managing the Risks of Extreme Events (SREX) and Disasters to Advance Climate Change Adaptation / The second phase of up to four years will build on the results and evaluation of the first phase (along with other evidence) and is expected to have a budget of between £200 to £300 million. A business case for the second phase will be developed in 2015/16.
Why is UK support required?
What problem are we addressing? / Poor people are the most vulnerable to climate-related disasters. Climate change is leading to higher temperatures, changing rainfall patterns and rising sea levels which in turn result in climate extremes[2] such as droughts, storms, floods and landslides. The impact of these climate extremes depends not only on the extremes themselves but also on the exposure and vulnerability of populations; high exposure and vulnerability can lead to disasters[3]. There is evidence that climate change has already affected the magnitude and frequency of climate extremes and these changes are likely to increase further in the future[4]. / With increasing populations more people – often the poorest – live in locations vulnerable to climate extremes, resulting in more people being exposed to risk and to an increasing number of climate-related disasters. Of the 3.3 million deaths from natural hazards[5] since 1970, 95% have been in developing countries[6]. Since 2000 there have been over 400,000 deaths as a direct result of climate extremes with 79 % dying in developing countries. Over the same period over 2.7 billion people were affected[7], with 98% in developing countries[8]. Economic losses due to natural disasters since 1992 (year of the Rio Earth Summit) amount to 25 times the annual level of Official Development Assistance (ODA)[9]. / Responding to these challenges are a DFID Ministerial priority. BRACED will support this response - focusing on the needs of the Sahel (a National Security Council) priority; meeting spending commitments on fragile states and climate change; and helping achieve the Millennium Development Goals on poverty and hunger. It will also address the Humanitarian and Emergency Response Review recommendation that DFID should respond to rising global risks (including climate change) by building and strengthening systems to respond to crises. It will also support DFID’s Strategic Vision for Girls and Women’s by providing economic assets directly to girls and women. / Box 2: What is Climate Resilience? / Resilience is[10] is the ability of a system to bounce back from stresses and shocks. Climate resilience can be defined as “the long-term capacity of a system or process to deal with extreme weather events and changes in climate and continue to develop”. / The concept of resilience, including climate resilience, adds an additional dimension to development thinking. It builds on other approaches such as disaster risk reduction and, livelihoods. It emphasises uncertainty and estimating the level of future risks in complex processes[11] beset by uncertainty. Hence, by definition, building climate resilience is not an exact science[12]. / Climate resilience can be viewed as a set of principles; and a developmental outcome. There is no template for building resilience. So it is essential to define who or what needs to be made resilient and against what kind of future change or shock[13]. The indicators of climate resilience are, therefore, specific to the situation, rather than generic. / The focus of BRACED is building resilience to disasters. At the community level this is about finding ways to stop shocks affecting households. This can be achieved in a number of different ways, such as insurance (allowing households to share risks), social protection (helping families to maintain their purchasing power in hard times), or provision of public goods and services (such as flood defences and early warning systems). / There are limits to how much resilience can be built within a single community. Support will need to go beyond the community level if it is to be transformational. At the policy and macro-economic level we need to strengthen national capacity, to promote economic development that builds resilience to climate and weather extremes. Interventions need to look beyond the needs of individual communities and look at regional and economy wide patterns. For example, interventions to build resilience of a drought prone community may increase the vulnerability of any communities who live downstream, so integrated planning is required. BRACED will build the evidence on what works well (and less well) to inform resilience planning at all levels. / Without action to address these risks more people will be killed and affected by disasters. The Humanitarian and Emergency Response Review (HERR) predicted 375 million people a year will be affected by climate-related disasters by 2015. Investment is needed to reduce the risks of a climate extreme becoming a disaster and to protect the poorest and least able to cope from the worst impacts. A key recommendation of the HERR was that DFID should ensure that building resilience is a core part of its programmes by integrating the threat from climate change, along with other hazards, into a Disaster Risk Reduction approach. BRACED is one of the first DFID programmes to take this approach at scale. / A study[14] on the economics of resilience in Ethiopia and Kenya and earlier humanitarian intervention shows the benefits of this approach. By combining DRR and development together in Kenya the study found that early response to drought could save between $107m and $167m for a population of 367,000 in a single event. In southern Ethiopia, with a population of 2.8 million, household level data showed that early response could save between $662m and $1.3billion in a single event. / The Foresight Report ‘Reducing Risks of Future Disasters’, also identifies global environmental change resulting from climate change as one of the two key drivers to increasing risks of disaster. The increase of extreme weather events combined the increase of urban populations exposed to these events will substantially increase the future risk of disasters. BRACED will respond to a number of the report’s recommendations. This includes: building a strong evidence base on the effectiveness of interventions to help decision makers determine how best to invest in disaster risk reduction; how to incentivise private sector investment in resilience; and, to integrate DRR within development programmes. / What countries and regions are most at risk? / DFID has identified countries that are at risk from disasters and that have limited capacity to respond as priorities for resilience support[15]. BRACED will provide grants to NGOs to support interventions in these countries. / One region that has suffered from repeated climate related disasters is the Sahel. The root causes of vulnerability in the Sahel are the lack of resilience to shocks and stresses caused by drought, floods and conflict. Building resilience is vital to break the cycle of recurrent humanitarian crises in the region. The 2012 food and nutrition crisis, and its after effects, are still being felt by millions of people across the Sahel. At the peak of its intensity, the crisis disproportionately hit the poorest in society. Many reverted to adverse coping mechanisms; including distress sales of livestock and buying food on credit. / A further example of the severity of the impacts of a climate event are the 2010 flood in Pakistan where up to 3000 people were killed, over a million homes destroyed and more than 21 million people were seriously affected. In the immediate aftermath of the floods US$2 billion was needed for emergency relief. Recovery after the floods cost a further US$2 billion. After the floods a longer term damage needs assessment was undertaken by the World Bank and the Asian Development Bank[16]. This estimated US$8.7 to 10.9 billion was needed to reconstruct and rehabilitate the infrastructure, institutions and services that had been destroyed or damaged by the floods. At the household level the impacts were also significant. An assessment of 1800 households six months after the floods found that 85% of the households had reported income losses of up to 50%.[17] / What is the rationale for UK Government intervention in this problem? / Some people will adapt to an increase in climate extremes by changing their behaviour, diversifying their livelihoods, and moving to less risky locations. Not everyone, especially the poorest, can do this. Consequently, there is a strong case for Government intervention to help these people adapt to extreme climate events as: / Many goods and services that are needed to reduce the costs of climate extremes, or that help people to cope with the effects of these extremes are not provided by the market. Examples are flood protection, sea defences, and climate change information/forecasts. / Governments have an important role in protecting poor and vulnerable people in society. Many people in developing countries are too poor to bear the costs of adaptation. / Governments have an important role in promoting more inclusive growth and economic empowerment, these actions are also essential to build the resilience of people to climate related disasters. / Governments fail to provide disaster risk reduction and adaptation goods and services as: (i) they lack institutional capacity; (ii) they are uncertain about when disasters will occur; (iii) they have limited knowledge of the costs of disasters and the benefits of early action. / By demonstrating what works well (and less well) and by testing new approaches to adaptation, public investments can have a large influence on the levels of resilience built. / Governments can also influence the broad patterns of macroeconomic development that can build resilience to climate extremes and disasters. We know for example, that macroeconomic stability can help countries recover from extreme events[18]. We have less evidence on what types of policy work well at building resilience across communities within a country. There are strong positive externalities associated with the knowledge of what works well and less well in economy-wide resilience building. / What are we doing to tackle this problem? / Two sets of action are needed: first actions to prevent a climate extreme becoming a disaster; and, second actions that when disasters occur to minimise their impacts and enable communities and countries to recover more quickly. Disaster risk reduction (DRR) is an approach that evolved from humanitarian relief to a planned response to reduce the risk of disasters. The HERR identified that the Disaster Risk Reduction approach does not sufficiently address the additional risks from climate change; so there is a need to integrate climate change risks into DRR. BRACED will address the HERR recommendation ‘to integrate the threat from climate change into disaster risk reduction by expanding this approach to explicitly accept the high levels of uncertainty around climate events and respond accordingly’. BRACED will work across the DRR, social protection and climate adaptation fields, both ‘top down’ through institutions and policies (national and international) and ‘bottom-up’ by directly supporting communities, whilst building evidence of what works and why.
What are the expected results?
What will change as a result of our support? / Impact. BRACED is expected to directly benefit up to 5 million vulnerable people, especially women and children, in developing countries by helping them become more resilient to climate extremes[19]. In addition, through improved policies and institutions at the national level and better integration of DRR, climate adaptation and development programmes, we expect the programme to reach many millions more. Estimates of these will be determined during implementation. This number will be determined in design of the fourth component to support wider institution building and will be set out in a separate business case. / The outcomes of the programme are expected to be: / Poor people in developing countries are reached by interventions that make them more resilient to climate extremes. / Knowledge and evidence for building resilience to climate extremes is built and is used at all levels (local, national, regional, international and within DFID). / BRACED has four expected outputs: / Large scale interventions make poor people less vulnerable to climate extremes. / Increased capacity to respond to climate extremes. / Better understanding of what works in building climate resilience. / Improved policies integrating DRR and climate change adaptation in place. / What will BRACED do? / To deliver these outcomes three immediate components are proposed. A fourth component on building institutional capacity will be developed subsequently. The four components are: / Scaling up actions on the ground to build the resilience of people to cope with climate extremes in the Sahel. (Up to £60 million). / Scaling up actions on the ground to build the resilience of people to cope with climate extremes in DFID focal countries at high risk of these events (Up to £40 million). / Building evidence on adaptation and DRR across the first two components, and identifying what policy and institutional changes are needed to build resilience to climate extremes (Up to £10 million). / Development of national and international capability and capacity on response to climate extremes (Up to £30 million). This will be covered in a separate business case. / Together these four components will directly benefit people at risk from climate extremes, and provide evidence on the importance of, and how to, integrate climate change, disaster risk reduction and development programmes. / Under Components (A) and (B) grants will be made to alliances comprised of NGOs, local government, private sector and research organisations. These will used to build the resilience of households and communities for example through: small scale flood protection schemes, water harvesting, local early warning systems, community adaptation planning, community level awareness raising and evacuation planning, crop diversification, and micro-insurance. / Component (C) will build on these two components to develop evidence and test approaches on adaptation and DRR to build the resilience of people to cope with climate extremes. It will identify future priorities for longer term support under second phase of BRACED in the Sahel and in DFID focal countries. In doing this it will work closely with DFID country offices and regional teams. / Component (D) will underpin the programme by providing support to build the capability and capacity of national and regional organisations to prepare and plan for the expected increases in the frequency and severity of climate extremes. This Component will enable policy makers to learn lessons on how to scale up actions and design sustainable policies and institutions to build both community resilience and the broader patterns of economic development needed to build resilience. / How does this programme link to DFID’s overall response to DRR and climate change? / The International Climate Fund Implementation Plan[20] identified Disaster Risk Reduction as a priority for investment[21]. Investment in climate resilience also has co-benefits[22] for ICF objectives on low-carbon development and greenhouse gas mitigation by avoiding the environmental degradation and unsustainable resource use often associated with disasters. It will also include activities that will have co-benefits for biodiversity conservation and the protection of carbon sinks such as mangrove restoration to protect coastal zones and drought tolerant crops. / BRACED will help deliver DFID’s commitments under the HERR and the Sahel Resilience Approach process led by Africa Regional Department. BRACED will address the priorities by ensuring resources are available to civil society organisations in the Sahel to build resilience. / BRACED is linked to the programme Building resilience in the Sahel through adaptive social protection. This programme is expected to provide up to £50 million over four years to support national systems for implementing adaptive social protection in the Sahel. It will provide direct support to the poorest and most vulnerable, helping them reduce their vulnerability and build their long term resilience to climate extremes, which is vital to breaking the cycle of recurrent humanitarian crises, conflict and poverty in the region. / The DFID Secretary of State co-chairs a ‘Political Champions for Disaster Resilience’ group with Helen Clark (UNDP). This group of developing country and international development ministers, and development agency heads has been convened to provide a greater focus and investment in disaster resilience. BRACED will help deliver on the UK’s commitments, as part of this group, to scale up investment in disaster resilience, and particularly in the Sahel and Horn of Africa. The programme also offers an opportunity for increasing donor and multilateral coherence by working with this group. / Future Fit is a DFID Executive Management Committee (EMC) initiative to produce a vision and strategy for DFID’s response to the challenges and opportunities that climate change and resource scarcity pose for poverty reduction and development. Future Fit asks the question what strategic shifts in our investment portfolio in front line sectors – Food, Water, Energy, and Cities are needed to protect development gains and respond to the challenge of climate change and resource scarcity. BRACED is part of the response to these challenges, demonstrating the links between climate and development finance and delivering poverty reduction, growth and environmental goals.
[2] ‘Climate extreme’ is used here to collectively refer to extreme weather and extreme climate events (following the terminology of the IPCC SREX report) – See Box 1. Climate extremes include: droughts, floods, cyclones, storms, landslides, heat and cold waves and wildfires, but not natural hazards such as earthquakes tsunamis and volcanoes.
[3] IPCC SREX Extreme Events Report (2011) Summary for Policymakers
[4] The 2012 IPCC “Special Report on Managing the Risks of Extreme Events (SREX) and Disasters to Advance Climate Change Adaptation” provides clear evidence that climate change has already affected the magnitude and frequency of some extreme weather and climate events and that these are likely to further increase in the future
[5] Earthquakes, floods, droughts and storms
[6] Natural Hazards, UnNatural Disasters, The Economics of Effective Prevention, (summary booklet) 2010, World Bank
[7] Source: EMDAT EM-DAT: The OFDA/CRED International Disaster Database
[8] Defined as non-OECD countries. Source: EMDAT EM-DAT: The OFDA/CRED International Disaster Database
[9] Including geophysical such as earthquakes and volcanoes as well as climate related disasters. UNISDR (June 2012) http://www.unisdr.org
[10] ### Jamais Cascio; Foreign Policy Magazine; The Next Big Thing; Resilience; April 15, 2009
[11] Mechler, R. and The Risk to Resilience Study Team, (2008): The Cost-Benefit Analysis Methodology, From Risk to Resilience Working Paper No. 1, eds. Moench, M., Caspari, E. & A. Pokhrel, ISET, ISET-Nepal and ProVention, Kathmandu, Nepal
[12] Protecting Gains, Minimising Losses: Putting Resilience at the Heart of DFID’s Development Work. Policy Division Draft Discussion Paper. (2012)
[13] Protecting Gains, Minimising Losses: Putting Resilience at the Heart of DFID’s Development Work. Policy Division Draft Discussion Paper. (2012)
[14] DFID. 2012. The Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia.
[15] Internal DFID report on countries at risk
[16] World Bank and Asian Development Bank. 2010. Pakistan Floods 2010 Preliminary Damage and Needs Assessment.
[17] Kirsch et al.2012. Impact of the 2010 Pakistan Floods on rural and urban populations at six months. PLos Currents published online.
[18] DFID (2010) Promoting Economic Growth When the Economy is Changing VIVID Economics. DFID
[19] The 5 million figure is based on an estimate of the number of beneficiaries from sub-programme 1 on scaling up DRR activities at grassroots level (though civil society organisations), as only this component will be designed to directly make large numbers of people climate resilient in the lifetime of the programme. This is based on an estimate of 0.25 million people to each grant of £5million. This is a rough estimated cost of £10 per person, which may need to be revised as BRACED is implemented.
[20] ### International Climate Fund Implementation Plan 2011/12-2014/15
[21] The Implementation Plan states: ‘The ICF will prioritise investment for adaptation in the following sectors through multilateral and bilateral channels - Disaster risk reduction (DRR) investments such as integrated DRR and adaptation planning, critical infrastructure, developing early warning systems, macro and micro insurance and addressing impacts on girls and women.
[22] Co-benefits are the benefits of policies implemented for various reasons at the same time, for example policies designed to address greenhouse gas emissions have other, often at least equally important rationales related to objectives of development, sustainability and equity (IPCC AR4 definition). Clearly the reverse can also apply; policies designed to achieve development or disaster resilience objectives can have other rationales related to addressing greenhouse gas emissions as well

# II. THE STRATEGIC CASE

Introduction / Under the International Climate Fund (ICF), DFID will design a two phase programme “Building Resilience and Adapting to Climatic Extremes programme” (BRACED). This strategic case sets out the justification for the first four year £140 million phase, answering the following of questions: / The Problem: / What has been the impact of climate extremes? / What are the impacts on nutrition? / How do climate related disasters affect women? / What are the implications of a changing climate for future disasters? / What are the regions and countries most at risk? / What are the main policy and institutional challenges? / Where should BRACED work? / The Response: / How do we build resilience to climate extremes? / How does combining Disaster Risk Reduction and adaptation help build resilience? / What policy and institutional links are needed to sustain and build resilience? / What are the best practices and approaches to build resilience? / Why is UK Government intervention needed? / What are the consequences of not intervening? / The Policy and Programme links: / How does the programme link to ICF priorities? / How does this programme link to DFID’s overall response to the HERR and action on DRR? / How does BRACED contribute to HMG strategy on the Sahel? / What are the links to Future Fit? / What are the links to DFID global, regional and country humanitarian and DRR initiatives? / What are others doing? / A. Context and the Problem / What has been the impact of climate extremes? / The consequences of climate change can be summarised as higher temperatures, changing rainfall patterns and rising sea levels which in turn result in climate extremes such as droughts, floods, cyclones and landslides. The 2012 IPCC “Special Report on Managing the Risks of Extreme Events (SREX) and Disasters to Advance Climate Change Adaptation” provided clear evidence that climate change has already affected the magnitude and frequency of some climate extremes including sudden onset such as floods and landslides and gradual onset such as droughts and saline intrusion from sea level rise[23]. Figure 1 shows the increase in extreme events[24] over the last thirty years. / As populations increase more people live and practise their livelihoods in locations vulnerable to extreme climate events. Where such events converge with vulnerability of human systems, disasters can occur. There have been 3.3 million deaths from natural hazards in the 40 years to 2010 (82,500 per annum) with 95% in developing countries. Droughts are the deadliest with almost 1 million people dying in Africa’s droughts alone[25]. Since 2000 there have been over 400,000 deaths from climate extremes (droughts, floods, extreme temperature, landslides, storms and wildfires) with 79% of those occurring in developing countries[26] (see Table 1). / Figure 1 Global extreme events 1980 to 2011[27] / There is strong evidence of increasing risks to national economies and to the livelihoods of poor people from current climate and weather conditions – both from sudden events and from gradual change. Fatality rates and economic losses as a percentage of GDP are the highest in developing countries[28]; whilst total economic disaster losses are higher in developed countries. / The IPCC SREX report provides evidence that economic losses from climate-related disasters is increasing[29], with a large year on year variation. Estimates of economic impact in developing countries often only take account of tangible impacts and ignore the large impact on livelihoods at the household level; an impact which is difficult to measure and aggregate. In fact it is the poorest that are most vulnerable to disasters. Many of the poorest will not recover from the forced selling or loss of their assets. They may become destitute and their children malnourished, often dropping out of school. Disasters destroy livelihoods and aspirations, as well as lives. Box 3 provides examples of these more indirect impacts. / Table 1: No of people seriously affected by climate related disasters since 2000[30] / Type of climate extreme No. of people affected (millions) / All countries non-OECD countries Percentage non-OECD of total / Drought 906.26 903.7 99.7% / Extreme temperature 89.85 89.61 99.7% / Flood 1275.92 1257.93 98.6% / Mass movement (landslides) after rains 3.94 3.94 99.9% / Storm 444.5 427.9 96.3% / Wildfire 2.19 1.17 53.5% / Total 2,722.66 2,684.25 98.6% / The Human Development Report from 2007/8 and the 2012 Foresight report on Reducing Risks of Future Disasters both emphasise the long term and indirect impacts of disasters. This is because the strategies used to manage increased risks can often reinforce deprivation. The poor may be forced to sell productive assets to protect consumption, with implications for longer term recovery. When asset sales, are not enough households resort to cutting meals, taking children out of school and reducing spending on health. If households do not have access to safe assets then an increase in risk may lead to lower levels of saving, in this way adverse shocks can have long-lasting negative effects[31]. In addition the 2011 Foresight Report on Migration and Global Environmental Change[32] found that when the impacts of disasters are irreversible and land becomes unviable, migration becomes the most viable coping strategy. In these circumstances the poorest communities are at risk of becoming ‘trapped populations’ unable to obtain a livelihood where they are but too poor to afford to move. / Many developing countries are geographically more vulnerable to the impacts of climate extremes than high income countries. They are also the least able to cope with the impacts on their economies, governance, infrastructure and services. / Box 3: Examples of indirect impacts of climate related disasters / Loss of economic activity. Overall GDP can fall by 0.6% after a drought of median intensity.[33] In a study of 85 disasters in 45 countries growth fell in the disaster year and did not increase to compensate in subsequent years.[34] / Nutritional impacts. Ethiopia; children aged 5 or less are 50% more likely to be malnourished if they were born during a drought. This translated to 2 million additional malnourished children in 2005. Niger; children aged two or less born in a drought year were 72% more likely to be stunted.[35] / Educational outcomes. Zimbabwe; children aged 12 to 24 months during the 1982-1984 drought who were stunted, had lower grades 13 to 16 years later and a 7% loss in extrapolated lifetime earnings[36]. / Conflict. Drought has been associated with conflict in Niger. Conclusive evidence on causal links is difficult to obtain though Miguel et al (2004) estimate that in Africa a 1% increase in annual rainfall can reduce the probability of serious conflict by 6%[37]. / Trade. One study found that developing countries experienced a decline of more than 20% in exports following a domestic disaster, with negative effects lasting for at least three years[38]. In 2008 a rapid increase in world rice prices fuelled by disasters and pest outbreaks in rice producing countries contributed to a world food crisis[39]. / What are the impacts on nutrition? / Evidence from regions affected by climate extremes demonstrates the impacts on nutrition and long term resilience. Gambian studies reveal that women who are pregnant during a hunger gap give birth to smaller babies[40]. Longitudinal studies in Malawi have shown a seasonal variation, linked to the annual hunger season, in height gain among young children[41]. In Ethiopia and Niger, children born during a drought are more likely to be chronically malnourished later in childhood than those who are not[42]. The prevalence of chronic undernutrition has been found to increase among Bangladeshi children following flooding[43]. In fact, it has been estimated that more than 20% of adult height variation in developing countries (the physical sign of having experienced chronic undernutrition in childhood) is determined by environmental factors, in particular drought[44]. / Ensuring that development and adaptation investments support improvements in the nutritional status of communities will help to build their resilience[45]. However, these investments might not go far enough to protect nutrition outcomes when shocks arise. It is already recognised that nutrition-sensitive interventions crucial for ensuring optimal nutrition outcomes are not currently sufficiently disaster proofed to maintain effectiveness in the face of crisis[46]. / A study of disaster resilience in the Sahel noted that “there is no better single indicator of resilience…than the level of child malnutrition”. The report went on to propose that “‘nutrition security’ be placed at the apex of the pathways to resilience”[47]. / How do climate extremes affect women? / Women are more vulnerable to the effects of natural disasters than men. For example a study of 141 natural disasters over 1981–2002 found that when economic and social rights are equal for both sexes, disaster-related death rates do not differ significantly for men and women. But when women’s rights and socio- economic status are not equal more women than men die in disasters[48]. In Bangladesh, for example, of the 140,000 people who died from the flood-related effects of Cyclone Gorky in 1991, women outnumbered men by 14:1. Factors limiting women’s mobility and use of cyclone shelters were social norms and roles for women including primary responsibility for the care of children, the sick and elderly; social norms preventing women from leaving their homes or staying in cyclone shelters without a male relative; traditional dress codes such as the wearing of sarees that can easily become entangled; and concerns around privacy and safety in shelters. Women also represented an estimated 61% of fatalities in Myanmar after Cyclone Nargis in 2008, and 70% of those dying during the 2004 Indian Ocean tsunami in Banda Aceh, Indonesia[49]. / Empowerment of women is an important ingredient in building climate resilience. There are now a wide range of studies on how empowering women in communities contributes to climate resilience[50]. There is also strong and mounting evidence at the country level that improving gender equality contributes to policy choices that lead to better environmental governance, whether through increased representation and voice of women within their communities, in society at large, and at the political level, or through increased labour force participation. In Nepal and India women’s participation in forest committees beyond a critical minimum threshold (around a third) has been seen to have a positive impact on forest regeneration and a reduction in illegal extraction of forest products[51]. / There is evidence that where women are empowered this can serve as a powerful springboard for building climate resilience. Good examples of how this can be done are seen in programmes that seek to build climate resilience through gender sensitive approaches to supporting rural livelihoods. In pastoral communities in Kenya and Ethiopia building resilience to drought, with a particular emphasis on empowering women to be agents of change, helped communities better manage the risks associated with the 2005–08 drought cycle by generating income, preserving assets and enhancing food security. [52] / What are the implications of climate change for future disasters? / The impacts of climate related disasters are already being experienced (for example Pakistan floods, droughts in the Sahel and Horn of Africa, and floods in Mozambique) and action is needed now to build the resilience of people. The risks of climate related disasters are likely to increase with climate change. The IPCC SREX report and the Foresight report on reducing the risks of future disasters both recognise the relative infrequency of particular types of extremes limits the data available to make assessments regarding changes in their frequency or intensity. The more infrequent the extreme event, the more difficult it is to accurately identify long-term changes. Evidence on these extremes varies depending on the event and region and the SREX report gives confidence or probability ratings for each[53]. The report does conclude that over the 21st century the world will get hotter on average, and while there is uncertainty over by how much, and what this will mean for different places, we can expect[54]: / Temperatures will rise. Models project substantial warming in temperature extremes by the end of the 21st century. / Extremes in rainfall will increase. It is likely that the frequency of heavy precipitation or the proportion of total rainfall from heavy falls will increase over the 21st century in many areas. In some regions increases in heavy precipitation are likely to occur despite projected decreases in total precipitation in those regions. / Sea level will rise. It is very likely that mean sea level rise will lead to upward trends in extreme coastal high water levels. / Leading to an: / Increase in droughts. Medium confidence that droughts will intensify in the 21st century in some seasons and areas due to reduced precipitation and/or increased evapo-transpiration; / Increase in floods. Medium confidence that projected increases in heavy rainfall will contribute to increases in local flooding in some catchments or regions / Increased risk of storms. Tropical cyclone and hurricane wind speeds are likely to increase, but low confidence in projections of changes in extreme winds. The very likely increased extreme coastal high water levels coupled with likely increase in tropical cyclone wind speed, is a particular issue for tropical small island states. / Increased risk of heat waves. There are likely to be more incidences of periods of high temperature and heat waves[55]. These will have direct impact on people’s health and deaths, and damage to crops. Indirectly this could lead to the increased risk of wildfires and associated disasters and loss of lives and assets. / Future climatic change in the Sahel is uncertain, with some models projecting a prolonged dry period and others an increase in precipitation. Temperatures are likely to rise with damaging impacts on both pastoralism and agriculture. FAO has predicted a significant decline in global cereal production by 2050 with a 20-50% decrease in productivity in the Sahel[56]. / In summary, the climate is changing and is likely to continue to change, although there is uncertainty about precisely how it will change. For the next 20 years or more the main impact of these changes is likely to be an increase in the number and intensity of climate extremes. The potentially devastating impacts of the gradual rise in global temperatures and sea levels are not likely to be felt fully until the middle of the 21st century and beyond. Vulnerability to climate change is, therefore, closely linked to climate-related disasters. It is important to note that climate is only one factor that will affect vulnerability – some studies[57] suggest that the patterns of socio-economic development also increase the vulnerability of poor people as much as the climate. Failure to correct ‘mal-adaptive’ patterns of socio-economic development will increase the risks and damage and loss from climate change. / What countries and regions are at most risk? / As well as suffering the overwhelming majority of deaths, developing countries are highly vulnerable to the impact of extreme climate events. Developing countries are more vulnerable because: / They have less resilient economies and depend more on climate sensitive activities; / They are often poorly prepared to deal with climate variability; / They are at risk from mal-adaption due to lack of finance, information and techniques in risk management, plus poor governance; / There has been little consideration of climate proof investment in areas of growing population; and, / They are already at an adaptation deficit’ from low levels of economic development. / The Sahel as an example of a region at risk / One region that has repeated climate related disasters is the Sahel. The root causes of vulnerability in the Sahel are the lack of resilience to shocks and stresses caused by drought, floods and conflict. Building resilience is vital to break the cycle of recurrent humanitarian crises in the region. The 2012 food and nutrition crisis and its aftereffects are still being felt by millions of people across the Sahel (Table 2). At the peak of its intensity, the crisis disproportionately hit the very poorest in society. Many reverted to adverse coping mechanisms including selling of livestock and buying food on credit. / In the Sahel both climate change and population growth will lead to increased competition for resources with the real risk that this could fuel further conflict in a region that is already deeply affected by conflict and insecurity. With a reliance on rain-fed agriculture, a lack of infrastructure and few diversification options, the region will be hit disproportionately hard by climate variability and is expected to be one of the worst affected regions globally by climate change. These stresses will be exacerbated by population growth. Annual population growth in Niger is over 3.5%, and the population of the Sahel will double by 2050. / Table 2: Numbers food insecure people in the Sahel 2013[58] / Country Total Population (2010) No of people at risk of food insecurity % of total no at risk across the Sahel / Burkina Faso 16,469,000 1,700,000 10 / Chad 11,227,000 1,800,000 16 / Mali 15,370,000 2,000,000 13 / Mauritania 3,460,000 1,000,000 29 / Niger 15,512,000 2,500,000 16 / Total 62,038,000 9,000,000 / Severe and persistent poverty means that people in the Sahel are extremely vulnerable to shocks and stresses. Sahelian countries are collectively among the poorest and least developed countries in the world. According to UNDP’s Human Development Index for 2011 Niger was ranked 186 out of 187 countries; Chad 183, Burkina Faso 181 and Mali 175. Indicators such as infant mortality, maternal mortality, nutritional levels and health coverage are amongst the worst in the world. Gender inequalities are also some of the highest in the world; in the 2011 Gender Inequality Index Chad ranked 145 out of 146, Niger 144 and Mali 143. Women are key actors in agricultural production, marketing food commodities, family food preparation and consumption, dietary habits, family and community health, and educating children. Yet, they often face persistent obstacles and economic and social constraints limiting their inclusion in decision-making in the field of agriculture and business. / There is a very high prevalence of malnutrition in the Sahel. An estimated 645,000 children die in the Sahel every year, with an estimated 226,000 of these deaths being directly linked to malnutrition. Sahelian countries suffer from low levels of education, lack of access to basic services, poor governance and weak markets. High food prices and price volatility have been a major contributing factor to recent food crises in the Sahel, meaning that poor people are unable to purchase food even when it is available, affecting both rural and urban households. / Conflict, civil war, military coups d’état, corruption, weak governance and poor human rights records have characterised the region for decades. Niger and Chad have experienced major conflicts in recent years and there is on-going conflict in Mali, resulting in over 430,000 displaced people[59]. There is a need for significant, long-term efforts by donors to strengthen governance and political leadership, particularly in fragile states, such as Chad, which currently cannot effectively manage major increases in aid. / A further example of the impacts of a climate related disaster are the floods in Pakistan where up to 3000 people were killed, over a million homes destroyed and more than 21 million people were seriously affected. In the immediate aftermath of the 2010 floods US$2 billion was needed for emergency relief, recovery needs came to a further US$2 billion. After the disaster a longer term damage needs assessment was undertaken, led by the World Bank and the Asian Development Bank[60]. This estimated US$8.7 to 10.9 billion was needed to reconstruct and rehabilitate the infrastructure, institutions and services that had been destroyed or damaged by the floods. This also stated the impact of the floods on the overall growth trajectory of Pakistan. At a household level the impacts are also significant; an impact assessment of 1800 households six months after the floods found that 85% of the households had reported incomes losses of up to 50%.[61] / DFID has identified the countries that are at risk from disasters as priorities to support in developing their overall resilience[62]. Many of these disasters are climate related and BRACED will provide grants to NGOs to support interventions in these countries. / What are the main policy and institutional challenges? / The early years of the 21st century have seen an increase in the commitment of the international community to reducing disaster losses. The International Strategy for Disaster Reduction (UNISDR) is a strategic framework adopted by the United Nations Member States in 2000, to guide and coordinate the efforts of a wide range of partners to achieve a substantive reduction in disaster losses. / In 2005, the international community approved the Hyogo Framework for Action; a 10-year plan to make the world safer from natural hazards. In response to the Hyogo Framework, in 2006 the Global Facility for Disaster Risk Reduction and Recovery (GFDRR) was established with a Secretariat in the World Bank. The mandate of the GFDRR is to mainstream disaster risk reduction and climate change adaptation into country development strategies, especially those focussed on poverty reduction, and into the operational strategies of the World Bank in order to support them. It works in partnership with UNISDR, whose mandate is to co-ordinate the UN system on disaster risk reduction. / Disaster risk reduction and climate resilience now have a higher profile and this is leading to increased support from multilateral and bilateral donors. In providing this it is important to recognise and address the institutional challenges. Building climate resilience can involve global, regional, national, and community financiers and stakeholders but the outcomes of specific interventions are geographically, community or sector specific. International priorities can (from a national perspective) be seen by some Governments as an opportunity to gain funding for unfunded projects across a range of national priorities. However, building climate resilience requires that the priorities of the people most vulnerable to climate change - the poor and politically excluded - are fully understood and taken into account. An understanding of the institutional complexity and the participation of local councils, civil society, the private sector and communities will be crucial to the success of any interventions. / The political will to fully address climate adaptation and climate resilience in many countries is often weak. This lack of political will carries several risks. Climate resilience may be seen mainly as a source of donor finance and the lead is given to a “political” Department which may become a “gatekeeper” and make funding decisions based on “political” rather than developmental priorities. In the absence of a technically competent lead Department, it becomes more difficult to develop capacity and build a better understanding of climate resilience. Mainstreaming climate resilience nationally requires action by a range of institutions and actors, from central to local government and the private sector to civil society. Without the political will and an associated commitment to putting in place and supporting effective institutional arrangements, this will not happen. / There can be a lack of a common understanding of the term “climate resilience” by Governments and development practitioners. Successful investment in climate resilience will require a common understanding of what climate resilience is and how it can be achieved. There is a case for a significant investment in improving understanding of climate resilience across the development community and, particularly, in developing country Governments. / Where should BRACED work? / In conclusion, in determining where BRACED should work we considered the evidence presented on which regions and countries were most at risk from climate extremes, and countries which did not yet have the capacity to respond and/or where support from development agencies on DRR and adaptation is most lacking. The following were identified for BRACED: / The Sahel – Burkina Faso, Chad, Mali, Mauritania, Niger and Senegal. / DFID focal countries at risk from climate extremes[63] (Pakistan, Burma, Ethiopia, South Sudan, Uganda, Kenya, Nepal and Mozambique). / BRACED will work at three levels of policy and governance: local, national and regional. In particular it will focus its efforts on linking local and national policies. Part of this will be linking up community and NGO action in DRR and climate adaptation, and to learn the lessons on how to scale up actions and the policies and institutions needed for this. Successful programmes that have scaling up interventions for resilience have included actions that institutionalised these interventions into local to national governance systems. BRACED will work to increase investments in time and money into local to national capacity and institutions to take outputs to outcomes. / B. The Response / How do we build resilience to climate extremes? / The response to the challenges outlined above should be to improve the resilience of people and communities to climate extremes. Resilience can be defined as “the long-term capacity of a system or process to deal with change and continue to develop”. Building climate resilience (Box 2) requires strengthening the ability of households, communities and countries to anticipate, absorb, accommodate and/or recover from climate extremes. This means where possible preventing a climate event becoming a disaster by avoiding or mitigating the impacts, and enabling countries and communities to quickly recover. / The response to the risks posed by climate extremes may take the form of moving people out of harm’s way (early warning systems and evacuation plans), shelter/physical protection (sea walls community infrastructure, environmental protection, building regulations), ensuring that essential services, food and water remain available during and after a crisis so that the poor don’t have to sell their assets (social protection, insurance, food stocks), promoting resilient livelihoods (livelihood diversification, drought resistant crops), ensuring that information knowledge is available to plan for these actions (climate and weather forecasting and the capacity to assess the risks systematically) and helping communities to recover as quickly and effectively as possible. As BRACED is responding to both slow onset disasters (mainly droughts in areas suffering from chronic food insecurity) and rapid onset disasters (e.g. cyclones and floods) it will need to support a wide range of interventions. / How does combining Disaster Risk Reduction and adaptation help build resilience? / Disaster Risk Reduction (DRR) is an approach that evolved from humanitarian relief, to go beyond emergency responses to a planned approach to reduce the risk of disasters occurring and the impact when they do occur. DRR provides a framework to build resilience to climate extremes, through measures including; identifying the risk, transferring the risk (for example re-insurance), avoiding the risk (for example early warnings), and reducing the risk (for example preparedness of infrastructure).[64] Disaster risk reduction shares some key characteristics with approaches to building resilience: (1) it is a holistic framework for assessing national systems, communities and individuals; (2) it places an emphasis on capacities to manage hazards or risks; (3) it incorporates options for dealing with uncertainty, surprises and changes; and, (4) it is proactive[65]. A system that is effective in managing risk is likely to become more resilient to shocks and stresses. / A study[66] on the economics of resilience in Ethiopia and Kenya clearly demonstrated the need to combine DRR and development together. In Kenya the study found that early response to drought could save between $107m and $167m for a population of 367,000 in a single event alone. In southern Ethiopia, with a population of 2.8m, household level data suggest that early response could save between $662m and $1.3billion in a single event. / However as identified by the HERR, the DRR approach does not sufficiently address the risks that climate change poses; so there is a need to integrate climate change risks into DRR. Climate extremes differ from the traditional hazards that DRR addresses in in some important aspects. Unlike other hazards[67] we know the risks posed by climate extremes are going to increase over the longer term, on the other hand there is considerable uncertainty as to exactly how these changes will manifest and managing climate risks requires being prepared for surprises – for example the one in a hundred year flood happening every ten years. Therefore a flexible approach that can incorporate new information as it is generated is important as well as investment in improved forecasting and knowledge of what works, to reduce uncertainty and enable choice and capacity to respond. There is a need for coherence with climate change adaptation interventions, such as resilient agricultural development, that seek to keep development on track in the face of climate change, and for a joined up approach and understanding between communities of practice on DRR and climate change resilience. In summary we need to make DRR ‘climate smart’. / What policy and institutional links are needed to sustain and build resilience? / There is also a need for better connections between local and national approaches. For example investment in national early warning systems will have limited impact on the lives of millions of poor people without local investment in, for example, cyclone shelters so that people can act effectively on the warnings. At the national level and in the context of policy formulation, it is necessary to consider the vulnerability to climate extremes from a sector perspective. For example the water, tourism, health, urban, agriculture, and housing and transport infrastructure sectors are all clear priorities. On the other hand, at the community and household level, planning purely from a sector perspective is less helpful. Poor people have complex livelihoods and it is more appropriate to identify the specific risks communities may face (such as drought, floods, saline intrusion) and build resilience from the perspective of their livelihoods. For example recent local climate resilience assessments in the drylands of Kenya have shown that it is better, from poor people’s perspective, to focus on measures to make local economies and natural resource governance systems resilient.[68] Interventions should be based on the priorities of communities and an understanding of what works, and this engagement should be maintained through the implementation. / The most effective disaster risk reduction and climate adaptation actions are those that deliver development benefits in the short-term and reduce vulnerability in the long-term[69]. They combine efforts to tackle the causes of poverty and vulnerability, integrate knowledge of changing risks and build adaptive capacity. The BRACED programme will seek to build coherence across this spectrum, from immediate humanitarian response, to traditional DRR, to longer term adaptation to climate change and resilient growth. BRACED will address the HERR recommendation to integrate the threat from climate change into disaster risk reduction by expanding this approach to explicitly accept the high levels of uncertainty around climate events and respond accordingly, it will work across the DRR, social protection and climate adaptation disciplines, and across ‘top-down’ institutional and ‘bottom-up’ community approaches, whilst building evidence on what works and why. Only by embedding efforts to build climate resilience within permanent institutional processes will it be possible to achieve the strategic, coordinated and long-term perspective that an effective response to climate change requires. Box 4 provides a case study of a successful intervention to help build the resilience of farmers in the Sahel, which built on grassroots actions and linked with wide range of different institutions. / Box 4: Example of success - Regreening the Sahel / Recent studies[70] on long-term trends in agriculture and environment in the Sahel show some interesting trends The first is that farmers in several densely populated regions of Niger protect and manage the natural regeneration of trees and bushes on their farms. This process was catalysed from around 1985 and has since led to much higher on-farm tree densities on a total of about 5 million hectares. This is the largest-scale recent environmental transformation in the Sahel - and possibly in the whole of Africa. / This protection and management of useful trees on farms concerns a number of indigenous species such as Faidherbia albida (a fertiliser tree that also produces large quantities of fodder for livestock), Piliostigma reticulatum (fodder, soil organic matter, fuelwood and poles), Combretum glutinosum (fuelwood and poles), Adansonia digitata (leaves and fruit for high-quality nutrition), Guiera senegalensis (fodder, green manure and fuelwood), and Shea trees (which provide about 40% of the income of rural women in Mali). / The resulting tree cover is estimated to produce about 500,000 additional tons of grain each year, enough to feed about 2.5 million people[71] The annual production of these new trees is now worth at least 200 million euro to the farmers. This estimate the values of produce and own use of non-food tree products. These agroforest parklands appear to be spreading in the Sahel: recent work by the US Geological Survey has mapped an expansion of parklands on about 450,000 hectares in the Seno Plains of Mali (Tappan, 2012). / A paper[72] about to be published looks at farmer’s perceptions of the impacts of re-greening on food security in Niger shows that the Kantché district (350,000 inhabitants) in Southern Zinder, which is characterized by high population densities and high on-farm tree densities, produced a grain surplus in 2011, a year of below-average rainfall, as well as in the four preceding years. Besides this, some species, like baobab, produce significant cash income through the sale of the leaves. During drought years, many farmers in the Sahel literally survive thanks to their trees: these provide non-food products (timber etc.) whose sale in the market allows the purchase of sufficient food and of seed for the next planting season. / Why is government intervention needed to help build resilience to climate extremes? / Some people will adapt to an increase in climate extremes by changing their behaviour, their livelihood strategies and changing their geographical location. However not everyone, especially the poorest, will have the means to make the changes needed. There is a strong case for government intervention to help these people to adapt to climate extremes.[73],[74] / Governments can also seek to influence the broad patterns of macroeconomic development that can build resilience to climate extremes and disasters. We know for example, that macroeconomic stability can help countries recover from extreme events[75]. We have less evidence on what types of policy work help build resilience across communities within a country. / Whilst these factors provide a rationale for Government investment in building resilience to all natural hazards, they particularly apply to climate extremes where the risks are increasing, uncertainty is high and the past does not provide a guide to the future, making ‘autonomous adaptation’ by the poorest and most vulnerable families and communities even harder, in the absence of Government support. / Table 3: Why governments should be involved in building resilience to climate extremes[76] / Rationale Description and examples / Public goods Public goods are goods that the market does not provide on its own because people can “free ride”, or use the good without paying. These goods will only be provided by government – for example flood protection is provided by government because a private company would find it difficult to charge people for this service. / Many goods needed to help build resilience to climate extremes are public goods; including flood protection, better sea defences, and dissemination of climate information. / Often it is not profitable for insurance companies to provide insurance against climate extremes[77], which means that governments have a role as the insurer of last resort. / Assistance to vulnerable groups Governments have an important role in protecting poor and vulnerable people in society. Many people in developing countries are too poor to bear the costs of adaptation on their own, and especially for a problem they have not caused / For example, poor people in flood prone areas may be unable to afford the costs of raising their houses on plinths. / Governance failures The SREX report notes that the ability of governments to implement disaster risk management responsibilities differs significantly across countries, depending on their capacity and resource constraints. Governments (and other spending organisations) sometimes fail to provide disaster risk reduction and other adaptation goods and services because they: / (i) Lack institutional capacity; / (ii) Are uncertain about when disasters will occur; / (iii) Have limited knowledge and experience of the costs of disasters and the benefits of early action. / What are the consequences of not intervening? / As the HERR highlighted it is predicted 375 million people a year will be affected by climate related disasters by 2015 and the number is expected to increase over time. This programme will make 5 million people more climate resilient by 2015, by large-scale funding at the grassroots level. The evidence building and institutional capacity strengthening components in the long term can be expected to benefit many millions as new programme innovations are introduced, and improved institutional and policy frameworks lead to more effective government action. / In addition the programme is expected to serve as a catalyst for Governments, the private sector and NGOs to provide additional funding, both directly to build climate resilience but also for long-term investments to reduce poverty. By “doing nothing”, 5 million people would not receive direct support and become climate resilient. Instead they are likely to become increasingly vulnerable as extreme climate events become more frequent and intense. Without the evidence building component the opportunity for learning lessons and strengthening institutions and improving policies will be lost. This will mean many more people remaining vulnerable to climate extreme events and disasters. Not supporting the Sahel Resilience Strategy could lead to increased humanitarian disasters in the Sahel and increased instability in the region. / C. Policies, Strategies and Programmes / How does this programme link to International Climate Fund (ICF) priorities? / Disaster Risk Reduction was identified as a priority for investment in the International Climate Fund (ICF) Implementation Plan (2011 – 15), approved by Ministers. This states: ‘The ICF will prioritise investment for adaptation in the following sectors through multilateral and bilateral channels - Disaster risk reduction (DRR) investments such as integrated DRR and adaptation planning, critical infrastructure, developing early warning systems, macro and micro insurance and addressing impacts on girls and women’. In addition DRR is a key aspect of other priority adaptation sectors under the ICF including agriculture, infrastructure and urban investments, coastal zone and ecosystems management and social protection. / How does this programme link to DFID’s overall response to the HERR and action on DRR? / The BRACED programme offers an important opportunity to help meet commitments under the UK Government response to the Humanitarian Emergency Response Review (HERR)[78]. The HERR recommends that the UK Government should do more to help people become better prepared to cope with the impact of future emergencies- to ensure that they remain hazards and do not turn into disasters. According to the report, doing this requires a renewed focus on resilience and preparedness. Of most relevance is the HERR recommendation that ‘DFID should ensure that building resilience becomes part of its core programme in at risk countries, by integrating the threat from climate change and other potential hazards into disaster risk reduction’. The BRACED programme will be an essential mechanism for helping achieving this. / How does BRACED contribute to HMG strategy on the Sahel? / An important HERR commitment that BRACED will help to achieve is to ‘champion the development of regional resilience programmes – starting with the Sahel’. BRACED will support the Sahel Resilience Strategy led by Africa Regional Department (ARD). BRACED will address the priorities it identifies for example by providing resources to civil society organisations in the Sahel to build resilience at a community level and to hold governments to account at the national level. / BRACED is linked to the programme Building resilience in the Sahel through adaptive social protection. This will provide up to £50 million over three years to support national systems for adaptive social protection in the Sahel. This programme will provide an additional tool to address the root causes of vulnerability in the Sahel for the poorest and build long term resilience to climate extremes such as drought and floods, vital to breaking the cycle of recurrent humanitarian crises and conflict in the region, that trap millions in poverty. / ARD will work to ensure coherence between BRACED and ARD’s existing portfolio in West Africa. This includes work on livelihoods, food markets, regional integration, climate change and innovative new risk financing mechanisms such as the Africa Risk Capacity initiative and the West Africa food markets programme. / BRACED will build on DFID’s existing humanitarian programme in the Sahel. DFID is supporting humanitarian programmes in the Sahel in 2013, through UN agencies and NGOs, on immediate response and early recovery. Whilst humanitarian programming gives people the emergency support they need to survive and to start to recover from the current crisis, resilience programming will enable them to maintain or transform their living standards so that they are able to withstand shocks and stresses without compromising their long term prospects. Humanitarian programming is an essential counterpart to resilience programming, and will help ensure that resilience gains are not lost during crises that may occur in the coming years, but on its own is not sufficient to lift people out of extreme poverty. / What are the links to Future Fit? / Future Fit is a DFID Executive Management Committee (EMC) initiative to produce a vision and strategy for DFID’s response to the challenges and opportunities that climate change and resource scarcity pose for poverty reduction and development. Future Fit asks the question what strategic shifts in our investment portfolio in front line sectors – Food, Water, Energy, and Cities are needed to protect development gains and respond to the challenge of climate change and resource scarcity. BRACED is responding to these challenges, and demonstrates the links between climate and development finance to deliver poverty reduction, growth and sustainable development goals. / What are the links to DFID global, regional and country humanitarian and DRR initiatives? / DFID’s Conflict Humanitarian and Security department (CHASE) has agreed a grant of £20 million to the Global Facility for Disaster Reduction and Recovery (GFDRR) for track 2 (Mainstreaming disaster reduction in development). This is core funding for the GFDRR’s overall operations to mainstream DRR and adaptation into national development strategies to achieve the MDGs. This type of funding is not tied to a particular theme or project and can be spent against any activity that relates to GFDRR’s mandate; it will also help embed organisational-wide reforms, such as better reporting of results at the country level. Additional support to GFDRR will be an option appraised in the full business case for the fourth component of the programme. / BRACED will complement and support CHASE’s work on Embedding Disaster Resilience in DFID Country Programmes. DFID’s Structural Reform Plan states a commitment to do this by 2015, and was a direct response to the HERR. Eight country offices, Bangladesh; Ethiopia; Kenya; Malawi; Mozambique; Nepal; Sudan; and Uganda, have now done this and a further six, Burma, DRC, OPT, Pakistan, Somalia, South Sudan and Yemen, are in the process of doing so. One key lesson from the first eight countries was the need to better link disaster resilience and climate change adaptation. Many country offices combined the Climate Change Strategic Programme Review and Disaster Resilience work processes. / BRACED will support DFID county office resilience strategies in two ways. Firstly, funding NGO led activities on DRR and adaptation, and policy and institutional work through component D. Secondly, through the Component C on building and sharing evidence on DRR and adaption the programme will benefit DFID’s country offices and other development partners. BRACED will be an important source of knowledge, and for example in a country like Pakistan which is developing a major bilateral resilience programme, work to share the knowledge this generates. / CHASE is developing a new Global Humanitarian Action Programme (G-HAP) to provide up to £40 million to UK international NGOs to increase their capacity for humanitarian response to disasters. G-HAP and BRACED will complement as each responds to different and distinct needs and commitments in the Government’s response to the HERR. / The Secretary of State co-chairs a ‘Political Champions for Disaster Resilience’ group with Helen Clark (UNDP). This group which consists of developing country and international development ministers, and development agency heads[79] has been convened to provide a greater focus and investment in disaster resilience. The champions met for the first time in April 2012 and agreed to focus initially on the key areas of regional resilience in the Horn of Africa and long-term resilience in the Sahel (as well as financial management of disaster risk and public-private innovation). The BRACED programme will be of clear relevance to the UK’s commitments as part of this group to scale up investment in disaster resilience, and particularly resilience in the Sahel, and offers an opportunity for increasing donor and multilateral coherence, and engaging the private sector in this area. / DFID’s Growth and Resilience Department (GRD) is working to promote the resilience of poor and vulnerable people so that growth strategies do not leave them behind. This will mean increased investment by Governments and other actors in longer term resilience-building such as social protection, livelihoods promotion, risk financing and insurance mechanisms and encouraging private investment strategies that are sustainable in the long term. Following recommendations of the DFID Development Policy Committee, GRD’s resilience policy work focuses on food and nutrition security, climate change, and social protection. GRD works closely with CHASE taking the post-HERR disaster resilience agenda forward and we will work with them on the relevant outputs of BRACED. / What are the links to DFID’s research programmes? / BRACED will complement other ICF investments in adaptation for small holder farmers and in urban areas. Two programmes are particularly relevant. The first is the Collaborative Adaptation Research Initiative for Africa and Asia (CARIAA) a research partnership with the International Development Research Centre (IDRC) with an investment of £37 million by the Climate and Environment Team in Research and Evidence Division. The second is the Climate Change, Agriculture and Food Security programme of the CGIAR (Consultative Group on International Agriculture Research) which includes research on the Sahel and in other regions at risk of climate extremes. BRACED will be expected to develop links with these programmes both in terms of using research evidence and in terms of informing the research agenda. / There is however little evidence on resilience in fragile and conflict affected states. DFID is therefore developing a new approach to build the knowledge and evidence base on resilience in such areas – which will include many BRACED focus countries. This will be jointly led by ARD, RED and CHASE. BRACED will ensure that the research/learning component is consistent with and supports this approach and that the programme is a major contributor to DFID’s evidence base on resilience. / What are other development agencies doing? / A survey of international financing mechanisms and funding streams on disaster resilience[80] highlights other relevant organisations and initiatives working in this area. These include the UNDP Bureau of Crisis Prevention and Recovery (BCPR), which has a goal to ‘integrate climate risk management and disaster risk reduction into broader national development and recovery plans’, and the International Strategy for Disaster Reduction (ISDR) which is not operational but was setup to coordinate UN DRR activities at the global level. ISDR’s first strategic level objective is that ‘disaster risk reduction is accepted and applied for climate change adaptation'. This survey lists other significant donors on Disaster Risk Reduction to be Australia, Brazil, Canada, Denmark, European Union (through the European Commission Humanitarian Aid and Civil Protection Office – ECHO), Germany, Japan, Norway, Sweden, Switzerland and the United States, but does not identify climate change as a priority for any. This report found that despite the actions of these organisations and other recent initiatives, a significant global funding gap remains for the upstream aspects of disaster resilience building, particularly in respect of the critical roles of NGOs and the private sector. / What are others doing in the Sahel? / The 2012 food crisis in the Sahel, following the 2011 Horn of Africa food crisis, led to increasing international attention on resilience and unanimous agreement that current approaches in the Sahel have failed to end the cycle of hunger and that greater efforts are needed on resilience in order to reduce the impact of future food crises. The most significant international initiative is the Alliance Globale pour I’initiative Résilience-Sahel (AGIR-Sahel), formed during a high level consultation in June 2012 of Sahel governments, regional organisations, multilateral organisations and donors. The US, France and the EU have all been actively engaged in the AGIR process. AGIR developed a four pillar road map for building resilience in the Sahel, particularly in Burkina Faso, Niger, Chad and Mauritania,. BRACED will particularly contribute to pillar three; Increasing food production, the incomes of vulnerable households and their access to food in a sustainable manner. / All the main UN agencies working on food security, nutrition and humanitarian response in the Sahel, notably OCHA, UNDP, WFP, FAO and UNICEF, are now prioritising resilience and developing resilience strategies and programmes. WFP, UNICEF and FAO, the main UN agencies working on food security and nutrition, are starting to work together to tackle the root causes of under-nutrition as well as to respond to current cases of chronic and acute malnutrition. / A large number of International NGOs have resilience programmes in the Sahel, and have been piloting innovative approaches. Operational research by these NGOs has demonstrated the effectiveness of early action and a new approach to resilience building – ‘integrated resilience building’[81]. This has been demonstrated through new conceptual frameworks including the Africa Climate Change Resilience Alliance (ACCRA) and the Local Adaptive Capacity Framework (LAC)[82], which is now enhancing the effectiveness of adaptation, DRR and resilience programming. The Sahel Working Group, an informal inter-agency network, and Regional Learning and Advocacy Programme (REGLAP) for Vulnerable Dryland Communities represent other specialist consortiums that are supporting integrated resilience approaches and their focus on all sectors and levels of government[83]. / The Sahel Working Group have developed a strategy for resilience in the Sahel based on lessons learnt during the 2010 crisis. NGOs in particular have led in lesson-learning and innovation in their work in the Sahel and the Horn of Africa, and many are already implementing programmes to build resilience at the community level. BRACED will provide grants to these NGOs to scale up their activities, which have the potential to be replicated and scaled in West and/or East Africa[84]. / An evidence paper[85] (summary in Box 5) prepared for this Business Case found that there is a clear funding need for NGO partners to scale-up resilience-building, adaptation and DRR activities in the Sahel. The review also recommended grants of between £1m and £10m as an appropriate scale for NGOs to absorb effectively and to deliver a fast and significant increase in the number of people being supported to cope with the impacts of climate change. / Box 5: Potential of NGOs to build resilience to climate extremes / International non-governmental organisations (NGOs) were invited to engage in the stakeholder consultations. These included Action Aid, CAFOD, CARE International UK, Christian Aid, Concern Worldwide, Oxfam GB, Plan International, Practical Action, Save the Children, Tearfund, Water Aid and World Vision. This group was selected based on their membership of the BOND Development and Environment NGO Group. / The NGO focal points provided details of current and planned resilience-building initiatives in Burkina Faso, Chad, Mali, Mauritania and Niger, as well as Ethiopia, South Sudan, Sudan, Somalia, Kenya, Uganda, Tanzania, Mozambique, Nigeria, Malawi, Zimbabwe, Nepal, Burma, Pakistan, and Bangladesh. Financial, policy and institutional challenges of existing programmes were communicated and potential activities that could potentially be scaled-up through the BRACED programme shared. The review estimated a financial gap of more than £378 million for resilience-building projects and programmes in the focal countries. / The NGO consultation was used to produce an illustrative pipeline portfolio. The data on funding gaps and numbers of beneficiaries were from a small sample of NGOs and hence the figures are indicative of activities BRACED could fund. / Absorptive capacity varies and larger NGOs have the capacity to manage grants of up to £10million over three years. Other NGOs consider the optimal grant sizes are £0.5 - £2.5 million for single-country three year project. / There is a larger average and range of optimal grant sizes for the multi-country projects versus single country projects. The average grant size for a single country project was £2.8 million over three years while for a multi-country project of three or four years duration is £8.2million. The ranges was from £0.3 million to support activities by NGOs operating in Mozambique, Malawi and Zimbabwe, to £48.5m for a new programme integrating child-centred disaster risk reduction across several fragile and conflict-affected countries in the Sahel.
B. Impact and Outcome that we expect to achieve / What results do we expect to achieve? / Impact: BRACED aims to make up to 5 million[86] vulnerable people, especially women and children, in developing countries more resilient to climate extremes[87]. In addition, through improved policies and institutions at national level and better understanding of DRR and adaptation, we expect the programme to reach many millions more indirectly. Estimates of these indirect beneficiaries will be determined during implementation. / Two indicators will be used to measure the impact of BRACED: / Reduction in the number of deaths caused by climate extremes and disasters. / Proportion of children under 5 who are suffering from global acute malnutrition and severe acute malnutrition as a result of climate extremes and disasters. / The outcomes of the programme will be: / Poor people in developing countries reached by interventions designed to make them more resilient to climate extremes. Indicators: / Number of people supported to cope with the impacts of Climate Change (ICF KPI 1). / Number and type of assets protected or improved per household. / XXXXX / Knowledge and evidence for building resilience to climate extremes is built and is used/influential at all levels (local, national, regional, international and within DFID). Indicators: / The number of countries where climate information is used to inform responses to climate extremes has improved (ICF Ada TI) / The number of countries where the extent to which planned interventions are likely to have a transformational impact (ICF KPI 15). / To deliver these impacts and outcomes BRACED has four outputs: / Large scale interventions[88] are in place to make people less vulnerable to climate extremes. Results include: large scale interventions established in five Sahelian countries and 6 other countries in Asia and other parts of sub-Saharan Africa to help reduce the risk of up to 5 million people to climate extremes. / Indicators: / Number of people whose resilience to climate extremes and disasters has been improved (ICF KPI 4) - disaggregated by programme type, gender, age and % of programme beneficiaries who are poor and extremely poor. / Number of countries where large scale interventions have been established, disaggregated by region (Sahel and Other) and type and number of intervention. / No of effective partnerships built between NGOs, local government and private sector to deliver interventions. / The number of countries where the quality of stakeholder engagement in decision-making to address climate extremes and disasters has improved (ICF Adaptation Indicator). / Increased capacity of local government, civil society and private sector to respond to climate extremes. Proposed results include: number of countries with improved early warning systems for climate extremes; number of interventions building resilience to climate extremes. / Indicators: / Number of countries with improved early warning systems for climate extremes disaggregated by region: / Depending on the types of interventions proposed and the focus of the work planned under Component C of BRACED a combination of ‘scorecard’ indicators will be used. / 3 of the Institutional level indicators from the Guidance on Measuring Disaster Resilience will be adapted for climate adaptation and disaster risk reduction for use by BRACED. / Better understanding of what works in building climate resilience from DRR and climate change adaptation interventions. Results will include evidence and sharing of knowledge on: economics of building climate resilience; effectiveness of micro-insurance; cost effectiveness of private sector and NGO-led DRR insurance programmes; role of private sector in DRR and adaptation; how to take innovations to scale; and, how to work in hard-to-reach and fragile locations. / Indicators: / Number of evidence studies and documents produced on climate change adaptation and DRR to climate extremes. / Number of strategic level evaluations (including beneficiary participation) commissioned and published. / The number of project level evaluations of climate change adaptation and DRR carried out by partners brought together under meta-analysis. / Number of new and existing climate change adaptation and DRR programmes whose design and/or implementation approaches are informed by the evidence from BRACED M&E and knowledge work. / Number of ICF and DRF indicators that BRACED is able to collect data for and report against. / Improved policies integrating DRR and climate change adaptation are in place at local, national, regional and international levels. Proposed results include: numbers of national resilience strategies incorporating adaptation and risk reduction in place and implemented; number of multilateral agencies with integrated policies on DRR and adaptation, number of countries where DRR and Adaptation are part of national and sectoral ministries policies and plans; and number of regional plans/actions on cooperation in DRR and climate adaptation. / Indicators: / Number of national and regional resilience strategies incorporating climate change adaptation and risk reduction in place and implemented. / Number of multilateral agencies and regional organisations with integrated policies on adaptation and risk reduction. / Under Component C of BRACED a combination of ‘scorecard’ indicators will be used, developed by the DFID Tracking Adaptation and Measuring Development Programme. / The logframe for BRACED with details of these expected impacts, outcomes and outputs is given in Annex F. The logframe will be a living document with milestones and targets being added after the selection of the NGO grants under Components A and B. Details of how the total number of people BRACED will help to be more resilient to climate extremes was calculate are given in Box 6. / A schematic Theory of Change is shown in Figure 2 below. BRACED will seek to achieve its stated impact to make poor people more resilient to climate extremes by two main pathways: / In the short term by the direct impact of funded projects on the resilience of men women and children in the communities targeted (thick orange line). / In the longer term it will achieve a transformational impact on resilience of poor people in vulnerable communities over time (sustained) and across regions (geographic) as well as social groups, ecological regions and economies through a longer pathway. This will be to learn lessons from funded projects of what approaches work in what context, and to influence policy making and development planning in national governments, regional institutions, local government and through international initiatives. Component D still to be designed will be key part of this at the national and regional level. / Figure 2: BRACED Theory of Change / This illustrates the central importance of Component C to BRACED, to learn from the range of approaches supported, and the importance of political economy considerations in influencing governance structures for sustainability and long term impact. It also highlights the importance of accountability of government to communities, to ensure lessons are implemented at local level. / What will BRACED do? / To deliver these outcomes three immediate components are proposed. A fourth component on building institutional capacity will be developed subsequently. The four components are: / Scaling up actions on the ground to build the resilience of people to cope with climate extreme events in the Sahel. (Budget up to £60 million). This is expected to directly benefit up to 5 million people. Boxes 5 and 6 provide details on how this figure was estimated. / Scaling up actions on the ground to build the resilience of people to cope with climate extreme events in DFID focal countries at high risk of these events (Budget up to £40 million) / Building evidence and testing approaches on adaptation and DRR (Budget up to £10 million) / Development of national and international capability and capacity on response to climate related disasters (Budget up to £30 million). / Together these four components will directly benefit people at risk from climate extremes, and build momentum among international partners on the importance of integrating climate change into disaster risk reduction. Improved evidence of what works and on the economics of investing in building resilience should pave the way for future at-scale funding for adaptive social protection, micro-insurance, and large-scale private funding mechanisms for spreading or transferring climate/extreme weather risks. / Box 6: Estimating the number of people who will benefit from BRACED / Direct beneficiaries / Estimating the total number of people who will directly benefit from BRACED depends upon the projects the programme supports under Components A and B, which cannot be defined until the projects have been designed and the best ones selected for funding. There is also a wide variation in the types of support to be provided. / Projects that support better planning and awareness on disasters due to climate extremes can benefit the entire community or district. For example a project that develops an early warning system to floods has the potential to directly benefit all who live in the flood risk area, which in areas of high population can be tens of thousands of people. Providing farmers and pastoralists with better access to weather forecasting –especially seasonal forecasts and advance notice of below average rains and potential droughts – can again benefit thousands of people. Similarly the development of community adaptation planning by NGOs and local government and its take up across districts and provinces has the potential to benefit a large number of people. / Whereas projects that develop and promote improved technologies and structures to help build the resilience of people to climate extremes will depend upon who has access to these technologies and structures. Examples of this are: better housing constructed on plinths or stilts that stand above floods; construction of cyclone shelters; and, irrigation structures for farmers. Here the number of people benefitting will be closely related to the unit cost of the intervention and thus to the overall size of the investment and project. / Other projects fall between the two. For example the development of better soil and water conservation measures and agroforestry (in the Sahel) and floating gardens (in Bangladesh) are about the use of approaches and knowledge. In these examples the number of people benefitting is the number of people using these approaches and practices. Therefore the impact of the intervention will be the total number of people adopting and using it. This could be by a project working to develop the technology with communities and then piloting it, and/or focussing efforts on sharing the knowledge of the approach across a whole district or province, or sometimes a whole country. / BRACED is expected to provide grants to NGOs to cover projects that do all of the above. Thus giving a precise figure on the total number of people BRACED will directly benefit is difficult. To estimate this we have used evidence from the evidence paper of NGO projects and consultations described in Box 5[89]. The study found that if funded in its entirety, the ‘Illustrative Pipeline Portfolio’ of NGO activities (indicatively priced at £378 million) would reach at least 33 million direct and indirect beneficiaries, most of these women, children and other individuals highly vulnerable to climate extremes and disasters in the DFID focal countries[90]. This can be disaggregated into around 14.2 million direct beneficiaries and 19.5 million indirect beneficiaries[91]. Using this evidence we estimate that the average number of people supported by a grant averaging £5 million will be about 250,000[92]. / Assuming BRACED awards twenty grants this would mean BRACED would directly support approximately up to five million people. This estimate requires further work, which will be undertaken in assessing the concepts and full proposals for grants where NGOs will be required to provide these details (see paragraphs 116 and 115). / Indirect beneficiaries / Components C and D of BRACED are also expected to help people build resilience to climate extremes. But these will be indirect benefits. Component C is expected by building and sharing the evidence on what works on DRR and adaptation interventions to inform new programmes and improve policies. Component D will again produce significant impacts by strengthening policies and institutions in countries to respond to climate related disasters sustainably. In implementation BRACED will aim to measure these impacts but until Component D is fully designed, and Component C started it is not possible to provide precise estimates. However they are expected to be significant, for example strengthening the capacity of an entire country to respond to climate related disasters could benefit all those at risk of these disasters in that nation. / Component A: Scaling up of DRR and adaptation in the Sahel / This component will work in Burkina Faso, Chad, Mali, Mauritania and Niger, and will provide large-scale support to adaptation and DRR activities at the grassroots level through grants to alliances/consortia of NGOs, local government, private sector and research organisations. These will be used to build the resilience of households and communities in the Sahel by improving and diversifying livelihoods, developing shared management systems of resources critical to resilience (water, rangelands, and forests) and embedding disaster risk reduction and adaptation in to climate change and development responses. / An important part of the activities will be building the evidence and strategies to resolve competing land uses (land/water/forests/ rangelands), and supporting communities to build resilient and sustainable livelihoods. For example ensuring agricultural and pastoralist livelihoods are able to co-exist and support each other in a changing climate. / Component B: Scaling up DRR and Adaptation in DFID focal countries / This component will scale up DRR and adaptation actions in DFID focal countries whose populations are at high risk of climate extreme events. These are to be finalised but potentially will include Pakistan, Burma, Bangladesh, Ethiopia, South Sudan, Uganda, Kenya, and Mozambique. The component will provide large-scale support to adaptation and DRR activities at the grassroots level through grants to alliances/consortia comprising of NGOs, local government, private sector and research organisations. These will used to build the resilience of households and communities by improving and diversifying livelihoods, flood protection, early warning systems, and community adaptation planning. / Challenges and Criteria for grants for components A and B / One of the challenges to Components A and B is to avoid “just” funding good adaptation projects that build resilience to climate extremes without reference to scale up, policy influencing and sustainability. This is because there are likely to be limits to the extent to which poor communities can develop resilience just from within. Economic diversification may entail better links to markets or seeking jobs elsewhere for parts of the year. Other forms of local support from outside the community may also help break or reduce the efficacy of mechanisms by which communities are indirectly adversely affected by weather and climatic shocks. Most successful interventions for resilience have therefore aimed to institutionalise interventions into local to national governance systems[93]. / In addition to supporting adaptation projects that might be ‘islands of excellence’ BRACED will support a broader set of interventions that involve policy influencing, political economy analysis and promoting empowerment and accountability. For example, promoting greater transparency and accountability in the use of adaptation and resilience funding through participatory monitoring processes. Grant recipients will need to demonstrate how the impacts of their projects will be sustained. / Evidence and experience already exists on how community-based DRR and adaptation can benefit people. However, funding to local level DRR and adaption is limited and often tied to a specific humanitarian response, when it could be considered to be too late. BRACED will support NGOs in partnership with UN agencies, national governments and the private sector to increase the number of programmes they deliver to help build the resilience of people to extreme climate events. / A two stage process will be undertaken in the selection of grants. There will be an initial call for concepts. The best of these will be selected and proponents asked to develop full proposals. To enable them to do this grant proponents will be allowed to apply for a project preparation grant of up to £250,000. The purpose of this significant grant size is to allow proponents to build alliances for new consortia to implement scaled up projects. Establishment of consortia will be a condition for successful bids, as well as the development of an evaluation framework in partnership with wider BRACED programme. / The grant will also be used to undertake pilot work to provide more evidence on the costs and benefits of the proposed approaches – including details on the unit costs of proposed actions; and the development of a results framework and clear theory of change. The building evidence Component C will be expected to share the knowledge generated from the project preparation phase. A detailed budget for the project preparation grant will be required to be submitted with the concept with all costs fully justified. It is anticipated that many concepts will require significantly less than the maximum grant amount, including where the proposal is partly funded from other sources (e.g. other donors or multilaterals). / The allocation of project preparation grants will be rule based, with concepts selected against eight key criteria: / Does the project propose work in one or more of the target countries? / Does the concept clearly set out what climate extremes and risks it will address, and how these will impact on people especially women? / Are the approaches and technologies it plans to scale up to build resilience of communities to climate extremes feasible? / Does it take these to scale and aim to reach at least 250,000 people directly or indirectly? / Degree that it involves partnerships between NGOs, local government, private sector and research organisations, demonstrates roles of the different partners, and indicates how lessons on policy and institutional changes to sustain impact will be determined? / Indicate how the results of the project will be sustained? / Do the proponents and partners demonstrate they have the capacity and capability to implement the proposed project? / Does the concept set out a plan for monitoring and evaluation? / Full project proposals will be assessed against more detailed criteria. These are given in Box 7 for both components A and B. It is expected that the average grant size will be £5 million over three years and will benefit up to 500,000 people giving an estimated total of 5 million directly helped by the BRACED programme. Higher grants of up to £10million will be considered where more than one country is to be supported. The minimum grant is expected to be £3million. / Box 7: Criteria, eligibility, length and size of grants for Component A and B / Criteria for Component A (Sahel): Criteria for Component B (DFID focal countries): / Support actions in one or more of the Sahelian countries: Mali, Burkina Faso, Chad, Mauritania, Niger. / Support the implementation of DFID’s Sahel Resilience Strategy. / Demonstrate how project will contribute to the prevention of violence and promotion of non-violent and participatory solutions. Support actions in one or more of the DFID focal countries that are at risk from climate extremes / Demonstrate how the project contributes to wider DRR and country resilience strategies. / Common criteria: / I. What the project will do and who will it help? / Identify what the climate extremes and risks are being addressed and how these may change in the future, and how the project will help manage and reduce these risks. / Scale up proven technologies and approaches on adaptation and DRR that have demonstrated results to build the resilience of people, and the ecosystems they depend upon, to climate extremes. / Identify how it will address economic empowerment to help build resilience through measures focused e.g. on helping create more and better jobs or key assets. / Identify which groups of people will be supported, clearly target poor people, and how it will benefit women and girls in particular, and vulnerable groups including the disabled and elderly. / Set out how these groups have been involved in the design of the project with a full gender analysis. / II. Partnership, Policy and Lesson Learning / Degree of partnership with local government, CSO, private sector and research organisations) and how partnerships will be built and sustained. / Extent on how stakeholders were and will be involved. / Demonstrate how project will build local and national capacity to sustain efforts after the grant ends. / How lessons will be shared and south-south learning promoted. / Identify how it will address policy and institutional needed to support the scaling up of DRR and adaptation. / III. Results / Clearly set out what results will be achieved, and the extent and numbers of people that will be helped. / Demonstrate how the project delivers value for money and clearly set out unit costs. / How the project will be accountable to all stakeholders. / Demonstrate how it will be evaluated. / IV. Capability / Evidence on how the organisation has successfully implemented similar programmes to scale up the impact of its work, and demonstrate it has the capacity and capability to do this again. / Amount of co-finance and leverage of investment from others. / Set out the risks to the project and how these will be managed. / Eligibility: Grants will be made to alliances or consortia consisting of an NGO and one or more of the following types of organisations: local government, private sector and research organisations. / Length of grants: Grants will be made for an initial three years. Subject to performance and approval of a second phase of BRACED they may be extended. / Size of grants: Minimum of £3 million and maximum of £10 million over three years. / Calls: One call for major grants is expected at the beginning of the programme. Further calls for specific actions will be determined during the implementation of BRACED. / Component C: Building evidence on adaptation and DRR / This component is of central importance to the Theory of Change for how BRACED will deliver a sustained transformational impact on people’s resilience to climate extremes, beyond the communities directly supported by funded projects. It will do this by learning lessons and building evidence on what works in different contexts, in order to both inform institutional approaches but also cross learning to other communities. It will work with NGOs, private sector, academics and governments to assess experience, and aim to build linkages with research institutions. / This component responds to the evidence from several sources of knowledge gaps in this field, hence BRACED will have a clear public good role in filling these gaps with all data generated being made freely available. For instance the recent HMG Foresight report on ‘Reducing the Risks of Future Disasters’[94] calls for the development of reliable measures of resilience combined with an evidence base on the cost and benefits of different interventions to support decisions on DRR investments. It states that the ‘current understanding of best practice in disaster risk reduction is very limited’ and recommends that ‘priority should be given to creating a shared, standardised repository of information on evaluations of interventions’. Component C will seek to contribute to this evidence base by: refining methods of measuring resilience; evaluating the costs and benefits of a range of interventions; conducting research and answering a number of strategic evaluation questions. / The economic appraisal (paragraph 136) and other studies show that the evidence base for benefit to cost ratios is lacking in this area. One systematic literature review finding only 11 studies that appraise the costs and benefits of preventative disaster management measures - see Annex A (DFID 2005 and Mechler 2005). There is also evidence of the benefits that can result from greater links with the research community – for example the Regreening of the Sahel initiative (Box 4) involved farmer and community groups, local and national government, NGO and the World Agroforestry Centre in both developing and implementing agroforestry technologies. There is a large body of evidence from for example agricultural research (particularly through the CGIAR centres and research programmes) that would be relevant for the Sahel and other countries facing chronic food insecurity and climate extremes, where the linkages with practice will be strengthened by BRACED. / This component will deliver not only evaluation outputs to meet this need for knowledge and evidence, but also support the on-going monitoring of the portfolio and knowledge and lesson learning exchange. In order to inform the design of phase 2 a synthesis review of the evidence available from monitoring of projects will be undertaken, to provide intermediary information on for example fund structure, process efficiency, initial indications of impact on resilience and approaches to vulnerability analyses. The objectives and outputs of this component are set out below, grouped under themes of i) dissemination, ii) research and iii) accountability. / The objectives of Component C are: / Dissemination: / To facilitate peer to peer lesson learning and knowledge sharing for impact across communities (horizontal) / To build linkages with research organisations to enable design of well-informed solutions / Research / To provide evidence on what interventions work in which contexts to deliver climate resilience, to support decisions for future investments by institutions (vertical) / To answer strategic evaluation questions on best approaches to resilience building to inform institutional approaches (vertical) / Accountability / To ensure delivery of results of BRACED at portfolio level and provide operational support to ensure monitoring at project level is of a high standard. / Outputs: / Dissemination / Delivery of a knowledge platform for live learning, knowledge management and network building (including with research organisations), peer to peer and south-south learning [3 months startup - 3 years duration] / Synthesis, dissemination and communication of results – including a summary review of results, lesson learning and process to inform phase 2 [3 months – 3 years] / Research / Evaluability assessment of project proposals, selection of projects for embedded evaluations and define and refine strategic evaluations, conduct project and strategic evaluations – approx. 6 embedded project evaluations and up to 5 strategic evaluations [6 months – 7 years duration] / Define research priorities and conduct lesson learning pieces. [6 months to design – 7 years duration] / Accountability / Develop and implement common indicator methodologies, establish baselines by 6 months from project start date and generate data to monitor these [3 months startup - 3 years duration] / Technical assistance to project grantees on monitoring and evaluation for project preparation grant phase and full bids phase [Immediate - 3 years] / Audience (in priority order reflecting resource constraints): / Project grantees in short term – to support monitoring and evaluation / Other implementers in longer term for project design, including DFID design of phase 2. DFID internal learning including Future Fit / Influence community of practice for approaches to DRR and climate resilience in longer term – e.g. GFDRR, UNISDR, AGIR, Political Champions on Resilience, national and local governments, research institutions, negotiation processes including on loss and damage. Contribute to systematic evidence base on costs and benefits of different interventions. Component D on policy and institutional approaches will be a key audience. / The climate change adaptation and the disaster resilience M and E communities – including DFID for the ICF, the IIED Tracking Adaptation and Monitoring Development process and the OECD for approaches to measuring and monitoring climate resilience. / The Indicative timeframe for the development of this component is given below. / Phase 1 (start to 3 months): Knowledge platform arrangements designed, priority strategic evaluation questions designed (see evaluation section), research priorities designed, design of portfolio logframe indicators. / Phase 2 (3 – 6 months) technical assistance to grantees for project preparation - design of project evaluations and monitoring arrangements, launch of knowledge platform / Phase 3 (6 months – 3 years - programme lifespan) assistance and quality assurance of project logframes, finalisation of portfolio logframe, conduct evaluability assessment to select projects for embedded evaluations and to finalise strategic evaluations, begin strategic and project evaluations, on-going quality assurance, operation of knowledge platform activities, synthesis, dissemination and communication of results, input to design of phase 2. / Phase 4 (3 years – 7 years – ex post) complete evaluations, synthesise, disseminate and communicate results. / Component D: Development of national and international capability and capacity extremes / This component will provide support to build the capability and capacity of national and regional organisations to prepare and plan for the expected increases in the frequency and severity of climate extremes. The results of this will be to help build the resilience of communities and reduce the impact of climate extremes on people’s lives and property at three levels: / National and local level: integration of climate risk management and adaptation in national strategies and national plans, investment programmes and post-disaster recovery efforts. Improved evacuation planning, better regulations (e.g. codes for disaster-proof buildings) and planning on the provision of critical infrastructure (e.g. flood shelters and defence systems). Building national risk financing and insurance programmes, and, early warning systems and capacity of national met offices on weather and climate information. / It will also work to link community and NGO action in DRR and climate adaptation, and to learn the lessons on how to scale up actions and the policies and institutions needed for this. / Regional/sub regional level: building regional capacity to integrate climate risk analysis in planning and investments, to help regional institutions (e.g. AGIR see paragraph 92) to provide better weather and climate forecasting and early warning, and promoting trans-boundary water/ecosystems management and adaptation. This could include a Regional Centre of Excellence for Climate change and DRR as called for by the UNFCCC in Durban[95]. / International level: building the capacity of international agencies (e.g. UNISDR, IFIs) to integrate DRR and adaptation into their operations so that they support national and regional partners to address climate resilience in national strategies and policies. This will include policy and analytical work, sharing of knowledge, and, establishment of a community of practice on DRR and adaptation. / What types of activities will be supported? / As already discussed there will be a wide range of interventions that BRACED will support to build resilience to both slow onset disasters (e.g. droughts) and sudden onset events like cyclones and floods. Table 4 gives an illustration of this with a mapping of the activities of a range of NGOS working in the Sahel. They cover community based adaptation and planning, technologies and improved land management, water harvesting and water storage, flood protection and early warning schemes, access to weather/climate information. They will also include activities that particularly target and empower women, and wider aspects of empowerment and accountability. / Reliable and affordable energy is also important to help people be productive and meet basic needs, such as cooking (and cooling and heating), and access telecommunications (important for resilience) and jobs. BRACED will support interventions on energy that will help build the resilience of people and their communities to climate extremes and climate change more broadly. This could include use of clean energy improvements to agricultural practices – for example solar water pumping for irrigation, more efficient biomass-residue fired agricultural processing (e.g. drying and curing), and renewable cooling using solar panels for milk and fish refrigeration. Providing reliable and clean energy supplies to key disaster risk management installations is important. This would include early warning and communication systems (including mobile phone-based systems), including health centres will be important actions. This links to objectives of the Sustainable Energy for All initiative (SE4ALL) for example in providing power to 400,000 health posts. It also offers opportunities to integrating planning for disasters with wider district climate and energy planning. / Table 4: Mapping of current NGO interventions in the Sahel[96] / Name / Themes Countries Description / CAFOD and Caritas Niger / Nutrition; Water Resource management Niger CAFOD and Caritas Niger work on the promotion of sustainable Water Resource Management (including small scale irrigation systems) for improved and diversified food production. A 3-year £350,000 pilot project funded by CAFOD and implemented by CADEV-Niger has started in January 2013 in Zinder, promoting the sustainable management of 60 water wells and agricultural inputs for the production and marketing of vegetables. / Christian Aid / Livelihoods for agro-pastoralists; diversification of livelihoods; adaptation to climate; access to markets; governance and empowerment Mali; Burkina Faso Programmes support 214,500 people, of whom more than 45% are women, to improve their resilience. Their aim is to support profitable, resilient and inclusive livelihoods and target agro-pastoralists (sedentary and migratory) and vulnerable groups living in rural areas, and focus on: • Supporting communities to meet their own food security needs, through increasing productivity of existing livelihoods, diversification of livelihood options, and adaptation to climate issues. • Promoting access to markets and economic resources and improving agricultural business opportunities, through private sector alliances and value chains • Strengthening the capacities of the poorest to influence decision-making affecting local livelihoods at local and national level. / Concern Worldwide / Integrated resilience programmes including cash transfers; nutrition; health; water; DRR; livelihoods; early warning systems (EWS) Niger, Chad Concern has developed a £1.1m 4-year Integrated Resilience Programme currently being piloted in 12 villages in Bambeye. By the end of 2013 this intervention will be scaled up to include 30 villages, and the following year to 50 villages. The programme aims to facilitate improvements in the lives of the extreme poor in Tahoua as a result of increased resilience through improved access to quality services, enhanced livelihood systems and environmental protection. Special focus is given to vulnerable groups, including poor and very poor households and women. In Chad Concern designed a £1.5m medium term intervention (running from 2012 to 2016) that brings together activities related to water, nutrition, disaster risk reduction (DRR), livelihoods and inequality to improve the overall health, nutrition and livelihood security of the rural population of Sila (Eastern Chad) while improving their resilience to shocks. Taking this integrated approach means that they will be able to deliver a range of projects which address multiple needs through coordination across a variety of sectors to achieve common goals. The programme will also incorporate a comprehensive community based Early Warning System (EWS) to identify the early onset of potential shocks, and enable them to deliver an early emergency response package that can be rapidly scaled up, bringing together humanitarian and development programmes in an integrated manner. / Islamic Relief / Water management; agricultural support; community health; environmental sustainability; sustainable crop cultivation Chad; Mali; Niger In southern Mali Islamic Relief is implementing an integrated €1.2 million three-year project (14,000 direct beneficiaries and 31,000 indirect) in which a combination of new water installations/facilities (microdams, solar-powered drip irrigation and large-diameter wells) and agricultural support (seeds, tools and training) is enabling women and young people to improve food security, nutrition and income generation through rice and vegetable cultivation. Access to water has been identified by the communities themselves as the biggest problem they face. With access to water for longer periods through microdams they can improve agricultural productivity (benefiting both food security and income generation), community health and environmental sustainability (women are reducing their reliance on charcoal production as an income generating activity). / A project in southern Mali (€650,000 over three years) is promoting and developing sustainable livelihoods by enabling companion cultivation of trees and food crops specially selected for their drought resistance and/or nutritional properties and/or income generating potential. Sorghum, beans, peanuts, vegetables, sheanut, cashew, sesame and moringa are among the crops and trees being grown. / Merlin / Early child development Chad Merlin started operating in Chad in 2012 and programmes are small and concentrated in Hadjer Lamis, north of N‘Djamena. As part of its effort to strengthen communities’ resilience to seasonal malnutrition peaks, Merlin Chad has been implementing Early Child Development activities in health and stabilisation centres over the last year. / Oxfam / Research and evidence gathering on drivers of resilience and gender and resilience; Niger; Burkina Faso; Mali Oxfam is currently reorienting its work in Sahelian countries to better tackle the need to build resilience in chronically vulnerable areas. This means re-focusing its expertise and interventions (emergency, long term and advocacy) to help people to secure a sustainable access to food and build sustainable livelihoods that would make them less vulnerable to shocks, stresses and a changing environment. Oxfam has piloted a study in Niger on perception of drivers of resilience by communities. It found that diversification of sources of income (including non agricultural ones), access to local market places, and access to a network of relatives in towns or as migrants play a critical role in providing “endogenous safety nets”. Longer term trends such as the degradation of the environment and increased frequency of shocks and growing prices are recognized as critical but other changes are considered to provide opportunities / security: mobility, communication, education, access to basic services and local governance structures etc. Simultaneously research on Gender and Resilience (currently taking place in Niger, Burkina Faso and Mali) is providing an in depth analysis of how the current “permanent crisis” that people feel they are facing has led to major changes in the respective role of men and women. / Plan UK / Strengthening education and health ministries; nutrition; cereal banks; community savings groups; child-centred DRR Burkina Faso; Niger; Mali; Senegal; Cameroon Plan’s approach is to strengthen sectoral ministries (particularly education and health) to better prepare for and respond to disasters (including drought, floods and epidemics) and support community capacity building to ensure local skills and resources can be built to address recurring risks and root causes of vulnerability. For example, Plan is working with the Ministries of Education (MoE) in Niger, Mali and Burkina Faso to equip schools and train teachers and MoE staff on how to address the particular needs of displaced children. In Cameroon, Niger and Burkina Faso Plan’s emergency nutrition interventions includes technical support and capacity building for Ministry of Health at provincial and district level, aligned with support for community based mechanisms. In Niger, since the 2005 locust crisis, Plan has been supporting communities to set up and manage cereal banks and trained community management committees in the use of more resilient agricultural practices. Plan is scaling up community-based microfinance programmes, using community saving groups as an entry point to strengthen local resilience to recurring shocks and stresses. / Plan’s Child Centred Disaster Risk reduction approach empowers children to better understand the social, economic and environmental risks facing their communities and to contribute to promote greater awareness and action towards the protection and restoration of ecosystems at the community level. / Save the Children / Cash transfers; livelihoods (including community seed banks, diversification, livestock distribution); health; nutrition; leads multi-agency HEA initiative across the Sahel building EWS Niger; Burkina Faso Development and emergency cash-transfers in Niger, Burkina Faso and Northern Nigeria have had a demonstrated impact on livelihoods and malnutrition levels amongst children in target areas. Livelihoods work, developing community seed banks, off-season gardening, and livestock distribution, amongst others, have helped to provide households with the capacity and agency to effectively manage change in drought-prone regions. Health and nutrition interventions for children under-five coupled with sensitisation and behaviour change work have provided a foundation that improves their ability to confront stresses and shocks throughout their lives One programme that is actively building resilience through a system-strengthening approach and increasingly robust evidence base is the regional HEA initiative. The multi-agency HEA Sahel project is led by SC and covers seven countries. It has made significant progress since 2010 in strengthening regional early warning systems, specifically by integrating analysis of household food access and poverty. The next phase, currently under development, will build on these foundations to improve decision-making for timely, appropriate, well-targeted emergency response, while also expanding the evidence base for longer-term resilience policies. / Tearfund / Asset restoration; livelihood diversification and protection; local risk governance; contingency planning; research; includes strong pastoralist element Mali; Burkina Faso; Niger; Chad • Asset restoration. Income generating activities, market gardening, and support for increased food production help people to rebuild their depleted assets. In areas where the economy is centred on livestock, animal loan programmes accompanied by vaccinations, training on livestock management and animal fodder banks will improve communities’ purchasing power in times of food crises. Improving potable water access and sanitation improves nutrition outcomes and reduces the stress of water-borne disease. • Livelihood diversification and protection. Crop diversification, market gardening, and new income generating activities enable agricultural communities to broaden their livelihood base. Community cereal banks and micro-finance institutions reduce households' exposure to market volatility. Protection and regeneration of agricultural and pasture land reverses the impact of desertification and environmental degradation. • Improved local risk governance. Tearfund partners support pastoralists in claiming their land rights and sustainably managing migration routes and the pastures around "fixation sites." Partners also help communities create new risk management institutions such as disaster management committees, and advocate to the government on key resilience issues. Tearfund increases local resilience by building up the emergency response capacity of local civil society. • Experimentation and learning. Farmer field schools where farmers try out different techniques and traditional knowledge and analyse them together, are helping farmers to learn and innovate. • Information. Tearfund is working to develop local knowledge, understanding and integration of climate change and environmental sustainability. • Contingency planning. Community disaster risk reduction work will help them arrive at a plan incorporating known shocks and stresses through assessing local vulnerabilities and building upon community assets. / World Vision / Farmer Manager Natural Regeneration (sustainable land restoration) Niger; Mali; Senegal World Vision has a long history in promoting FMNR (Farmer Manager Natural Regeneration) a sustainable land restoration technique (through the regeneration of tree roots), in Niger, Mali and Senegal. The approach has produced dramatic results, including increased crop harvests and in many areas a significant shortening of the annual hunger gap. In addition to this, the increased income of many rural producers (up to 300% increase) through the sale of wood, seeds and edible leaves is significant. Research has shown that areas in Niger with high levels of FMNR adoption coped far better (lower rates of malnutrition and did not require emergency assistance) during periods of food crises due to their ability to stockpile grain and improved fertility and water holding capacity of soils.
[23] 2012 IPCC “Special Report on Managing the Risks of Extreme Events (SREX) and Disasters to Advance Climate Change Adaptation
[24] In this case including earthquakes as well as floods, droughts and storms, though earthquakes remain the most stable through time of the 4 phenomena
[25] Natural Hazards, UnNatural Disasters, The Economics of Effective Prevention, (summary booklet) 2010, World Bank
[26] Defined as non-OECD countries. Source: EMDAT EM-DAT: The OFDA/CRED International Disaster Database
[27] Munich re
[28] IPCC SREX Extreme Events Report (2011) Summary for Policymakers page 6
[29] See UN-ISDR (2009) and Peduzzi et al (2011).
[30] Source: EMDAT: The OFDA/CRED International Disaster Database
[31] Foresight: Reducing Risks of Future Disasters (2012). Final Project Report. The Government for Science, London
[32] Foresight: Migration and Global Environmental Change (2011). Final Project Report. The Government Office for Science, London
[33] Loayza et al (2009)
[34] Hochrainer, (2006)
[35] Human Development Report (2007/8)
[36] Alderman et al (2006)
[37] Miguel et al (2004)
[38] daSilva, J.A. and Cernat, L, 2012 coping with loss: the impact of natural disasters on developing counties trade flows, quoted in Foresight 2012 reducing Risks of Future Disasters.
[39] International Rice research Institute (2008) quoted in Foresight 2012 Reducing Risks of Future Disasters.
[40] Rayco-Solon, P. et al. (2002) Differential effects of seasonality on preterm birth and intrauterine growth restriction in rural Africans. Am J Clin Nutr., 81(1) 134-139.
[41] Maleta,K. et al. (2003) Seasonality of growth and the relationship between weight and height gain in children under three years of age in rural Malawi. Acta Paediatr 92: 491-497.
[42] Fuentes, R. and Seck, P. 2007. The Short-Term and Long-Term Human Development Effects of Climate-Related Shocks: some Empirical Evidence. New York, UNDP
[43] Del Ninno,C., Dorosh,P.A. and Smith,L.C. (2003) ‘Public policy, markets and household coping strategies in Bangladesh: Avoiding a food security crisis following the 1998 floods’. World Development 31(7): 1221–1238.
[44] Silventoinen, K. 2003. Determinants of variation in adult body height. Journal of Biosocial Sciences, 35:263–285.
[45] UN Standing Committee on Nutrition (2010) Climate Change and Nutrition Security: Message to the UNFCCC negotiators.
[46] One example is the Ethiopian Productive Safety Net Programme which now incorporates a risk financing mechanism to provide additional support during bad years.
[47] Gubbels,P. (2011) Escaping the hunger cycle: pathways to resilience in the Sahel. Sahel Working Group / Groundswell International.
[48] Neumayer, Eric, and Thomas Plümper (2007). The gendered nature of natural disasters: the impact of catastrophic events on the gender gap in life expectancy, 1981–2002. Annals of the Association of American Geographers 97(3): 551–66.
[49] World Bank (2011b). Making Women’s Voices Count: Integrating Gender Issues in Disaster Risk Management. Operational Guidance Notes. Washington, DC: The World Bank, East Asia and Pacific Region.
[50] World Bank. 2011. Gender and Climate Change: Three Things You Should Know.
[51] Agarwal, Bina (2010). Gender and Green Governance: The Political Economy of Women’s Presence Within and Beyond Community Forestry. Oxford: Oxford University Press.
[52] D. Layne Coppock, Solomon Desta, Seyoum Tezera, Getachew Gebru 2011. Capacity Building Helps Pastoral Women Transform Impoverished Communities in Ethiopia. Science. DOI: 10.1126/science.1211232
[53] Two metrics (are used) for communicating the degree of certainty in key findings, based on author teams’ valuations of underlying scientific understanding: 1) Confidence in the validity of a finding, based on the type, amount, quality, and consistency of evidence and the degree of agreement, expressed qualitatively 2) Quantified measures of uncertainty in a finding expressed probabilistically (based on statistical analysis of observations or model results, or expert judgment).
[54] Source for all figures: IPCC SREX Extreme Events Report (2011) Summary for Policymakers
[55] Coumou, D. and Rahmstorf, S. 2012. A decade of weather extremes. Nature Climate change. doi:10.1038/nclimate1452
[56] DFID Sahel Resilience Strategy 2012-15 (DRAFT) September 2012
[57] To add
[58] Consolidated figures from the various CAPs and the UN Sahel Regional Strategy. Source of national population total (2010): UN Population Division, population estimates and projections section Source of 2013 numbers at risk: CAP ‘at risk’ figures for BF, Chad, Mali, Mauritania and Niger and Sahel Regional Strategy 2013 ‘at risk’ figures for Cameroon, Gambia, Nigeria and Senegal
[59] IOM Survey quoted in IDMC: 20/02/13: Mali: A Cautious Return: Malian IDPs Prepare to Go Home.
[60] World Bank and Asian Development Bank. 2010. Pakistan Floods 2010 Preliminary Damage and Needs Assessment.
[61] Kirsch et al.2012. Impact of the 2010 Pakistan Floods on rural and urban populations at six months. PLos Currents published online.
[62] Internal DFID report on countries at risk
[63] Internal DFID report on countries at risk
[64] Foresight: Reducing Risks of Future Disasters (2012). Final Project Report. The Government for Science, London
[65] Berkes (2007); (Obrist) et al. 2010
[66] DFID. 2012. The Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia.
[67] For example geophysical hazards such as earthquakes and tsunamis and human induced hazards such as those relating to conflict are not emerging threats in the same way as climate change as there isn’t certainty about the fact they will increase. Climate change will also increase the difficulty of addressing climate and weather events such as floods and droughts, by increasing the severity, frequency and unpredictability of these events. Unlike other hazards the past is not a guide to the future for hazards resulting from climate extremes.
[68] Ward level climate resilience assessments will be available on the website of the National Drought Management Authority of the Government of Kenya very soon.
[69] IPCC SREX Report; Summary for Policy makers(2011) p15
[70] Botoni, E. and C.Reij (2009). Silent transformation of environment and production systems in the Sahel: impacts of public and private investments in natural resource management. CILSS and VU University Amsterdam. Reij, C., G. Tappan and A. Belemviré (2005) Changing land management practices and vegetation in the Central Plateau of Burkina Faso (1968 – 2002). Journal of Arid Environments 63 (3): 642 - 659 Reij, C., G. Tappan and M. Smale (2009). Agricultural transformation in the Sahel: another kind of “Green Revolution”. IFPRI Discussion Paper no. 00914. (www.ifpri.org/millionsfed).
[71] Reij, C., G. Tappan and M. Smale (2009). Agricultural transformation in the Sahel: another kind of “Green Revolution”. IFPRI Discussion Paper no. 00914. (www.ifpri.org/millionsfed).
[72] Yamba and Sambo, 2012. To be published
[73] Frankhauser and Soare (2012). Strategic Adaptation to Climate Change in Europe
[74] Adaptation Topic Guide. 2013. DFID
[75] DFID (2010) Promoting Economic Growth When the Economy is Changing VIVID Economics, DFID
[76] Frankhauser and Soare (2012) Strategic Adaptation to Climate Change in Europe pp 24-27 2012 IPCC “Special Report on Managing the Risks of Extreme Events (SREX) and Disasters to Advance Climate Change Adaptation” pp. 349
[77] Froot, K.A., 2001: The market for catastrophe risk: A clinical examination. Journal ofFinancial Economics, 60, 529-571.; SREX page 372
[78] Humanitarian Emergency Response Review; DFID website; March 2011
[79] Full list: Helen Clark (UNDP) Andrew Mitchell (UK), Valerie Amos (OCHA), Gunilla Carlsson (Sweden), Rowan Douglas (Willis Re), Kristalina Georgieva (EU), Rachel Kyte (World Bank), Joao Ribeiro (Mozambique), Dr. Raj Shah (US) aYuji Yamamoto (Japan) Reem Al Hashemi (United Arab Emirates), Irwin LaRoque (CARICOM) and Dr. Hasan Mahmud (Bangladesh)
[80] Synthesis report: Analysis of financing mechanisms and funding streams to enhance emergency preparedness, Jan Kellet and Hannah Sweeney, Development Initiatives, October 2011. Commissioned by FAO on behalf of the IASC.
[81] Turnbull, M., Sterrett, C., Hilleboe, A., 2013. Toward Resilience: A guide to disaster risk reduction and climate change adaptation http://reliefweb.int/report/world/toward-resilience-guide-disaster-risk-reduction-and-climate-change-adaptation
[82] Oxfam GB (2013). The Africa Climate Change Resilience Alliance http://policy-practice.oxfam.org.uk/our-work/climate-change-drr/accra
[83] REGLAP (2013) Regional Learning and Advocacy Programme (REGLAP) for Vulnerable Dryland Communities. http://www.disasterriskreduction.net/east-central-africa/reglap/
[84] # UN OCHA, 2013. Sahel: Millions need long-term support. 29 May 2013 http://www.unocha.org/niger/top-stories/sahel-millions-need-long-term-support
[85] Rapid review and stakeholder consultation on the potential of NGOs to build resilience to climate extremes and disasters in the Sahel. 2013. Evidence in Demand Paper, PEAKS, DFID
[86] This figure is based on BRACED commissioning 20 NGO projects with an average grant of £5million that will benefit 500,000 people.
[87] The 5 million figure (see Box 5) is based on an estimate of the number of beneficiaries from on scaling up DRR activities at grassroots level (though civil society organisations), as only this component will be designed to directly make large numbers of people climate resilient in the lifetime of the programme. This is based on an estimate of 0.25 million people to each grant of £5million. This is a rough estimate and will need to be revised as BRACED is implemented.
[88] By large scale we are meaning interventions that affect over 40,000 households.
[89] Rapid review and stakeholder consultation on the potential of NGOs to build resilience to climate extremes and disasters in the Sahel. 2013. Evidence in Demand Paper, PEAKS, DFID
[90] Due to limited data availability, total estimated numbers of beneficiaries cannot currently be attributed to total funding requirements
[91] This includes some advocacy beneficiaries
[92] This is a cautious estimate based on the NGO mapping evidence. The study (Rapid review and stakeholder consultation on the potential of NGOs to build resilience to climate extremes and disasters in the Sahel. 2013. Evidence in Demand Paper, PEAKS, DFID) identified a indicative pipeline of 116 NGO activities. These ranged in scope, duration and geographic focus. The average grant funding requirement was approximately £4.5 million. The average estimated number of direct beneficiaries was 222,500. These averages should be treated with some caution but are the best available estimate of expected results.
[93] See the paper by James Pattison et al “Local to national: putting local voices and priorities at the heart of national policy making.” Presented at the “Hunger, Nutrition, Climate Justice” Dublin Castle, April 2013. Available at: http://eu2013.ie/media/eupresidency/content/documents/HNCJ-conference-papers_final_small.pdf
[94] Foresight: Reducing Risks of Future Disasters (2012). Final Project Report. The Government for Science, London
[95] Piloting Regional Centre of Excellence for Climate change and DRR were called for by the UNFCCC in Durban
[96] Summary of Resilience Activities in the Sahel. 2013. Sahel Working Group.

# III. APPRAISAL CASE

A. Approach and Evidence / In line with the “3 E’s Framework” as set out in DFID’s Approach to Value for Money,[97] this appraisal considers three questions and associated sets of options. / Whether to invest in DRR and adaption to build resilience to climate extremes? / This considers effectiveness - what outputs can we design that will achieve our outcomes. This section looks at the cost effectiveness of community based adaptation and DRR activities to achieve improved resilience of communities to climate extremes. It considers whether the benefits of investing in these outputs are likely to outweigh the costs. Under this two options are considered: / Do not fund any more DRR and adaptation actions. / Fund investments in 10 countries at most risk from climate extremes. / What is the best delivery option to provide support to DRR and adaptation? / This considers efficiency - how we can design inputs to best achieve those outputs. This section looks at a number of delivery options that could feasibly deliver community based adaption and DRR. Three delivery options are considered: / Multilateral organisations to implement activities on DRR and climate change adaptation. / Direct provision of DRR and adaptation activities by DFID country offices. / Direct support to civil society organisations their partners and to scale up their existing activities on DRR and climate change adaptation. / What is the best management option for the preferred delivery option? / This considers economy – how to purchase inputs at the best quality and price. In this section we consider the best way to manage the delivery agent. Under this four management options are considered: / NGO consortium. / Third party management agent. / International agency. / DFID direct management. / Figure 2 sets out the structure of the BRACED programme and the three stages of decision making that will be required to assess VFM using the 3 E’s framework. Figure 3 is a flow chart which describes how the appraisal case will be structured in this Business Case. / In appraising the finance, delivery and management options the quality of evidence for each option has been rated as Strong, Medium or Limited in Table 5. / Figure 3: Flowchart of appraisal process for BRACED / Table 5: Summary of options considered and assessment of evidence for appraisal / Option Evidence rating / Effectiveness analysis – whether to invest / Fund DRR and adaptation Medium / Do not fund Strong / Efficiency analysis - delivery options for components A. B and C / Finance multilateral organisations to implement activities on DRR and adaptation Medium / Direct provision of DRR and adaptation by DFID country offices (not applicable for Sahel component) Strong / Direct support to NGOs and partners on DRR and adaptation Medium / Economy analysis - management options for grants to NGO led consortia / NGO consortia Weak / Third party management agent Medium / Multilateral agency Medium / Direct management by DFID Medium / Component A / Activities that build resilience in the Sahel / Component B / Activities that build resilience in DFID focal countries / Component C / Activities that build evidence of what works / Delivery body / Delivery body / Delivery body / Administration of funds / Strategic oversight / Management structure / Outputs / Delivery agent / Appraisal of investing in DRR and adaptation / - Challenges and uncertainties / - Cost and benefits analysis of support to DRR and adaptation. / - Climate and environment assessment / - social and gender assessment / - Conclusion / Appraisal of Different Delivery Options / - Wider options considered and discounted / - Description of feasible options / - Advantages, risks and disadvantages of options / - Multi-criteria analysis / - Climate and environmental assessment / - Social, Gender, Political and Governance assessment / - Summary of appraisal / - Conclusion on preferred option / Appraisal of management option / - Description of management options / - Procurement and costs / - Value for money / - Fiduciary risks and management / - Management and implementation / - Reporting and Evaluation / - Conclusion
[97] DFID’s Approach to Value for Money (VFM) Department for International Development, July 2011

B: The case for investing in DRR and adaptation / There are two options / Table 6: Investment Options / Option Short description / 1 Significant increase in funding on DRR and adaptation / 2 No extra funding to DRR and adaptation by DFID / Economic appraisal / The Strategic Case made the economic case for government intervention to deal with the impacts of increased extreme weather and climate events on communities in developing countries. There are a number of different interventions that can be used to tackle the market and governance failures set out in the Strategic Case. / To deliver public goods to communities, governments can provide goods and services such as small-scale buffer infrastructure, local early warning systems, community awareness raising and evacuation planning, crop diversification, and micro-insurance. To help poor and vulnerable groups in society build their resilience to deal with shocks governments can provide goods and services – or they can deliver social protection programmes such as cash transfers; asset transfers; employment guarantees; or social pensions. Governments can also seek to influence the broader patterns of economic development that can build resilience of the economy as a whole to extreme events. / Where programmes work in a defined context, the usual approach to the economic appraisal is to present and compare the additional costs and additional benefits of the proposed set of activities, and subject these to sensitivity analyses. However, the BRACED programme proposes to support a range of projects in multiple contexts, many of which have not yet been designed and actual costs and benefits are uncertain. Therefore a comprehensive cost and benefit analysis (CBA) is neither possible nor proportional, and has not been undertaken. / Instead the approach used to consider the costs and benefits of BRACED has been to identify the costs and benefits of community based adaptation and DRR from the literature and to provide CBA from comparable projects. This section makes the case for the effectiveness of the programme – the extent to which BRACED outputs will active the planned outcomes. It will also consider the costs and benefits of the counterfactual scenario – no further DFID support to community based adaptation and DRR. / Option 1: Fund community based adaptation and DRR / There is a substantial and growing body of evidence to suggest that the benefits of climate change adaptation and DRR exceed the costs. At a global level, Parry et al estimate that the mean cost of adaptation measures is $6 trillion. Even though adaptation does not remove all – or even most – of the impacts of climate change, it is clearly worthwhile, with a mean benefit of over $300 trillion, at a mean benefit to cost ratio of about 60 to 1 (Parry et al, 2009). / It is more difficult to assess cost benefit ratios at a micro level. As Hallegatte et al (2013) has shown, net-present-value calculations (discounted total benefits minus discounted total costs) break down in the presence of uncertainty about which climate projections will play out in practice[98]. Small changes in the ‘without programme’ climate scenario have a big impact on the expected benefits of the programme being appraised. / It is also difficult to quantify the benefits of adaptation and DRR activities. The impacts of climate change can play out over very long time periods, meaning that programme benefits need to be evaluated a long time into the future. What is more, ‘resilience’ is context specific and can mean different things to different communities - is therefore often difficult to place a monetary value on the benefits of interventions that aim to build resilience to climate extremes. / This programme will work at the micro level in a range of countries and contexts to scale up responses to climate change that are specific to the risks identified in those communities, and will through components C and D work to strengthen the policy and institutional frameworks to sustain and replicate these interventions. This will be complemented by support to governments to develop macro strategies that build systematic resilience to shocks. As the specific grassroots interventions that this programme will implement are yet to be identified, this section reviews evidence from similar interventions in order to assess the extent to which they offer a positive rate of return. / BRACED is also expected in its implementation to provide more details on the costs and benefits of DRR and adaptation interventions. This will include information on unit costs. This is important as the evidence in developing the assessment of VFM of DRR and adaptation interventions. / Evidence review / Despite the huge number of community-based adaptation programmes under implementation by governments, donors and NGOs; until recently the number of rigorous, experimental, and peer reviewed cost-benefit analyses for those projects was relatively small. Where evidence of benefit to cost ratios does exist, it is largely drawn from ex-post evaluation of projects. / Two studies (DFID 2005 and Mechler 2005) reviewed the evidence base for benefit to cost ratios for community based adaptation and DRR in 2005. The DFID study concluded that, “research into the costs of natural disasters and the costs and benefits of DRR measures is not well developed, and much of the evidence is anecdotal. However, a number of bottom-up, or micro-economic assessments, of DRR measures have also been undertaken. These typically examine a proposed package of DRR measures for a specific area. Such studies have identified a wide range of DRR measures with positive benefit-cost ratios. The benefit-cost ratios are obviously heavily dependent upon local circumstances (for example construction cost, efficacy of DRR measure, value of assets and numbers of persons affected), but the studies demonstrate the potential for economically effective DRR measures in developing countries. This evidence strongly suggests that there can be positive economic returns from DRR measures, and that additional development benefits can be realised”. / Mechler (2005) reviews the literature on the efficiency and net benefits of preventive disaster management measures in reducing and avoiding disaster impacts. The author finds that large returns to preventive measures have been found in studies appraising the potential benefits before implementation, or evaluating the actual benefits ex-post (a summary of the 11 studies reviewed is provided in the Annex A). Benefits to cost ratios were £2 for every £1 invested or higher. In a subsequent paper, Linnerooth-Bayer and Mechler (2008)[99] updated this analysis and found that in many contexts every Euro invested in risk prevention returns roughly 2 to 4 Euros in terms of avoided or reduced disaster impacts on life, property, economy and environment. / A literature review commissioned as part of this appraisal has identified a number of more recent studies - some of them from programmes operating to scale - that have provided stronger evidence of value for money with benefits greatly exceeding costs. These are summarised below, and an evidence rating is provided for each study. / A DFID-funded project in Malawi supporting crop diversification, soil and water conservation, and provision of drought-resistant livestock, has yielded positive benefit cost ratios (calculated at a discount rate of 10%) between 24.30 and 37.32 depending on the underlying assumptions[100] (Medium; small scale study but independent and controlled); / The Chars Livelihoods Programme in Bangladesh has used community public works, to raise more than 100,000 homesteads on the riverine chars above the 1998 record flood levels. In addition it provides women (55,000 by 2010) with productive assets to reduce income poverty and strengthen further their resilience. A DFID study concluded that the plinths had a benefit to cost ratio of 4.3 to 1 and the assets 7.9 to 1[101]. (Medium evidence). An independent, controlled, longitudinal study in four chars villages[102] confirmed that the improvements made in the livelihoods of flood prone households continued over time. It identified additional qualitative benefits for women from the programme, including greater social inclusion, confidence and empowerment. (Strong evidence, independent and controlled); / The DFID-funded Protracted Relief Programme in Zimbabwe has shown that small scale projects (for example conservation farming; seeds, fertilisers and small stock distribution; crop diversification) aimed at increasing food security have led to benefits outweighing costs by between 1.6 and 17.2 times[103] depending on the intervention. The package of interventions resulted in an Internal Rate of Return[104] of 44% (calculated using a discount rate of 12%). (Strong evidence; large scale and programme designed taking account of drought risk); / The Risk to Resilience Study Team (2009) reviewed drought- and flood- risk reduction strategies in India, Nepal and Pakistan. The review shows that individual measures have positive BCRs (between 1 and 8.55) and in some cases well above those achieved through other common development investments (Strong evidence); / Venton and Venton (2004)[105] looked at two community-based projects in Bihar[106] and Andhra[107] in India, the former vulnerable to floods and the latter to both floods and droughts. The economic analysis shows benefit-cost ratios (BCR) (at 10% discount rate) of 3.76[108] and 13.38[109] respectively (Medium evidence; small-scale study). / Box 7 reviews the evidence on the specific types of activity likely to be funded by the BRACED programme – these are early warning systems; community based risk reduction; social protection programmes; insurance; natural resource management; and infrastructure. / The evidence allows us to conclude that the benefits of adopting a disaster risk reduction approach to build climate resilience exceed the costs in the vast majority of cases. / Option 2: No further DFID support to community based adaptation and DRR / The costs of not investing in community based adaptation and DRR are potentially very large. The World Bank Economics of Adaptation to Climate Change study estimates that the global costs of adapting to a 2-degree world between 2010 and 2050 to be in the region of $70 billion to $100 billion per year[110]. / Box 8: VFM review of activities similar to those in the BRACED programme / There is strong evidence of the benefits of weather services and early warning systems for natural disasters. The benefits exceed the costs of weather services by a factor of ten or more[111]. Early warning systems for natural disasters such as floods and cyclones are classical “no regrets” options. They provide good value for money and positive benefit/cost ratios analyses, typically in excess of four and often higher in the case of floods and cyclones.[112]'[113]. (Strong evidence from several studies). / Community-based risk reduction[114]. There is good evidence that this can be effective on a small-scale in reducing the risks from extreme climate events[115],[116] but there only limited evidence on value for money in terms of benefits and costs. One of two recent studies demonstrated benefit/cost ratios of 3.49[117] and the other of between 1.13 and 2.04[118]. Both examples are from Nepal and involved programmes covering fewer than 1000 households with unit costs per person ranging £65 to £150 and per household from £300 to in excess of £1,000. These figures reflect significantly different contexts, approaches and household sizes. (Medium evidence; more evidence needed “at scale”); / Social Protection, including cash transfers; asset transfers; employment guarantee; social pensions, (but excluding insurance). There is little evidence of the benefits and costs of social protection schemes designed specifically for disaster risk reduction and building climate resilience. One of the few examples comes from the Chars Livelihoods Programme in Bangladesh, where the transfer of productive asset transfers to flood-prone households yielded a benefit to cost ratio of 7.9[119]. Davies, Oswald and Mitchell[120] explore the concept of adaptive social protection and conclude that there is a need to further develop an evidence base on how effectively to combine social protection measures to mitigate vulnerability to climate change in different contexts. / Insurance against losses from natural disasters[121]. Linnerbooth-Bayer and Mechler (2009) cited examples of positive benefit to cost ratios for insurance against natural disasters. Many, but not all, were from developed countries. However, they highlighted that the record of insurance for providing security against floods, earthquakes and other hazards is more tenuous than other forms of insurance, in part because of the potential scale of the losses. Early experience with index-based crop and livestock insurance suggests that it can be a cost-effective alternative to indemnity-based agricultural insurance. They concluded that pilot (insurance) programmes should be carefully monitored and built upon. / Natural Resource Management. An impact assessment of a large scale mangrove replanting programme in Viet Nam covering 8,961 hectares and with 350,000 direct beneficiaries, plus up to 2 million indirect beneficiaries, in five provinces yielded benefit to cost ratios of between 3.06 and 68.92; though there was a wide variation between each province[122]. / A small watershed project in Rajasthan assessed by Sahu (2008)[123] showed a benefit to cost ratio of 2.14 (based on a discount rate of 5%), remaining well above 1 when using a higher discount rate of 7%[124]. / Infrastructure. The provision of infrastructure carries some of the heaviest costs in disaster risk reduction. In Bangladesh, raising homesteads on plinths above flood levels cost £78 per plinth at 2007 prices[125]. Construction was labour intensive, providing income for the community, but large scale, with 100,000 households being raised. It is likely that investments in infrastructure will produce large benefits in the event of climate extremes, but it is important to note that (per person), these investments can be relatively expensive up front. / The costs to HMG and to society that will result from climate extremes if there is no further intervention are threefold. First is the cost of wider investments failing due to extreme climate risk (opportunity costs). The second is the long-term impacts of a changed climate (higher temperatures, changes in total precipitation and rainfall patterns), which are likely to reduce crop yields[126] for farmers unless adaptation measures are implemented, or disruption of other livelihood generating activities. These costs can worsen food security and increase hunger and malnutrition[127]. The third is the actual cost of humanitarian response to extreme climate events when adaptation actions have not been undertaken to support the most vulnerable. / On the third of these costs, there is strong evidence to suggest that investment in building the resilience of communities to cope with risk in disaster prone regions is more cost-effective than humanitarian response after the fact. The evidence from a recent DFID paper[128] analysing the economics of early response measures in Kenya and Ethiopia clearly points to three conclusions: / Early response is far more cost effective than late humanitarian response. In southern Ethiopia, with a beneficiary population of 2.8m, household level data suggest that early response could save between $662m and $1.3billion in a single event. A perceived risk in responding early is that humanitarian funds will be released incorrectly to situations that turn out not to be a disaster. However, these figures suggest that donors could mistakenly release funds two times in Kenya, and seven times in Ethiopia, before the cost is even equivalent to the cost of humanitarian aid in one event. / Given uncertainty, the estimates presented in the paper suggest that while the cost of building resilience is comparatively high, the wider benefits of building resilience can significantly outweigh the costs, leading to the conclusion that investment in resilience is the best value for money. The cost of resilience would have to approach $200 per capita per year for 10 years (almost 50% higher than the figure assumed in this paper) before the modelled costs of resilience begin to approach the cost of humanitarian response. / The paper concludes that early response and resilience building measures should be the overwhelming priority response to disasters. The findings in this study fully support an economic imperative for a shift to greater early response and resilience building. / Whilst this study only uses a sample of two countries and should not be seen as globally representative, the experience from Kenya and Ethiopia suggests that early action can be very good value for money. Overall, the evidence presented is supportive of community-based adaptation and DRR activities that will encourage resilience building and early responses for disaster risk reduction. / The case for investment in BRACED Component C / The BRACED theory of change hypothesises that the programme will be achieve a transformational impact on resilience of poor people in vulnerable communities by learning lessons from what approaches work in what context; and using this evidence to influence policy making and development planning. BRACED Component C will generate, synthesise and communicate evidence on which interventions under components A and B work well (and less well). Box 9 looks at whether the benefits of programme component C are likely to outweigh its costs. / Box 9: Benefits and Costs of BRACED knowledge and evidence component / BRACED Component C will generate knowledge and evidence on what works well (and less well) in resilience building activities. It will generate evidence through experimental techniques, analyse and synthesise data from across the programme, and disseminate and communicate this knowledge to a range of audiences. / Expected benefits from Component C / Appraisal section B considered the case for investment into community based adaptation and DRR. Whilst a strong case is made, the evidence is fairly anecdotal - no systematic database of benefit-cost ratios exists, making it difficult to compare VFM across different types of investment. Activities under this component will generate a stronger and more robust evidence base around investments in resilience building. This evidence will improve the effectiveness of current and future climate finance programming by the UK and others. With better evidence of what works and how, future programmes will be more evidence-based and therefore expected to have greater impact and to represent greater value for money. / By generating robust evidence on the cost effectiveness of different types of intervention, the component has the potential to inform the design of the international climate finance architecture – notably the design of the Green Climate Fund. It will help inform the design of programmes and policies of our partners, including other donors, international financial institutions, and partner governments. The gains from more effective programming in the future could potentially be large as there will be reduced wastage that occurs as a result of ineffective programming. / Robust and timely assessment of results, impact, and value for money of the BRACED programme will inform the improved design of Phase II of the programme. The evidence will inform decisions around which interventions under Phase I should be further scaled up or replicated. Interventions implemented under Phase II should therefore be more cost effective than those under Phase I. / Expected costs of Component C / The estimated cost of Component C is £10.7 million, or 7.7% of the total BRACED programme budget. This includes the following outputs: / Data generation: developing common indicator methodologies; reporting at portfolio level; technical assistance to grantees; and data collection. / Evaluation: development of evaluation questions and methodologies; technical assistance to grantees including on control group selection and baselines; implementation of experimental evaluations; implementation of strategic evaluations. / Synthesis, dissemination and communication: analysis, synthesis and packaging of monitoring and evaluation findings; communication of results to a range of audiences through knowledge platform; develop partnerships, networks and community of practice with others. / Discussion – costs versus benefits / It is difficult to monetise the expected benefits from this programme component. If investments in knowledge and evidence generation improve the cost effectiveness of future climate change finance – by the UK and by others – then the benefits are potentially very large relative to the costs. / To take a numerical example: the UK International Climate Fund assigns £2.9 billion to climate finance – with an aspiration to allocate half of this (£1.45 billion) to adaptation activities. An explicit objective of the ICF is to demonstrate what works well and less well in climate programming[129]. If just 1% of the ICF adaptation programming is allocated to programmes that display poor cost effectiveness, this would equate to £14.5 million of ‘ineffective’ programming’. If investments in activities identified under BRACED component C were to avert similar losses from future climate change programming then an investment of £10 million is easily justifiable. / Climate and Environment Appraisal / Table 7 summarises the climate change and environmental categories on whether to invest in DRR and climate change adaptation. The categories are defined as: Category A, high potential risk or high opportunity; B, medium or manageable or medium opportunity; C, low or no risk, or no opportunity; or D, core contribution to a multilateral organisation. / Table 7: Climate change and environmental categories / Option Climate change and environment / Risks and impacts / Category (A, B, C, D) Opportunities / Category (A, B, C, D) / Option 1 - Fund DRR and adaptation B A / Option 2 - Do not fund B C / As the main objective of BRACED as set out in the strategic case is to build resilience to climate extremes and reduce and prevent disasters occurring the decision to invest in DRR and adaptation will have significant opportunities and benefits (Category A). The logframe has explicit climate change and environment indicators. A decision not to invest would forgo those opportunities and benefits and in the face of a worsening environment represent a significant risk – this option would therefore be category B. / An important opportunity of BRACED is to bring together development and humanitarian interventions to address the environmental challenges of climate change, and to develop programmes and projects that meet both humanitarian, development and environment objectives by building resilience to climate extremes. More details on the opportunities BRACED presents and how to enhance these benefits is given in the Climate and Environment Assurance Note attached as Annex B. / There are risks that some of the proposed activities and investments under BRACED may lead to maladaptive outcomes. For example some grants may fund include rural infrastructure. There is a risk that the ‘climate-proofing’ of these components may exclusively focus on making them physically able to withstand climate effects. These investments could potentially, for example, provide “incentives” for the most vulnerable to remain in locations that would be unviable in 20-30 years’ time according to current projections. This was an important issue identified by the Foresight Report on Migration and Environmental Change.[130] For the Sahel specifically there is a risk that the resilience inherent in the ‘dis-equilibrium’ nature of the drylands environment is not recognised and externally imposed solutions such as intensive agriculture prove maladaptive. Conversely enhancing traditional livelihood strategies that are resilient to existing climate variability may not be sufficient alone in the face of future climate change, both scenarios would prove maladaptive. / The individual projects supported by BRACED will need to work at scale in a truly integrated way, with each other and with the policy and institutional context, to enable consideration of complexities and trade-offs in complex socio-ecological systems to ensure they achieve maximum impact. By working at individual community level there is a risk of displaced environmental risks from one community to another, for example an activity to improve irrigation and water use could have an impact on water users downstream by increasing the amount of water taken out of the river. It could also have negative impacts on the wider ecosystem. This risk is more acute if individual projects don’t work with the national and subnational policy and institutional contexts – ensuring government buy-in at all levels. To address this consideration and mitigation of wider systemic climate and environment risks to the whole region or ecosystem in question will be included as criteria for grant selection. NGOs and NGO alliances will need to demonstrate an understanding of the policy and institutional context and have plans for addressing this. Many of the project level impacts can be avoided or reduced where these are identified and actions taken. However, as the projects that BRACED will support are still to be determined there is no definitive list of risks that can be identified at the outset. It will therefore be important when awarding grants that all proposals are subjected to a climate and environment appraisal. / There will be a set of more generic risks, and opportunities, with BRACED on implementing the project and choice of activities. This would include limiting the travel associated with the project and ensuring that low carbon technologies are used, and that any interventions are energy efficient. There will also be an opportunity for BRACED to support climate compatible development approaches that deliver triple wins: adaptation, mitigation and development benefits. / The option to fund DRR and adaptation is appraised as category B while there are risks these can be mitigated or avoided. The option not to fund implies continued and increasing climate risks to those communities and so is category B for risks. The option to fund provides significant environment and climate change opportunities and is category A. The option not to fund does not provide opportunities and is category C. More details on the potential risks and negative environmental impacts are given in the Climate and Environment Assurance Note (Annex B). / Social and Gender Appraisal / BRACED recognises the strong links between poverty, gender and vulnerability to climatic disasters. By focusing on the Sahel BRACED will provide significant funding to countries that are at the bottom of the human development index (HDI) and which suffer from chronic food insecurity. Other countries covered by BRACED will be DFID focus countries including fragile states that are highly prone to disasters. / The focus of BRACED is building resilience to disasters. This will require a range of interventions to help people manage the risk of droughts, floods and cyclones. In parallel to these interventions there needs to be a renewed focus on addressing the fundamental causes of vulnerability. Of these, chronic poverty is the underlying driver of vulnerability across the Sahel and many other BRACED countries and is reinforced by huge gender disparities, insecurity and conflict, poor governance and lack of respect for human rights, inadequate health provision and lack of education, particularly for girls. / All of these need to be addressed through policies and programmes on wealth creation, empowering women and girls and greater investments in education and health, including reproductive health. These are all important for building resilience and while not the focus of BRACED, nonetheless BRACED-funded projects will need to show how they relate to these wider set of issues and interventions. Furthermore, at a political level establishing good governance and building peace and stability across the Sahel and other fragile environments will be critical for long term resilience to climate disasters. / One of the key issues for BRACED will be targeting within the selected countries. In order to do this effectively the selection criteria for potential BRACED-funded programmes will need to give high priority to social dimensions of vulnerability in addition to physical vulnerability. The following will be key requirements for selection: / Gender. This needs to include a gendered approach to vulnerability analysis. While there is a consensus that women are more vulnerable to disasters than men, there is a need to understand the particularly vulnerabilities facing women and men in each context. Furthermore, BRACED will consider funding programmes specifically targeting women and girls. This will be critical for the Sahel where gender inequalities are also some of the highest in the world; in the 2011 Gender Inequality Index Chad ranked 145 out of 146, Niger 144 and Mali 143. / Multi-dimensional analysis of vulnerability - In addition to gender there are other important social drivers of vulnerability including age and ethnicity which will require an understanding of the multi-dimensions of vulnerability. / Social exclusion and marginalisation - In many countries covered by BRACED, including large parts of the Sahel, social exclusion and marginalisation have been major drivers of both conflict and vulnerability. / Participatory methodologies - including participatory vulnerability analysis will be critical for both understanding vulnerability and designing effective interventions. BRACED funded projects will need to clearly demonstrate a strong track record and commitment to participatory approaches. / Empowerment and accountability - BRACED will expect NGO partners to be involved in policy influencing, political economy analysis and empowering communities and local civil society groups to hold governments and donors to account for their policies and programmes on adaptation and disaster risk reduction. / C. Appraisal of Delivery options / Economic Appraisal / Appraisal Section B shows that investments in community-based adaptation are very likely to have a positive rate of return. It also shows that costs to society and to HMG are likely to be higher in the without-programme scenario) than with the programme - because it is more expensive to respond and recover from extreme climate events than it is to build resilience ex ante. / This section looks at a number of ways in which the BRACED programme could deliver its activities. A range of options to support community based adaptation and DRR to build resilience to climate extremes were considered. These were assessed against the following critical success criteria: / Table 8: Critical Success Criteria / Criteria Description / Scope, vision and feasibility Delivery agent must have capacity to deliver community based adaptation in the programme focus countries. The organisation should have clarity of purpose and scale of support is such that the project can address the core barriers to enhanced resilience in a locality, which may well lie outside the target communities. Delivery agent must be able to absorb and disburse funds in a timely manner. / Operational effectiveness In line with the multilateral aid review, effective organisations will: challenge and support partners to think about value for money; consider rates of return and cost effectiveness issues in decision-making; achieve economy in purchase of programme inputs; control administrative costs; demonstrate good financial accountability and transparency; and display effective leadership and governance. / Ability to deliver and measure results at scale The delivery agent must have demonstrated ability to implement activities that build resilience of communities to extreme climate events at scale, and have strong capacity to monitor and evaluate those results. / Effectiveness at building local and national capacity The delivery agent must demonstrate ability to work in effective partnership with others and in particular with existing local government systems. Good organisations will build capacity of local partners to deliver community based adaptation in the future. / Potential for demonstration and wider policy influence The delivery agents should have strong capacity to measure and evaluate results as well as demonstrated ability to communicate and disseminate results. The delivery option should facilitate lesson learning and inform design of future climate change programming / In addition the social and environment appraisals consider the extent which the delivery options perform well in fragile contexts; target women and girls; and ensure that activities are low carbon, climate resilient environmentally sustainable. / The list of wider options considered but rejected include: / Provision of goods and services by national or local governments in priority countries funded through DFID budget support. This option is not feasible (at least in phase 1 of the programme), as DFID does not have geographical presence in the programme focus countries. DFID does not have existing working relationships with local governments in the programme countries and so the number of new ground staff needed to implement this option is unacceptably high. However this option could be considered under phase 2 of the programme following preparatory work in-country. / Delivery through a multilateral climate investment fund such as the Pilot Programme on Climate Resilience or Adaptation Fund. HMG already provides support to multilateral funds elsewhere under the International Climate Fund (to date, £431 million to the PPCR and £10 million to the Adaptation Fund). Working through multilaterals can complement the bilateral programmes that we implement through our country and regional offices. Multilateral programmes enable us to deliver large scale support for adaptation through institutions that are effective, and build progress in key areas that we are unable to bilaterally. A separate Business Case will consider whether the multilateral climate funds are able to absorb and disburse additional finance and the extent to which this offers good value for money. / Appraisal of the delivery options / The three remaining options to be appraised are: / Finance to adaptation multilateral organisations to implement activities on DRR and climate change adaptation either as part of their core activities or within separate facility or trust fund. Organisations with core business in this focus area include WFP, UNISDR, and the GFDRR. / Direct provision of DRR and adaptation activities to vulnerable communities in a selection of countries by DFID country offices. NB this option is not possible for the Sahel where DFID does not have country offices. / Direct support to civil society organisations their partners and to scale up their existing activities on DRR and climate change adaptation. / Option 1: Finance to adaptation multilateral organisations / How it would work / Under this option DFID would transfer funds to a multilateral organisation that would deliver community based adaptation and DRR activities as part of its core activities or under a new programme window. Multilateral organisations with core business in this subject are the United Nations World Food Programme[131] (WFP), the United Nations Office for Disaster Risk Reduction[132] (UNISDR) and the Global Fund for Disaster Risk Reduction[133] (GFDRR). The analysis of these three organisations draws heavily on the assessment made during the DFID Multilateral Aid Review 2011 as well as desk-based research using online resources (including the Australian Multilateral Aid Review). / The World Food Programme is the world’s largest humanitarian organisation with two-thirds of its resources channelled through humanitarian interventions. Delivering food assistance, it also advocates globally for attention to hunger. It is entirely voluntarily funded and its scale of operation is driven in large part by fluctuating humanitarian need and funding. In 2009 its expenditure was US$ 4.2 billion; in 2010 it was US$ 3.8 billion. WFP receives no core funding: its administrative budget derives from a 7 per cent surcharge on programme funding. The vast bulk of WFP’s income is earmarked by donors to specific operations/purposes – only eight per cent is undirected multilateral[134]. / The United Nation’s International Strategy for Disaster Reduction (UNISDR) is a strategic framework, adopted by United Nations Member States in 2000, aiming to guide and co-ordinate the efforts of a wide range of partners to achieve substantive reduction in disaster losses and build resilient nations and communities as an essential condition for sustainable development. UNISDR’s main role includes co-ordination amongst UNISDR system partners, policy guidance, and provision of strategic information on disaster risk – and so it does not at present directly implement activities on the ground. Worldwide UNISDR has approximately 90 members of staff (which includes 48 in regional offices) and an overall annual budget of approximately US$ 28 million. / The Global Fund for Disaster Risk Reduction (GFDRR) was established in 2006. It is a facility hosted by the World Bank and guided by a Consultative Group made up of donors, developing countries and international partners. The GFDRR Secretariat employs around 12 full-time staff at its Washington Headquarters, and relies on a network of World Bank and UNISDR staff to support its three ‘tracks’ of programming (global and regional level advocacy; technical and financial assistance to low and middle-income countries; and a disaster recovery fund). Its annual budget for 2010 was $131.5m. / Estimated costs and benefits of the approach / Table 9 sets out the costs of delivering the BRACED programme through a multilateral organisation. The analysis assumes that programme oversight would be managed by a core advisory team in DFID Policy Division, comprising an A1 Team Leader, A2 and A2L policy leads, and two grade B programme management staff. / The multilateral body would deliver overall programme management, implementation, and monitoring and evaluation functions. Information on the proportion of the UNISDR and WFP budget that is spent on administrative and management costs was not readily available from Annual Reports (though a breakdown of expenditures by programme activity was provided in both it was not possible to disaggregate programme and management costs). According to the UNISDR Annual Report 2012, 57% of the organisation’s expenditure is on staff costs. This is to be expected from a knowledge-based institution that delivers its outputs through its staff. / A World Bank evaluation of the GFDRR found that the administrative costs of the GFDRR Secretariat as a share of total expenditures administered by the Secretariat have declined steadily as the program has grown since 2006. At 11.3 percent in 2012, these are comparable to other technical assistance and investment programs that World Bank Independent Evaluation Group has reviewed[135]. / Through negotiation with multilateral organisations, we would aim to reduce this figure to 10% of programme budget to administration and management costs. / Table 9: Cost estimates – Option 1 Finance to Adaptation Multilateral Organisation / OPTION 1: MULTILATERALS / Policy Division staff costs Percentage of adviser time Year 1 Year 2 Year 3 Year 4 / A1 Team Leader (London) 10% 8,950 8,950 8,950 8,950 / A2 Adviser (London) (lead adviser) 25% 18,447 18,447 18,447 18,447 / A2L Adviser (London) 25% 15,036 15,036 15,036 15,036 / BID Programme manager (East Kilbride) 20% 9,065 9,065 9,065 9,065 / B2 Administrative Support (East Kilbride) 10% 3,764 3,764 3,764 3,764 / Adviser travel* 4,000 4,000 4,000 4,000 / Total DFID staff costs 59,262 59,262 59,262 59,262 / Total 4 years £237,050 / * Assumes one adviser makes 2 international trips per year at £2000 per trip / ** FTE estimates based on DFID Unit Costs data / Table 10 assesses the potential benefits of this delivery option against the critical success criteria. / Table 10: Benefits estimates - Option 1 Finance to Adaptation Multilateral Organisation / Scope, vision and feasibility Partnership with all three of these organisations is feasible and DFID has past experience working with each organisation to draw upon. All three organisations have the ability to link community activities with national government, which will help the programme to go ‘beyond’ the community level. / World Food Programme has offices in all BRACED priority countries and significant experience in implementation of community resilience programming. Although some WFP activities are in middle-income countries, in general the organisation has a strong focus on low income and fragile/conflict affected countries. Two thirds of WFP expenditure in 2009 was directed to those countries identified as having the greatest humanitarian need. / Though UNISDR fulfils a unique role in the coordination of global risk reduction activities, it has not demonstrated experience at implementation of projects on the ground. Though UNISDR have been expanding its work at the national level, the MAR identified this had deflected resources away from its core mandate in international co-ordination. / GFDRR is already working with 31 countries and so has good geographical reach in the BRACED priority countries. However, to date the organisation has not demonstrated ability to implement programmes on the ground as this is beyond its core mandate. / Overall score = 2 / Operational effectiveness World Food Programme scored weakly on organisational strengths in the MAR. Though the organisation has made progress at improved results frameworks and design of evaluations; the MAR noted that evaluations could go further to address VFM and whilst basic structures are in place, achieving a results based culture across the organisation is still work in progress. However, its financial accountability systems and processes are strong and the organisation is making ongoing improvements to these. / UNISDR scored poorly across the MAR organisational strengths criteria. It was criticised for having no clear line of sight between its mandate, strategy and implementation plan. The organisation is weak in driving forward improvements in performance based on evaluation findings, and it has no results framework in place. It also scored poorly on financial accountability: its cost plans and actual expenditures have not been fully linked to strategic objectives, outcomes and deliverables. Its internal accounting system also does not reflect expenditures against deliverables. / GFDRR displayed satisfactory performance across the organisational strengths criteria in the MAR. It has a clear mandate, purpose and strategy to deliver on the Hyogo Framework for Action priorities. It has a good, responsive and transparent Secretariat structure in Washington which is influenced by the consultative group. Its results based frameworks are still under development and there are some doubts as to the effectiveness of in-country programmes. It has a good financial management system with mostly robust accountability processes and policies and some ability to redirect funds. It is constrained by some of the WB systems which prevent pooled funding or innovative approaches. / Overall score = 2 / Ability to deliver and measure results at scale World Food Programme scored ‘satisfactory’ in the MAR contribution to results category. WFP delivers results at scale in humanitarian and fragile contexts. The most unambiguous results are where food assistance and logistical support is life-saving. School feeding programmes demonstrate results but often with sustainability and VFM caveats. / UNISDR received an ‘unsatisfactory’ score on the MAR contribution to results criteria. Its reporting has focussed mainly at the activity level and has not been linked to impacts or outcomes. This has made it difficult to understand how it has contributed to any real DRR outcomes / The core mandate of GFDRR is to mainstream disaster risk management and climate change adaptation strategies across the MDGs through Poverty Reduction Strategy Papers (PRSPs) and national development strategies. The organisation is yet to demonstrate whether it is able to implement community adaptation and DRR activities at scale. / Overall score = 1 / Effectiveness at building local and national capacity Through its country programmes World Food Programme has longstanding relationships with government and so has strong potential to build local capacity. / UNISDR has not demonstrated ability to build local and national capacity to date (though this is not currently within the remit of the organisation) / GFDRR is a unique model incorporating developing country governments, donors and international partners with an excellent partnership with UNISDR and other UN partners. It works in 31 priority countries alongside national Disaster Risk Management Departments and so there is strong potential for effective national capacity building through this organisation. / Overall score = 3 / Potential for demonstration and wider policy influence World Food Programme scored ‘satisfactory’ in the MAR at building partnership behaviour. It is generally well regarded for its humanitarian cluster leadership and has developed effective relationships with other UN agencies such as the FAO and IFAD / UNISDR is a system of partnerships with governments, inter-governmental and nongovernmental organisations, international financial institutions, scientific and technical bodies and specialised networks as well as civil society and the private sector. There is therefore good scope for this organisation to communicate and disseminate knowledge and evidence from the BRACED programme to its partners. / Through its network of donors, international organisations and governments, GFDRR is in a strong position to communicate and disseminate the results from community based adaption and DRR projects. / Overall score = 4 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / This option scored poorly against feasibility, organisational effectiveness, and ability to deliver results at scale; however, it has good potential to work with partner governments and to influence wider policy-making. / An overall score for the three institutions has been given against each criterion in table 10. This hides differences between the three institutions. Notably, the World Food Programme performs better against the criteria than the other two organisations. A more detailed consideration of the pros and cons of delivering BRACED through WFP is provided in Box 10. / On balance we do not believe that it is feasible to deliver BRACED through WFP because the programme scope is beyond the mandate of the organisation. / Broader advantages and risks of the approach / A broader advantage of the multilateral option (not captured in Table 10) is the potential to leverage in additional finance from other donors. If the BRACED programme were to set up a new window or trust fund within an existing multilateral organisation, other donors and international organisations could be invited to contribute finance to the fund. / A strong disadvantage of this option is the limited scope to build capacity and knowledge in DFID. Outsourcing the delivery of BRACED entirely to a third party could mean that the potential for lesson learning on effective management, implementation and delivery of community based adaptation and DRR activities is not maximised. / Box 10: WFP as a potential partner for BRACED delivery / Pros / Potential to offer for good VFM / WFP was assessed as offering good value for money for UK aid in the 2011 Multilateral Aid Review. Preliminary results from the 2013 update of that review suggest good progress against the 2011 score. The MAR highlighted several strengths of WFP, which include proven ability to deliver emergency food assistance at scale, often in difficult environments; strong financial management systems; and strong corporate emphasis on cost effectiveness. / Strong of expertise in emergency preparedness and livelihood rebuilding in difficult and fragile environments / The MAR assessment found that WFP is the only international agency capable of delivering emergency food assistance at scale in difficult and often dangerous environments. Two thirds of its work is in fragile countries. WFP identifies its own competences as: emergency preparedness; food security analysis; nutrition; and procurement[1]. / Cons / Institutional focus on ex-post intervention rather than ex-ante resilience building / In its Strategic Plan 2008 – 2913[2], the World Food Programme sets out five strategic objectives. These are: / Save lives and protect livelihoods in emergencies / Prevent acute hunger and invest in disaster preparedness and mitigation measures / Restore and rebuild lives and livelihoods in post-conflict, post-disaster or transition situations / Reduce chronic hunger and under nutrition / Strengthen the capacities of countries to reduce hunger, including through handover strategies and local purchase / Institutional focus is predominantly around saving lives after disasters happen, rebuilding livelihoods after disasters, and helping countries to build their own capacity to respond to disasters. The BRACED programme aims to build resilience of communities before disasters occur. Delivery through WFP would therefore require the organisation to shift in focus from an ex-post to an ex-ante approach. / Limited scope to learn from different institutional approaches and project type / As set out in the strategic case, BRACED will aim to build evidence and test approaches on adaptation and DRR to build the resilience of people to cope with climate extreme events both at the community and macroeconomic level. It will aim to develop new and innovative mechanisms and ways of working and to evaluate the extent to which different interventions are successful. By restricting programme delivery to just one agency (WFP) there is a risk that interventions would be homogenous in nature and learning from different types of approach would be limited. / Option 2: Direct provision of activities by DFID country offices / How it would work / This would require individual DFID Country Offices to design programmes of support to communities based around a risk assessment of climate impacts in country. Because DFID does not have Country Offices in all of the priority countries identified in the Strategic Case (for instance in the Sahel) this option would require DFID to deploy staff in new locations, based for example in an FCO office. In DFID Country Offices where we do have presence, this option would require new staff resource to design and manage the programmes, where these are additional to any existing programmes. / There are no FCO or DFID offices in Mali, Mauritania, Burkina Faso or Chad; but an FCO office is in place in Senegal. DFID offices are based in Sierra Leone (also working with Liberia), Ghana, Nigeria, Sudan and South Sudan. Programme staff could potentially be based in one of these regional offices and implement activities from a distance. / Estimated costs and benefits of the approach / Table 11 estimates the costs of delivering BRACED directly through DFID offices. The analysis assumes that overall coordination and oversight would be managed by a core team in Policy Division. The Policy Division team would also directly manage the knowledge and evidence sharing programme component through support to results collection, design of strategic evaluations, synthesis of findings, communication and dissemination. Policy Division advisers would be required to travel to the programme countries for annual review and results collection activities. / Design and implementation of programme activities would be managed by five Country Office teams (each comprising an A2 and B1D adviser) plus three new implementation teams developing activities in the Sahel; based in neighbouring Country Offices. Country Office staff would require budget for internal and regional travel in order to design, implement and monitor the programme activities. / The estimated costs set out in Table 11 (approximately £15 million over four years, or 13% of total programme) are highly conservative. They do not include the costs of setting up new regional offices, or the administrative costs of running those offices. There will also be programme design costs as DFID advisers will need to assess climate risks in the contexts that they are working and design appropriate interventions from scratch. / Table 11: Cost estimates – Option 2 Direct provision of activities by DFID country offices / OPTION 2: DELIVERY IN HOUSE / Policy Division staff costs / Percentage of time Year 1 Year 2 Year 3 Year 4 / A1 Team Leader (London) 10% 8,950 8,950 8,950 8,950 / A2 Adviser (London) (lead adviser) 25% 18,447 18,447 18,447 18,447 / A2L Adviser (London) 25% 15,036 15,036 15,036 15,036 / BID Programme manager (East Kilbride) 20% 9,065 9,065 9,065 9,065 / B2 Administrative Support (East Kilbride) 10% 3,764 3,764 3,764 3,764 / Travel costs* 12,000 12,000 12,000 12,000 / Country Office units (x5) / A2 Adviser x 5 100% 375,723.95 375,724 375,724 375,724 / B1D programme manager x 5 100% 301,630 301,631 301,631 301,631 / Internal travel expenses 5 countries** 20,000 20,000 20,000 20,000 / New implementation units in Sahel (x3) / A2 Adviser x 3 100% 2,769,304.89 2,769,305 2,769,305 2,769,305 / B1D programme managers x 3 100% 180,978.54 180,979 180,979 180,979 / Regional and internal travel expenses*** 48,000 48,000 48,000 48,000 / Total DFID staff costs 3,762,901 3,762,901 3,762,901 3,762,901 / Total 4 years 15,051,603 / ** FTE estimates based on DFID Unit Costs data; overseas posts are assumed to cost £15,000 per annum more than UK posts (this is a conservative estimate based on DFID overseas allowances data and does not include accommodation costs) / * 2 advisers make 3 international visits per year at £2000 per visit / ** assumes that in each country 2 advisers make 1 visit per quarter at £500 each / *** assumes that in each country 2 advisers make 1 visit per quarter at £2000 per trip / Table 12 assesses the potential benefits of this delivery option against the critical success criteria. / Table 12: Benefits estimates - Option 2 Direct provision of activities by DFID country offices / Scope, vision and feasibility This delivery option is not feasible unless significantly more design work takes place to establish country and regional offices capable of delivering the programme. Limited HMG presence in the Sahel region will make implementation on the ground very challenging. There is a strong risk that there will be financial slippage as it will take some time to set up implementation units and to design interventions from scratch. / Overall score =1 / Operational effectiveness There is good potential for this option to be operationally effective as the programme will use existing DFID internal systems and approach to VFM. / Overall score = 2 / Ability to deliver and measure results at scale DFID Country Offices have a range of high quality experience in the design and implementation of adaptation, DRR and social protection programmes. However, BRACED priority countries that do not already have a DFID Country Office may struggle to deliver results on the ground. Designing programmes from scratch is likely to be time consuming and require significant staff resources during design and implementation. / Overall score = 1 / Effectiveness at building local and national capacity This option has the potential to score well against this criterion if activities are actively designed with a view to build capacity of local and national governments. In countries where HMG does not have an existing country presence (such as the Sahel) it may be challenging to establish new relationships and build trust with partner governments (both local and national). / Overall score = 2 / Potential for demonstration and wider policy influence This delivery option has the potential to score well against this criterion if programme activities designed by DFID staff are explicitly designed to demonstrate what works well and less well. The central coordination team could design an M&E framework to collect results and evidence and to draw lessons across the different programme countries. The risk with this option is that the core team do not successfully synthesise, disseminate and communicate the results and evidence effectively and/or do not have access to the right audiences. / Overall score = 3 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Broader advantages and risks of the approach / This delivery option scored poorly against all of the critical success criteria on. In addition, this option limits potential to leverage in finance from other donors. / One advantage of in-house delivery not captured in the analysis is the potential to build internal knowledge and capacity. There is strong potential for DFID staff to gain knowledge and experience in effective management, implementation and delivery of the programme activities. There would also be scope to produce original research outputs that draw on the evidence of what works well and less well across the range of programme contexts. / Option 3: Direct support to civil society organisations their partners and to scale up their existing activities on DRR and climate change adaptation / How it would work / This option would provide grants to NGOs and their partners (local government, UN agencies and private sector) to scale up proven technologies and practices at grassroots level. Selected by a set of investment criteria, NGOs and their partners would be required to demonstrate ability to achieve results on the ground, to build local and national capacity, and to build evidence on what works well and less well on adaptation and DRR. In order that the BRACED programme is transformational – i.e. the whole of the programme is more than the sum of a collection of NGO programmes – NGOs would be required to demonstrate how their activities build resilience beyond just the target communities. There would need to be a strong independent research and evidence programme component to draw lessons across the suite of interventions and to influence local and national policy decision making. / An evidence paper prepared for this Business Case[136] shows that there is evidence of demand from NGOs to scale up community based adaptation and DRR activities. Consultations with a sample of international NGOs (including Action Aid, CAFOD, CARE International UK, Christian Aid, Concern Worldwide, Oxfam GB, Plan International, Practical Action, Save the Children, Tearfund, Water Aid and World Vision) and DFID regional advisors demonstrated evidence of a strong demand for support in the NGO resilience community for the scale-up of resilience-building initiatives in the Sahel and other DFID priority countries. NGO focal points provided details of current and planned resilience-building initiatives in Burkina Faso, Chad, Mali, Mauritania and Niger as well as Ethiopia, South Sudan, Sudan, Somalia, Kenya, Uganda, Tanzania, Mozambique, Nigeria, Malawi, Zimbabwe, Nepal, Burma, Pakistan, and Bangladesh. Financial, policy and institutional challenges of existing programmes were communicated and potential activities that could potentially be scaled-up through the BRACED programme shared. / The evidence paper identified a financial gap of more than £378 million for resilience-building projects and programmes in the focal countries. Some of the above-mentioned partners have funding gaps in programmes or projects that are designed and ready for implementation. Moreover, some NGOs are implementing successful programmes in just one of the programme countries and could scale-up or strengthen activities in other countries, including across the Sahel. At the same time, there are also NGOs that are implementing relevant programmes elsewhere in Africa with learning strong enough to justify replication in countries in the Sahel. Many NGOs lack in-country presence but have a strong network of local partner organisations. Additional funding would likely lead to strengthened capacity among civil society organisations in the more isolated countries and a potential increased involvement of countries in regional programmes. / Estimated costs and benefits of the approach / The costs of delivery through NGOs would be similar to those for delivery through a multilateral organisation. / Programme oversight would be managed by a core advisory team in DFID Policy Division, comprising an A1 Team Leader, A2 and A2L policy leads, and two grade B programme management staff. Overall management, implementation, monitoring and evaluation of programme activities would be delivered by NGOs. The knowledge and evidence component of the programme would be delivered either through a dedicated A2 adviser based in Policy Division, or it could be outsourced to an external supplier (such as a policy research institute, consultancy company or think tank). / All NGOs are required to publish their Annual Report (including financial data) on their external websites. It is however quite difficult to determine what proportion of expenditure should be categorised as administrative and what is programme (staff costs for example are usually not disaggregated). Some NGOs do provide a breakdown of expenditure category: / Oxfam report that 9% of budget is spent on administrative support and running costs[137] (not inclusive of 7% fundraising costs) / Practical Action report that only 1% of their budget is spent on administrative costs[138], though this does not include 10% of budget expended on ‘consultancy and publishing’ and 12% on ‘fundraising’ / Save the Children International[139] report that 8% of all expenditures are for administration (not inclusive of 12% fundraising costs) / We assume that through negotiation with multilateral NGOs this delivery option would allocate up to 10% of programme budget to administration and management costs. / Table 13: Cost estimates – Option 3 Finance to NGOs and Partners / OPTION 3: NGOs / Policy Division staff costs Percentage of adviser time Year 1 Year 2 Year 3 Year 4 / A1 Team Leader (London) 10% 8,950 8,950 8,950 8,950 / A2 Adviser (London) (lead adviser) 25% 18,447 18,447 18,447 18,447 / A2L Adviser (London) 25% 15,036 15,036 15,036 15,036 / BID Programme manager (East Kilbride) 20% 9,065 9,065 9,065 9,065 / B2 Administrative Support (East Kilbride) 10% 3,764 3,764 3,764 3,764 / Adviser travel* 4,000 4,000 4,000 4,000 / Total DFID staff costs 59,262 59,262 59,262 59,262 / Total 4 years £237,050 / * Assumes one adviser makes 2 international trips per year at £2000 per trip / ** FTE estimates based on DFID Unit Costs data / Table 14 assesses the potential benefits of this delivery option against the critical success criteria. / Table 14: Benefits estimates - Option 3 direct support to civil society organisations / Scope, vision and feasibility A background paper on potential NGO partners was prepared as evidence to support this appraisal. The paper found strong demand from NGO organisations in the BRACED focus countries, including those in the Sahel, to scale up existing programmes and to implement new programmes. Interviews with NGO representative indicated that organisations would have the capacity to absorb and disburse grants. / There is a risk that civil society organisations will have a narrow focus on needs at community level and fail to have a vision for the bigger picture of resilience building across geographies. This risk could be mitigated if through the grant proposal process if preference is given to bids that consider macro patterns of resilience building alongside community driven adaptation. / Overall score = 4 / Operational effectiveness This option would deliver the BRACED activities in a range of contexts through a multiple civil society organisations and NGOs. / The DFID Civil Society Portfolio Review 2013[140] carried out a consultation with staff in DFID country offices to assess why they had chosen to work with civil society organisations (as opposed to other delivery agents). Advisers reported that: CSOs were close to communities and their able to reach vulnerable and marginalised groups; and due to this proximity there is also quick delivery of services, programmes and information. Advisers also chose CSOs as a way to promote and strengthen accountability and responsiveness of governments to their people. They reported that CSOs can act as watchdog, monitoring government policies and budgets in countries where information or the capacity to analyse information may be lacking. / The operational effectiveness of different delivery agents is likely to be highly varied. It is therefore difficult to make an overall assessment of effectiveness against this criterion. However, strict investment criteria could be put in place to ensure that only high performing organisations were able to access BRACED grants. / Overall score = 3 / Ability to deliver and measure results at scale The background paper to this appraisal found that there are a large number of NGOs and civil society organisations working in the BRACED priority countries with demonstrated ability to deliver results at scale (see Annex C for a detailed summary). A number of organisations (for example Oxfam, Practical Action and Tearfund) are already implementing community based adaptation and DRR activities in the priority countries and so there is scope to scale up or replicate activities in new communities. / The DFID Civil Society Portfolio Review 2013 looked at how well civil society organisations deliver results. Summarising the evidence on NGOs and service delivery, Ibrahim and Hulme (2011)[141] note that NGO service delivery is often unsustainable due to dependence on external funding, the difficulties of going to scale and their inability to recover costs through user charges. However, when certain conditions are met, NGO provision can be extremely effective in both the short and long term. These conditions include having an integrated approach, and being complementary to state provision of services. / The bid proposal process will need to be designed in such a way that only NGOs with demonstrated ability to deliver at scale and with a strong commitment to VFM receive grants from the programme. NGOs will also be required to have strong M&E systems in place before receiving grant funding. / Overall score = 4 / Effectiveness at building local and national capacity Under this option the BRACED activities would be delivered by civil society organisations that have established networks in communities and regions in the priority countries identified. These organisations have strong potential to work with local governments to build capacity of local implementing partners. / The BRACED programme could actively encourage bids from NGOs that aim to build local (and national) capacity for community based adaptation and DRR. / Overall score = 4 / Potential for demonstration and wider policy influence Whilst international NGOs have a good track record in supporting community level interventions, they often have less leverage on wider institutional change, or influence on policies in partner countries. The BRACED programme will need to develop a strong evidence and knowledge component in order to draw lessons across a wide range of NGO programmes. / Overall score = 3 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Broader advantages and risks of the approach / This delivery option scored well against the critical success criteria, but performance of individual NGOs and their partners may be varied. Good performance will be heavily dependent on effective design of the proposal selection criteria – which should strongly reflect critical success criteria examined here. / As set out in the DFID Civil Society Portfolio Review, a strong advantage of delivery through civil society organisations is their ability to deliver services in fragile and conflict affected environments such as the Sahel countries. DFID is on target to spend 30% of official Overseas Development Assistance - approximately £3.4 billion - in fragile states by 2015. A recent IDC inquiry found that DFID was right to increase aid to fragile and conflict-affected states, such as Rwanda and Democratic Republic of Congo (DRC), but it must be prepared to suspend or even cancel a programme if a government flouts agreements or refuses to engage in efforts to increase transparency and accountability[142]. Working with civil society is a way of diversifying the delivery of aid on the ground, reducing the risk of having to stop aid completely, as is the case currently in Rwanda. / NGOs will have a range of results reporting and evaluation systems in place and the risk in this delivery option is that reporting will be varied in quality. A meta-evaluation produced by DFID 2011 noted weaknesses in planning, measurement and monitoring of results, and evaluation[143]. The 2010 civil society Portfolio Review also highlighted that it was clear through consultation with NGO partners that they felt they had fallen short on a focus on measuring outcomes and struggled to articulate their value added. However, since the publication of the 2010 Portfolio Review there has been a step change in what is expected from partners in terms of conceptualising and planning. Many organisations now undertake beneficiary monitoring; for example CAFOD and Action Aid have participatory approaches at the core of their M&E processes and routinely gather feedback from beneficiaries. To mitigate this risk there will need to be a strong focus during programme design on harmonisation and quality of results monitoring and evaluation. / Summary comparison of delivery options and recommendation / Table 15 sets out a multi-criteria analysis for the BRACED delivery options based on the analysis provided above. Each option has been allocated a cost “score” from 1 to 3, with 1 being the lowest cost option and 3 being the most expensive option. Since options 1 and 3 are expected to have similar costs, they both score 2. Each option has been allocated a benefits score, which are weighted according to the relative importance of the criteria. / Table 15: Multi-criteria analysis – BRACED delivery options / Criteria Weight (sums to 1) Option 1 Option 2 Option 3 / Cost score 2 3 2 / Benefits Score (1-4) weighted score Score (1-4) weighted score Score (1-4) weighted score / Scope and feasibility 0.3 1 0.3 1 0.3 4 1.2 / Operational effectiveness 0.2 2 0.4 2 0.4 3 0.6 / Ability to deliver and measure results at scale 0.3 1 0.3 1 0.3 4 1.2 / Effectiveness at building local and national capacity 0.1 3 0.3 2 0.2 4 0.4 / Potential for demonstration and wider policy influence 0.1 4 0.4 3 0.3 3 0.3 / Total Benefit Score 1.7 1.5 3.7 / Benefit/Cost Ratio 0.85 0.5 1.9 / * Benefit scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / ** Cost scores: The options are ranked from 1 to 3, with 1 being the lowest cost option as 3 being the most expensive option, / *** The benefit cost ratio has no cardinal significance but should be considered relative to the other options. Higher benefit cost ratios are associated with good performance. / Option 3 (direct support to civil society organisations to scale up their existing activities on DRR and climate change adaptation) is the best performing option. Though it scored the same as option 1 on cost it scored very well against all of the benefits criteria relative to the other options. The benefit-cost ratios presented should not be treated with any cardinal significance here (they do not describe the return from £1 of investment) but they can be used to compare success across options. Option 3 has the highest benefit to cost ratio and so is the recommended option. / Delivery options for BRACED Component C / BRACED Component C will generate, synthesise and communicate evidence on which interventions under components A and B work well (and less well). Box 9 considered whether the benefits of programme component C are likely to outweigh its costs and concluded that the benefits of those activities are likely to be large relative to the costs. Box 11 considers delivery options for this component of the programme. / Box 11: Delivery options for BRACED knowledge and evidence component / BRACED Component C will generate knowledge and evidence on what works well (and less well) in resilience building activities. Activities will include: / Data generation: developing common indicator methodologies; reporting at portfolio level; technical assistance to grantees; and data collection. / Evaluation: development of evaluation questions and methodologies; technical assistance to grantees including on control group selection and baselines; implementation of experimental evaluations; implementation of strategic evaluations. / Synthesis, dissemination and communication: analysis, synthesis and packaging of monitoring and evaluation findings; communication of results to a range of audiences through knowledge platform; develop partnerships, networks and community of practice with others. / Delivery agent Discussion / Option 1: DFID in house There is insufficient advisory capacity in DFID Climate and Environment Department to carry out this function. A project team with new staff with the requisite expertise would need to be recruited. New advisors would need to include climate change and humanitarian experts, monitoring and evaluation experts, economists, statisticians, and IT and communications experts. The project team would require programme resource to carry out the activities identified, including funds for international travel to carry-out field work. / A key benefit of this approach is that it will build up capacity of DFID staff in this field of expertise. However, there will be large start-up costs associated with this option (including recruitment costs). It does not have the potential to build on existing centres of expertise or professional networks already in place at other organisations / Option 2: Multilateral organisation (e.g. WFP, GFDRR or UNISDR) Under this option a multilateral organisation such as WFP, GFDRR or UNISDR would be invited to manage the knowledge and evidence component of BRACED. There is strong potential here – the multilateral organisations scored “strong” against the ‘potential for demonstration and wider policy influence’ criterion in table 13 above. Multilateral organisations could draw on their existing networks of partners and use existing online platforms. / However it is not clear that these organisations have the technical expertise required to deliver the programme activities identified or the extent to which these activities lie within their organisational remit. Whilst there may be strong potential in knowledge dissemination and communication, it is less obvious that the organisations will have the necessary expertise in climate change and humanitarian M&E, statistics, data collection, and econometric analysis. / Option 3: Externally contracted knowledge manager (competitive tender) Under this option DFID would competitively tender for an external supplier to deliver the programme activities. Potential suppliers might include private consultancy companies, think tanks and research institutes, academic institutions, and NGOs. / The strength of this option is the flexibility to bring in the best and most relevant skills and expertise into the programme. Suppliers could form consortia in order to draw upon the comparative advantage of different institutions. / Overall assessment: It is not feasible that DFID would be able to carry out this function in-house. The discussion of delivery options for component C of BRACED suggests that option 3 – externally contracted knowledge management agent - is the most feasible solution. Multilateral organisations may not have the expertise to deliver the required functions – however bids from multilaterals could be considered as part of a competitive tender process. / D. Appraisal of Management options / Appraisal Section B showed that investments in community-based adaptation are very likely to have a positive rate of return and that the costs to society and to HMG are likely to be higher in the without-programme scenario (the counterfactual) than with the programme. Section C considered at a number of ways in which the BRACED programme could deliver its activities. Delivery through NGOs is the recommended option. This section considers economy - how to purchase inputs at the best quality and price. / What management functions are required? / Table 16 outlines the management functions required of the programme. / Table 16: BRACED management functions / Strategic oversight functions / Policy oversight & accountability of programme components A and B (delivered through NGOS) and component C (delivered through knowledge manager); liaison with key partners at senior level; strategic decisions, high-level operational issues / Liaison with host governments and other key national stakeholders / Set appraisal criteria for proposal grants and full grants / Decision-making on grant selection based on recommendations / Contracting independent process evaluation of programme component C (which is implemented by knowledge management fund) / Analysis of evidence generated from component C to inform phase II of programme / Fund administration functions / Grant selection Issue call for proposals process for project preparation grants and full grants / Guidance and support for grant applicants, feedback on proposal grants and full grants / Assess concepts and make recommendations to DFID on grantee selection / Due diligence / Agree budgets, logical frameworks and grant agreements with grantees for full grants / Logistics of grant implementation and review On-going monitoring of output and financial tracking including verification through spot checks, ensure compliance / Conduct annual reviews and project completion reports / Portfolio analysis and risk management / Checking and verifying expenditure claims, disbursement, review audited accounts, monthly financial forecasting and monitoring against yearly accounts. / In this section we consider the best way to manage the delivery agent. Management options are given in Table 17. The critical success criteria against which we will assess the benefits of these options are set out in Table 18. As the functions largely concern management of the grants components of BRACED (i.e. A and B), and making links with the knowledge component (C), the estimated costs are given as a proportion of components A and B only (£100m). / Table 17: Management Options / Option Short description / 1 Management by NGO consortium / 2 Third party management agent / 3 Management by international organisation (such as WFP, GFDRR or UNSIDR) / 4 Management in-house / 5 Hybrid – combination of 2 and 4 / Table 18: Critical Success Criteria / Criteria Description / Feasibility and ability to deliver strategic oversight functions The option should deliver policy and strategic oversight of BRACED components A and B (delivery of community based adaptation and DRR through NGOs) and component C (knowledge and evidence building, delivered by independent body) as set out in table 20. / Feasibility and ability to deliver fund administrative functions The option should to deliver the administrative functions required for BRACED components A and B (delivery of community based adaptation and DRR through NGOs) as set out in table 20. / Appraisal of the management options / Option 1: Management by NGO consortium / How it would work / Under this option DFID would invite bids from NGO consortia to manage the implementation of components A and B of the BRACED programme. The evidence review conducted for this Business Case found no evidence of NGO consortia operating at such large scale[144]. / Estimated costs and benefits of the approach / Table 19: Benefits estimates of management option 1 – NGO consortium / Criteria Description / Feasibility and ability to deliver strategic oversight functions An NGO consortium could build on existing relationships with NGOs and draw upon relevant experience relating to grant proposals. However, it is less clear that it would be appropriate for an NGO management agent to make strategic decisions around bid criteria (DFID may wish to retain oversight of this), or to liaise directly with partner governments. / Overall score = 2 / Feasibility and ability to deliver fund administrative functions An NGO consortium has the potential to draw together experience in delivering financial accountability and risk management functions from good organisations with a range of experience. The main concern would be lack of management capability as there is no evidence of NGO consortia operating at such as large scale elsewhere. / Overall score = 3 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Table 20: Cost estimates of management option 1 – NGO consortium / There is no evidence of on which to base a numerical estimate of the costs of this option. A recent review of DFID’s experience with intermediaries for managing funds for civil society bodies found a wide range of mark-ups[145]. In principle, it could be expected that not-for-profit NGOS with the requisite capacity and experience would be cheaper than commercial intermediaries – but further consultation with potential partners will be needed to ensure cost effectiveness. / Option 2: Management by third party external management agent / How it would work / Under this option a management agent would be selected following competitive bids to manage the fund. The chosen management agent may be drawn either from the not-for-profit or fully commercial companies or consultancy groups. The DFID South Asia Climate Resilience Alliance (SACRA) Programme is an example of management by a third party management agent from the not-for-profit sector (International Institute for Environment and Development IIED). The Global Poverty Action Fund (GPAF) management solution, discussed in Box 14 under option 5 below, is another example of using an external manager. / Box 12 / Example of third party management agent: the South Asia Climate Resilience Alliance (SACRA) / SACRA is a 7-year project with a total cost of £37.7m in the form of core support to the International Institute for Environment and Development targeting the 5 countries of South Asia. It aims to leverage £300 million of additional finance. It operates through a hierarchy of institutions, in which a Regional Alliance and five National Forums are key. SACRA’s key outputs are scaling up promising projects, developing multi-stakeholder processes, and generating evidence on what works. / Estimated costs and benefits of the approach / Table 21: Benefit estimates of management option 2 – third party external agent / Criteria Description / Feasibility and ability to deliver strategic oversight functions Competitive tender would allow DFID to select a management agent with strong skills around bid selection and results monitoring. However, it may not be appropriate for the Fund Administrator to make strategic decisions around bid criteria (DFID may wish to retain oversight of this), or to liaise directly with partner governments. / Overall score = 2 / Feasibility and ability to deliver fund administrative functions External agencies in the DFID SACRA and GPAF programmes are proving to be effective solutions to the management of large-scale and complex development funds, offering good VFM. A range of different external agencies are available from both not-for-profit and commercially driven companies, consultancies and quasi-academic bodies, offering a variety of commercial, financial, research and developmental expertise. / A review of DFID’s use of intermediaries to manage civil society funds[146] found that the majority of DFID advisers interviewed felt that intermediary agents were more effective in the role than DFID staff. Agents are able to dedicate staff to specific management tasks, they can access a range of specialist skills and advice, and they have the flexibility to pull in extra staff to deal with surges, most importantly the major but discontinuous effort needed to run a large grant competition. / Overall score = 4 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Table 22: Cost estimates of management option 2 –third party external agent / The conclusions of a recent evaluation of DFID’s use of intermediary management agents for disbursing funds to civil society organisations were: “On large funds dealing with established UK CSOs, commercial intermediary agents can provide the services described as Core Functions, administration, commissioning and basic performance management for as little as 2% of the total fund.”[147]. Further evidence of the costs of a range of Fund Administrators is provided in table 28 below. / The Business Case for the DFID Global Poverty Action Fund estimated that an external Fund Administrator over the 7 year life of the programme, costs of DFID staff, fund management, M&E and due diligence would amount to approximately 6% of the total funds expected to be disbursed, excluding matching funding. The external fund management fees were estimated to amount to approximately 2.5% of funds to be disbursed. 2.5% of the £100 million grants components of the BRACED programme would equal £2.5 million / Option 3: Management by international organisation / How it would work / Under this option, an international organisation such as GFDRR, UNISDR or WFP would be invited to manage grants to NGOs and partners. Any DFID contribution to this would probably take the form of a Trust Fund. An example of an international agency as Fund Administrator is the DFID Adaptation for Smallholder Agriculture Programme (ASAP), managed by IFAD. / Box 13 / Example of an international agency as management option: the Adaptation for Smallholder Agriculture Programme (ASAP) / DFID is providing up to £150m for this programme from 2012 to 2015 to benefit around 6 million smallholder farmers in the most vulnerable countries to be channelled through the International Fund for Agricultural Development for ASAP. ASAP’s keynote features are safeguarding agriculture and food systems on which poor smallholders depend, scaling up practices and technologies to build farmers’ resilience, and producing evidence to help shape future international efforts in this area. ASAP aims to involve private actors in funding and implementing its programmes. / Estimated costs and benefits of the approach / Table 23: Benefits estimates of management option 3 – international organisation / Criteria Description / Feasibility and ability to deliver strategic oversight functions This option would limit the degree of competition in selecting a Fund Administrator and so may limit the range of expertise that can be brought into the programme. However, international agencies will have existing relationships with partner governments and other donors which could be drawn upon. / Overall score = 2 / Feasibility and ability to deliver fund administrative functions Using well-established international agencies offers the opportunity of disbursement through existing proven channels, avoiding start-up costs and delays from starting from scratch. Where these agencies are in the UN family they may also be more acceptable funding sources for some country recipients than bilateral sources – though funds based in the World Bank (such as GFDRR) may not have this perceived advantage. / However, international agencies can have more cumbersome and less flexible procedures and are more remote from the field. Table 13 in the delivery options appraisal considered the operational effectiveness of GFDRR, UNISDR and WFP. Drawing on the Multilateral Aid Review, that analysis found that the WFP and UNISDR scored poorly on operational effectiveness, whilst GFDRR displayed satisfactory performance. In the case of WFP it is not clear that a focus on resilience building is within the scope of the organisation’s mandate. / Overall score = 2 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Table 24: Cost estimates of management option 3 – international organisation / For the ASAP programme, DFID negotiated a mark-up of 7.5% with the IFAD. This was assuming a projected spend of $100 m per year, with 10 projects per year. The fee comprises 3.5% for direct project management, 2% for M&E, and 2% for knowledge management. Arguably, the two latter categories are programme costs, in which case the management fee could be regarded as 3.5%. / In Somalia the total handling and service charges paid by a bilateral donor to UN agencies for disbursements through the Central Humanitarian Fund typically amounted to 11-13% of the funds involved. These comprised a United Nations Development Programme (UNDP) banking fee of 1%, a UNDP administrative or managing agency fee of 7%, and an OCHA management fee of 3-5%. Where OCHA disbursed to NGOs, the latter’s administrative overhead was also added, making a total mark-up of 16-18% in this case.[148] / If DFID could agree with an organisation such as WFP, UNISDR, or GFDRR a similar fee rate for management through a Trust Fund as that obtained with IFAD under the ASAP programme, this would cost 3.5% of £100 million, or £3.5 million / Option 4: Management in-house / How it would work / Under this option DFID would recruit a new project management unit. Due mainly to manpower constraints, DFID has been reducing its direct management activities in recent years and it would require very strong evidence in order to adopt this approach for BRACED. / Estimated costs and benefits of the approach / Table 25: Benefits estimates of management option 4 – in house / Criteria Description / Feasibility and ability to deliver strategic oversight functions Under this option all strategic decision making and programme oversight would be managed in house by DFID advisers. This option would maximise internal learning from the programme and allow DFID to retain control of strategic direction. DFID is well placed to form and manage partnerships with partner governments in the BRACED programme countries. / Overall score = 4 / Feasibility and ability to deliver fund administrative functions DFID has strong experience at managing programmes from head office. DFID’s humanitarian aid programme has been responsible for delivering large volumes of humanitarian funding (£528 m in 2009/10) to a variety of international humanitarian agencies and NGOs in a number of countries. As the HERR Review states, “DFID has long been seen as a fast and flexible humanitarian donor”. [149] This has, however, been achieved in a fairly labour-intensive way, involving a large number of personnel in HQ and country offices. It is unlikely that existing staff resource would be sufficient to manage this programme – new administrative staff would need to be recruited. / Overall score = 2 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Table 26: Cost estimates of management option 4 – in house / The evaluation of DFID’s use of intermediary management agents for disbursing funds to civil society organisations reviewed 14 civil society funds, 5 of which are managed in-house by DFID. The results of the evaluation are summarised in the table below. The rows highlighted in yellow are managed internally by DFID (the WAHRF, CSCF, GTF, DAF and PACS funds). / Review of intermediary agency costs for DFID civil society funds (shaded yellow are managed in house) / IA Cost % Core Function % DFID Cost % Con-current Grants Average Grant £ Cost Per Grant £ / WAHRF 0.0 0.0 0.9 5 1,660,000 7,178 / CSCF 1.8 1.8 1.5 130 428,000 3,570 / GTF 2.9 2.9 0.2 38 2,631,500 12,496 / DAF 3.4 3.4 n/a 87 180,451 2,421 / BSF 9.1 9.1 0.1 23 1,490,000 41,471 / EEP 11.8 6.8 0.1 18 1,222,000 54,321 / CGI 12.1 7.3 0.1 190 55,000 2,450 / RGCF 13.8 8.7 0.1 122 140,000 5,727 / AcT 19.8 11.1 0.2 20 611,000 30,936 / CSUP 21.4 0.0 8.6 20 192,000 5,404 / DRF 35.4 35.4 0.2 33 28,000 15,373 / FCS 40.6 22.6 0.2 201 12,500 6,932 / PACS 42.0 10.0 0.2 150 96,000 2,840 / CSSM 42.5 26.6 0.4 44 25,600 15,379 / Four in-house managed funds come at the top of the table, i.e. with the lowest intermediary agent (IA) to cost ratio. IA and DFID costs relative to the total fund are low. This reflects a number of factors. First, no “value added” functions are undertaken (such as programme and project development, CSO capacity building, research/lesson learning and public relations). Although some of the funds have had logical frameworks retrofitted, none of them was launched with specific strategic objectives or any requirement that the IA should work to deliver those objectives. Second, the funds are large and, with the exception of CSCF, the number of grants relatively small. Even for CSCF, there is only one bidding round per year. Lastly, these funds are for UK organisations, or organisations which can bid effectively in the UK. Grant holders are, therefore, established organisations. Partly for that reason, performance management and M&E are largely limited to paper reviews of grant holder reports. On CSCF and GTF at least it is being recognised that this is not enough[150]. The BRACED management functions described in Table 16 are wider in scope than those undertaken by these Fund Administrators so costs may be slightly higher. / The review estimates that cost ratios of between 1.8% and 3.4% seem reasonable for the basic level of fund management support. The Governance and Transparency Fund (GTF) looks the most similar to BRACED in terms of grant number and size. If BRACED costs were comparable to GTF, the cost of in house management would be 2.9% of £100 million, or £2.9 million. / Option 5: Hybrid management option / How it would work / Under this option the strategic oversight management functions identified in table 19 would be implemented in house by DFID advisers, whilst the fund administrative function would be contracted to an external management agent (as per option 2). The DFID Global Poverty Action Fund (GPAF) programme combines strong DFID oversight, an independent advisory panel, day-to-day management by an external agent, and specific functions (monitoring and evaluation and due diligence) delegated to two further external agents. / Box 14 Example of Hybrid option – the Global Poverty Action Fund (GPAF) / A four-year project offering £40 million per year. A demand-led challenge fund open to NGOs, targeting DFID’s 28 focus countries or the bottom 50 countries on the UN’s Human Development Index. Consists of an Innovation Window offering grants of up to £250,000, and an Impact Grant window for “tried and tested” methods for grants of £250,000 to £4 million. Requires 25% matched funding from recipient NGOs. / GPAF is managed through the following structure: / DFID’s Civil Society Department – overall management: / External Fund Administrator – Triple Line Consulting, with support of Crown Agents for day to day management, including initial assessment of all concept notes and appraisals, fund disbursement and oversight of grants; / Evaluation Manager (Coffey International); / Due Diligence Manager (KPMG) / Advisory Board (now Panel) – external professionals helping in design and aspects of implementation / Table 27: Benefits estimates of management option 5 – hybrid option / Criteria Description / Feasibility and ability to deliver strategic oversight functions As per option 4, all strategic decision making and programme oversight would be managed in house by DFID advisers. This option would maximise internal learning from the programme and allow DFID to retain control of strategic direction. DFID is well placed to form and manage partnerships with partner governments in the BRACED programme countries. / Overall score = 4 / Feasibility and ability to deliver fund administrative functions As per option 2, this option offers the opportunity to bring in expertise from a range of external agencies with strong expertise in this field. Evidence suggest that external agents are able to dedicate staff to specific management tasks, can access a range of specialist skills and advice, and have the flexibility to pull in extra staff to deal with surges, most importantly the major but discontinuous effort needed to run a large grant competition. / Overall score = 4 / Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / Table 28: Cost estimates of management option 4 – hybrid option / The strategic oversight functions for the BRACED programme could be met by existing DFID advisor staff. / The fund administrative functions would be managed by an external agent (as per option 2). The DFID review of intermediary agents for civil society finds estimates that cost ratios of between 1.8% and 3.4% seem reasonable for the basic level of fund management support. The Business Case for the DFID Global Poverty Action Fund estimated that external fund management fees at approximately 2.5% of funds to be disbursed. 2.5% of the £100 million grants components of the BRACED programme would equal £2.5 million / Summary comparison of management options and recommendation / Table 29 sets out a multi-criteria analysis for the BRACED management options based on the analysis provided above. Each option has been allocated a cost “score” from 1 to 5, with 1 being the lowest cost option and 5 being the most expensive option. Since options 2 and 5 are expected to have similar costs, they both score 3. Each option has been allocated a benefits score, which are weighted according to the relative importance of the criteria. / Option 5 (strategic oversight by DFID plus fund administration by and external management agent) is the best performing option. Though it scored the same as option 2 on cost it scored very well against all of the benefits criteria relative to the other options. The benefit-cost ratios presented should not be treated with any cardinal significance here (they do not describe the return from £1 of investment) but they can be used to compare success across options. Option 5 has the highest benefit to cost ratio and so is the recommended option. / Table 29: Multi-criteria analysis – BRACED management options / Criteria Weight (sums to 1) Option 1 / (NGO consortia) Option 2 / (External agent) Option 3 / (Multilateral) Option 4 / (In house) Option 5 (Hybrid) / Cost score 2 3 5 4 3 / Benefits Score (1-4) weighted score Score (1-4) weighted score Score (1-4) weighted score Score (1-4) weighted score Score (1-4) weighted score / Strategic oversight function 0.5 2 1 2 1 2 1 4 2 4 2 / Fund administration function 0.5 3 1.5 4 2 2 1 2 1 4 2 / Total Benefit Score 2.5 3 2 3 4 / Benefit/Cost Ratio 1.25 1.00 0.40 0.75 1.33 / * Benefit scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong / ** Cost scores: The options are ranked from 1 to 5, with 1 being the lowest cost option as 5 being the most expensive option. / *** The benefit cost ratio has no cardinal significance but should be considered relative to the other options. Higher benefit cost ratios are associated with good performance. / E. Summary of appraisal recommendations / In line with the “3 E’s Framework” as set out in DFID’s Approach to Value for Money,[151] this appraisal considered three questions and associated sets of options. / Appraisal section B concluded that the benefits of investing in DRR and community based adaptation will outweigh the costs. It also showed that the costs of early actions to build resilience are much lower than those associated with ex-ante responses. / Appraisal section C considered delivery options for BRACED. The recommendation is delivery through an NGO led consortia for programmes A and B, and delivery by an independent agency for component C / Appraisal section D considered VFM of different management arrangements for the BRACED programme. The recommendation is that strategic oversight functions be carried out in-house by a dedicated advisory team in DFID, with fund administration functions contracted out to a third party management agent. / The recommendations from the appraisal case are summarised in figure 3. / Figure 3: Structure of the BRACED programme based on appraisal case recommendations / Component A / (Community based adaptation and DRR in the Sahel) / Component B / (Community based adaptation in other DFID priority countries) / Component C / (Knowledge and evidence generation) / NGO led consortia / NGO led consortia / Knowledge manager / External fund administration body / Strategic oversight - DFID / Management structure / Outputs / Delivery agent
C. For each feasible option, what is the assessment of local capacity? / Is the intervention likely to strengthen capacity in a durable manner? / The objectives of BRACED aim to build the capacity of a range of stakeholders to be able to respond climate extreme events. The grants to NGOS include criteria on developing capacity and sustainability (see Box 6) and of the knowledge and evidence building Component C is to use this evidence to help build capacity and capability, while Component D will focus on building national level policies and institutions.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The climate and environment appraisal was undertaken under the appraisal of the finance, delivery and management options (see sections above and Annex B). This appraisal only considers the climate and environment impacts of the management options. Therefore the main issue to be determined is how the different management options will manage the risk and opportunities BRACED presents, and how they will be avoided and mitigated or enhanced where these are positive. The result of this assessment is given in Table 30. / Table 30: Climate change and environmental categories of management options / Option Climate change and environment / Risks and impacts / Category (A, B, C, D) Opportunities / Category (A, B, C, D) / Option 1 – NGO consortium C B / Option 2 – Management agent C B / Option 3 – International agency C B / Option 4 – DFID C A / Option 5 - Hybrid C A
E. If any, what are the likely major impacts on social development? / The social impacts of BRACED are discussed under paragraphs 166 to 169 and are addressed by the programme design.
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / It is expected that BRACED will have a positive impact in fragile countries by reducing the impacts of climate related disasters which can be a contributing factor to instability and conflict. Conflict will increase the risk of project delays but working with local partners these will be minimised. This approach will also reduce the risk of conflict over project resources.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / These are covered in the appraisal sections.
H. Theory of Change for Preferred Option / The theory of change for the preferred option is attached as Annex E and shown Figure 2 (page 33).
I. What measures can be used to monitor Value for Money for the intervention? / The appraisal of the delivery and management options and the monitoring and evaluation section provides details on how we plan to monitor for value. Most important of the actions is determining the unit costs of the interventions planned which will then be subject to Cost Benefit Analysis. In addition, costs of these will be negotiated as part of the selection of grants.
J. Summary Value for Money Statement for the preferred option / The appraisal of the delivery and management options considers the costs of these different options and why the preferred delivery option, grants to NGOs managed by a hybrid option of DFID oversight and a third party offers the best VFM. Costs will be driven down under all the components of BRACED by ensuring costed proposal are negotiated to obtain maximum VFM and be paid, as far as possible on an output basis.
[98] Hallegatte et al (forthcoming) Investment Decision Making Under Deep Uncertainty – Application to Climate Change World Bank Policy Research Paper 6193
[99] “Insurance against Losses from Natural Disasters in Developing Countries”; IIASA Background paper for United Nations World Economic and Social Survey; Joanne Linnerooth-Bayer and Reinhard Mechler; (2008)
[100] Tearfund Report; Investing in Communities; The benefits and costs of building resilience for food security in Malawi (2010)
[101] DFID, (2007) Bangladesh Reducing Extreme Poverty in the riverine areas of North-West Bangladesh: Options for the Chars Livelihoods Programme beyond 2010
[102] Scott, L. D (2011) PhD Thesis, Manchester University; “Giving Assets; An effective approach for vulnerability and building livelihoods? The case of the Chars Livelihoods Programme”
[103] Some projects’ benefits were not possible to quantify. The highest cost-benefit ratio was found for crop diversification (sweet potato), 17.2.; a BCR of 1.6 was found for conservation farming.
[104] The IRR of an investment is the interest rate at which the net present value of costs (negative cash flows) of the investment equals the net present value of the benefits (positive cash flows) of the investment.
[105] ODI Humanitarian Practice Network Paper No. 49 (2004)
[106] Measures include the construction of an escape road, the provision of boats for evacuation, and the installation of raised hand pumps. Capacity-building included the establishment of a Village Development Committee (VDC), comprising members elected by the community, as well as smaller groups with specific responsibilities (e.g. a Village Rescue and Evacuation Team, a Village Vigilant Team, and a Flood Evacuation Centre Management Group). Each village has also established a women’s self-help group. Each community has created a village development fund.
[107] In each of the ten villages, a Disaster Management Committee (DMC) were established, and 20 young people were trained as an emergency response task force, responsible for rescue and evacuation. Vulnerability assessment and contingency planning have been conducted in each village, and women’s self-help groups and farmers’ groups have been established. The NGO has also initiated a number of physical measures such as raised hand pumps in seven of the villages, and made provision for repairs by training mechanics and issuing toolkits. The NGO has also been involved in testing alternative cropping in the villages to help with food security. Each village selected two farmers, who have received hybrid seeds that are stronger varieties and more resistant to pests (which are more common during flood periods and heavy rains). They have also provided diesel powered irrigation pumps to two villages, benefiting approximately 35 farmers. These are intended to extend the duration of the cultivation period.
[108] Benefits consist of avoided costs of repairing hand pumps, the reduced loss of household possessions, tools, and livestock, the reduction in loss of life and injury, and the avoided costs of boat rental. However, there are additionally many benefits that are more difficult to value, such as community confidence, gender-related impacts, and reduced stress.
[109] Quantified benefits are from raising hand pumps leading to time savings and health benefits during droughts, and avoiding blockage during floods.
[110] World Bank (2010) The Economics of Adaptation to Climate Change Synthesis Report
[111] “The Costs and benefits of Early Warning Systems”; Global Assessment Report on Disaster Risk Reduction; Rogers, S and Tsirkunov, V (2011)
[112] “Background Paper on the benefits and costs of Early Warning Systems for Major Natural Hazards”; GFDRR Paper; Teisberg, T J and Weiher, R F (2009)
[113] “The Costs and benefits of Early Warning Systems”; Global Assessment Report on Disaster Risk Reduction; Rogers, S and Tsirkunov, V (2011)
[114] “Community level adaptation to climate change; The potential role of participatory community risk assessment”; van Aist, M K, Canon, T and Burton, I; Global Environmental Change Vol 1 p165 (2008)
[115] “Integrating community based disaster risk reduction and climate change adaptation: Examples from the Pacific”; A. Gero, K. M´eheux, and D. Dominey-Howes; Natural Hazards and Earth System Sciences No. 11, p101 (2011).
[116] “Christian Aid and Disaster Risk Reduction”; Humanitarian Exchange Magazine; Issue 38, Moss, Sarah, (2007).
[117] “Cost-Benefit Analysis for Community-Based Disaster Risk Reduction in Kailali”; Mercy Corps, Nepal Publication; White, B A, and Rorick, M M (2010)
[118] A Cost-Benefit Analysis of Practical Action’s Livelihoods-centred Disaster Risk Reduction Project in Nepal; Practical Action Report; Willenbockel, D. (2011)
[119] DFID, (2007) Bangladesh Reducing Extreme Poverty in the riverine areas of North-West Bangladesh: Options for the Chars Livelihoods Programme beyond 2010; and Scott, L. D (2011) PhD Thesis, Manchester University; “Giving Assets; An effective approach for vulnerability and building livelihoods? The case of the Chars Livelihoods Programme”
[120] Climate Change Adaptation, Disaster Risk Reduction and Social Protection; Davies, M, Oswald, K and Mitchell, T; (IDS) P201 In Promoting Pro-poor Growth: OECD (2009)
[121] “Insurance against Losses from Natural Disasters in Developing Countries”; DESA Working Paper No. 8; Joanne Linnerooth-Bayer and Reinhard Mechler; October 2009
[122] “Breaking the Waves; Impact Analysis of Coastal Afforestation for Disaster Risk Reduction in Viet Nam; International Federation of Red Cross and Red Crescent Societies; (2011)
[123] Sahu Cost Benefit Analysis of Participatory Natural Resource Management; A study of Watershed Development Initiative in Indian Village; Munich Personal RePEc Archive (2008)
[124] Quantified benefits include increased (and more diversified) agricultural output and levels of income. Non quantified benefits included greater availability of water due to the construction of check dams, and health status of animal husbandry.
[125] DFID, (2007) Bangladesh Reducing Extreme Poverty in the riverine areas of North-West Bangladesh: Options for the Chars Livelihoods Programme beyond 2010
[126] Lobel ibid
[127] Climate Change: Impact on Agriculture and Costs of Adaptation. 2009 IFPRI
[128] The Economics of Early Response and Disaster Resilience: Lessons from Kenya and Ethiopia Courtenay Cabot Venton, Catherine Fitzgibbon, Tenna Shitarek, Lorraine Coulter, Olivia Dooley June 2012
[129] International Climate Fund (ICF) Implementation Plan 2011/12 – 2014/15 Technical Paper
[130] Foresight Report on Migration and Environmental Change. 2012.
[131] http://www.wfp.org/
[132] http://www.unisdr.org/
[133] https://www.gfdrr.org/node/1
[134] DFID Multilateral Aid Review 2011
[135] The World Bank (2012) Global fund for Disaster Risk Recovery, Global Program Review; Volume 6 Issue U World Bank Independent Evaluation Group
[1] http://www.wfp.org/our-work/competences
[2] http://www.wfp.org/about/strategic-plan
[136] The full paper is provided in annex 1
[137] http://www.oxfam.org.uk/what-we-do/about-us/~/link.aspx?_id=938CD43327384DCEBB80BD5F0946E570&_z=z
[138] http://practicalaction.org/how-we-are-funded
[139] http://www.savethechildren.net/about-us/our-finances
[140] DFID (2013) Civil Society Portfolio Review Refresh 2013, Department for International Development
[141] Ibrahim, S and Hulme, D., “Civil Society and Poverty”, in The Oxford Handbook of Civil Society, 2011. Edited by Michael Edwards.
[142] International Development Committee (2011) - Twelfth Report “Working Effectively in Fragile and Conflict Affected States: DRC and Rwanda”
[143] DFID (2013) Civil Society Portfolio Review Refresh 2013, Department for International Development
[144] DFID (2013) Building Resilience To Climate Extremes & Disasters Rapid Appraisal of the Management Options, 2013. Evidence in Demand Paper, PEAKS, DFID
[145] Morton J, (2010) Understanding and Learning Lessons from DFID’s Use of Intermediary Management Agents for Executing Civil Society Funds Centrally and in Country offices, DFID, March 2010
[146] Morton J, (2010) Understanding and Learning Lessons from DFID’s Use of Intermediary Management Agents for Executing Civil Society Funds Centrally and in Country offices, DFID, March 2010
[147] Morton, 2010, p. 25
[148] From Table 3.1 on p. 17 of Value For Money in humanitarian aid for Kenya and Somalia. A Report for DFID’s Nairobi Office by Coffey International, April 2011.
[149] Humanitarian Emergency Response Review. Final Report, 28 March 2011, p. 44
[150] Morton J, (2010) Understanding and Learning Lessons from DFID’s Use of Intermediary Management Agents for Executing Civil Society Funds Centrally and in Country offices, DFID, March 2010 (page 23)
[151] DFID’s Approach to Value for Money (VFM) Department for International Development, July 2011

# Commercial Case

A. Procurement/commercial requirements for BRACED / The procurement route for selection of grants to fund will be a ‘Call for Proposals’ process, with a competitive process for selection of projects and the selected projects managed under an Accountable Grant. This is the most appropriate approach as we want to ensure the participation of a range of CSOs through the consortia, including those not for profit and smaller organisations that would be put off by a legal contracting process. An accountable grant mechanism will also be quicker to arrange and more flexible, without requiring lengthy contract negotiations to make adjustments. On the basis of consultations so far we expect significant competition to be generated through a calldown process without a full tender being necessary to drive competition. / There will be two main contracts under the BRACED Programme. The first is a combined contract for the Fund Administration and to undertake routine M&E and Due Diligence of organisations receiving grants. The second contract will be to manage Component C on building evidence and knowledge, and undertaking strategic and thematic evaluations. / Funding through a Fund Administrator. The primary reason for the approach of using a Fund Administrator is that it is more effective than in-house management, as specialist staff can be dedicated to tasks and will have the flexibility to handle issues as they arise. This approach will also enable DFID to have a more strategic oversight of the BRACED programme, and will remove the administrative burden of managing the proposals and funds from DFID. / The external Fund Administrator will be required to : / Manage the BRACED competition process- Issue call for proposals process for project preparation grants and full grants / Assess all applications and making recommendations to DFID / Issue call for proposals process for project preparation grants and full grants / Prepare and put in place all grant agreements for successful BRACED applicants / Issue call for proposals process for project preparation grants and full grants / Undertake due diligence checks on all organisations receiving grants under BRACED / On-going monitoring of output and financial tracking including verification through spot checks, ensure compliance / Conduct annual reviews and project completion reports / Portfolio analysis and risk management / Checking and verifying expenditure claims, disbursement, review audited accounts, monthly financial forecasting and monitoring against yearly accounts. / There will be a parallel contract for Building Evidence, Knowledge and Evaluation Management. This manager will undertake a range of tasks on knowledge management and in addition will conduct routine monitoring and evaluation of the grants provided under Components A and B throughout the life of BRACED. Quarterly reports will be submitted by the Building Evidence, Knowledge and Evaluation Manager to DFID for review, to allow key decisions to be made regarding the direction of the programme and to ensure efficiency levels are maintained and effective delivery against outputs achieved. / The exact requirements for the Building Evidence, Knowledge and Evaluation Manager would be determined in line with CED’s approach to evaluation, learning and evidence including the implementation of the ICF (see Management Case). The indicative breakdown of activities and costs is provided below. / Activity Cost / Knowledge Platform / -Network building, including with research / -Peer to peer learning actions – meetings etc. / -Synthesise learning into reports, communicate findings Sharing of knowledge / £1.05 million / Data Collection / £2 million / Analysis and documentation / £1.9 million / Technical assistance / - Development of indicator methodologies / - Support to grantees for logframes / - Conduct project evaluations Technical assistance to ongoing monitoring / £0.4 million / Project evaluations (6 at £400,000 each) / £2.4 million / Strategic Evaluations / - Conduct up to 5 strategic evaluations 5 strategic evaluations at £450,000 each / £2.25 million / Fees / (including ongoing technical support costs) 0.75 million / A thorough and open tendering process will be followed for the procurement of the Fund Administrator and Building Evidence, Knowledge and Evaluation Manager. This process will be in line with the OJEU procedures. As there is a tight timeline for the implementation of BRACED, an accelerated restricted procedure and a negotiated procedure will be used, as agreed with Procurement Group. This means the final selection of the successful bidder will be made within a six month period. / To support the implementation of BRACED two smaller contracts will be let. One will be for an organisation to undertake due diligence check of the organisations selected to be the Fund Administrator and Building Evidence, Knowledge and Evaluation Manager. This check will be determined if each organisation is able to manage risk and ensure close fiduciary control. / The second contract will be to support DFID in assessing the call for concepts for NGO grants. It is expected that this will be done through an existing framework agreement. This is to allow the call for concepts process to start before the Fund Administrator is selected through OJEU, which would delay the start of the programme by several months. Neither CED nor ARD have internal administrative capacity to manage this call process in this timeframe. / In awarding grants to NGOs it will be necessary to provide advance payments for two main reasons: / Those bidding for BRACED grant funding will be ‘not-for-profit’ organisations, which are unlikely to have sufficient financial resources to provide the advances necessary from their own reserves to cover programme costs. DFID wants to encourage such organisations to bid as they often drive innovation. According to standard DFID procedure, ‘not-for-profit’ organisations can individually request payment in advance and will be granted this if the request is justified. The Fund Administrator will ensure that the necessary confirmation from each organisation is secured that they are not-for-profit and do not have the means to pre-fund. / If the Fund Administrator had to borrow sufficient resources to cover this pre-financing, there would be a significant cost to the taxpayer in terms of bank charges. There is also a risk that a requirement to borrow to pre-finance will severely restrict the supply base and number of suppliers able to tender, with negative consequences for the quality and value for money DFID will obtain. / Payment Process / The management of the BRACED funds will be undertaken by the Fund Administrator, and will include appraisal of proposals, the review of progress reports, and checking financial request claims. The tender evaluation will include a robust evaluation of the financial and procurement capability of bidders. The final decision on which bids are supported will remain the responsibility of DFID. / The Fund Administrator will be required to open an account solely for the BRACED Programme. In order to keep account balances low, on a monthly basis the Fund Administrator will provide DFID with a list of all claims received that month from fund recipients and a total figure for that month. This list would detail all of the actual expenditure being accounted for and the amount of advance funding requested for each on every individual programme. / The Fund Administrator will need to submit an assurance statement that all amounts claimed had been checked and verified by their finance team and that they were certifying the accuracy of the figures produced. They would also require fund recipients themselves to have certified the accuracy of all figures and that all advance amounts requested were appropriately justified. / DFID would review the claims list and, where satisfied that all the necessary assurances had been received, issue a payment to the project account. As part of the process we would undertake a fuller spot check of a small selection of payment requests from Fund Holders to ensure the accuracy and reliability of both the Fund Administrator’s and the Fund Holder’s calculations. DFID will put in place an agreement with the contracted Fund Administrator that they would ensure that all payments transferred by DFID into the project account would be passed on to the organisations running the successful bids. The agreement with the Fund Administrator would also stipulate that any interest accrued on this account would be used to offset any bank charges. Any interest over and above charges will be the property of HMT. However we do not expect to have any significant interest as funds are being released just in time. / This method of payment would put DFID funds at an increased level of risk. So to reduce this DFID will ensure that all of the necessary certifications are in place and agreed and that the process and the role of all parties involved are clarified.
B. How we expect the market place will respond to this opportunity? / BRACED is a significant programme and we expect tenders for both managers to attract considerable interest in the market and to generate a range of competitive bids. / An advance funding process for managed grant costs will reduce barriers to entry for NGOs who would be unable to pre-finance fund disbursement to project recipients. This will increase the number of potential bidders.
C. How does BRACED use competition to drive commercial advantage for DFID? / Competition will be conducted in an open and transparent manner, under the EU Procurement Directives. In order to drive commercial value CED will build the following requirements into all terms of reference: / Clearly defined deliverables/outputs that demonstrate contribution to BRACED outcomes. / Linked to the above, the contract will have clear key performance indicators and where possible will be based on payment by results / Determining budgeting, accounting and reporting schedules that work not only for DFID, but also for the Fund Administrator (and ultimately for successful bidders) / Engagement with senior project stakeholders to turn around, and if necessary terminate, poorly performing projects. / DFID does not pay in advance of need. However, Climate and Environment Department will request approval from DFID’s Finance and Corporate Performance Department (FCPD) and HM Treasury to a payment to the Fund Administrator for financing of accountable grants.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Bids will be judged against the value for money criteria of economy, efficiency, effectiveness. / economy – fees, daily rates, overheads etc. and unit costs of specific inputs. For example; comparison with current costs, and those for other Fund Administrator contracts. Costs of accommodation, travel, and other expenses will be included in the commercial evaluation. In consultation with PrG, consideration will be given to requesting a breakdown of supplier overhead costs, including profit in the commercial bids; / efficiency – number of days and/or staff required to deliver outputs, the inclusion of recommendations, which would improve the delivery of outputs or reduce fiduciary risks etc.; and, / effectiveness – elements of the proposals that would improve the overall impact of local technical capacity or introducing better management practices into the sector as a whole. / Management fees being charged will be included in the commercial evaluation to ensure these costs are at an appropriate level for the programme and benchmarked against other similar fund disbursement programmes.
E. How will the contract be structured and how will contract & supplier performance be managed through the life of the intervention? / (See the Management case for full details) CED will follow DFID’s best practice guidance for managing supplier performance as set out in Money Sight. Key Performance Indicators will be included in the Terms of Reference, and used to measure supplier performance through contract duration. CED will have regular supplier meetings to discuss progress against KPIs. / Reporting and monitoring requirements will be included in the Terms of Reference and will be on a quarterly, six-monthly and yearly basis. The Fund Administrator will submit monthly accounting reports to DFID. This will enable DFID to make key decisions regarding the direction of the programme, to ensure efficiency levels are maintained and effective delivery against outputs achieved.
Delivery through a third party entity (multilateral organisation; civil society organisation or support to government) / A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The appraisal of delivery and management options sets out why this is the preferred option.
B. What assurance has been obtained on capability and capacity to deliver? / The appraisal of delivery options set out the capability and capacity of NGOs to deliver the grants to scale up actions on DRR and adaptation. In selected the preferred bidders for the Fund Administrator and Building, Evidence and Evaluation Manager capacity and capability will be criteria for the selection of these contracts.
C. Is there an opportunity to negotiate on anticipated costs? / Yes there will be opportunities to negotiate costs of the Fund Administrator and Building, Evidence and Evaluation Manager. In awarding grants the Fund Administrator will be required to negotiate costs and seek value for money before grants are awarded to NGOs.

# Financial Case

A. Who are the recipients of all proposed payments? / Grants will be made to alliances or consortia led by an NGO. Initial project preparation grants of up to £250,000 may be awarded. Following this and assessment of proposal full grants will be made for an initial three years and will be minimum of £3 million and maximum of £10 million. Subject to performance and approval of a second phase of BRACED, these grants may be extended. Full details of the grant process are given in paragraphs110 to 116.
B. What are the costs to be incurred directly by DFID? / BRACED is a seven year programme. In the first four year phase from August 2013, the UK will provide up to £140 million from the International Climate Fund (ICF). This business case covers £110 million for Components A, B and C. A further business for component D will be prepared as this component requires further design. / The second phase of three - four years is expected to have a budget of between £200 to £300 million. A separate business case will be submitted for this phase in 2015/16.
C. What are the costs to be incurred by third party organisations? / Not applicable as no costs will be incurred by third party organisations.
D. Does the project involve financial aid to governments? / Not applicable as no direct financial aid to governments.
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / This programme will be funded using 100% current programme resources available from the ICF budget for the first phase. Resources for the second phase will be subject to next resource allocation round starting in 2016/17.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / The overall budget of £140 million will be profiled as £9.7m in financial year 2013/14, £38.1m in FY 2014/15, £38.3m in FY 2015/16 and £24m in FY 2016/17. See Table 31 for an indicative breakdown of costs. / The Programme Managers within Climate and Environment Department (CED) and Africa Regional Department (ARD) will ensure accurate forecasting through developing a strong working relationship with the Fund Administrator, enabling effective engagement on programme issues including financial management issues. The Fund Administrator will submit quarterly financial statements and a more detailed annual financial and narrative progress report which will also include an assessment of risks associated with delivery. These reports will clearly indicate realistic projection of spend for the current financial year broken down by quarter on all major budget category lines. / The Fund Administrator will provide financial forecasts to DFID on a monthly basis. Forecasts should be accurate to within 2%. This is ensured by including accurate forecasting as a Key Performance Indicator for the Fund Administrator. DFID will require that the Fund Administrator advise DFID in advance of any unexpected potential significant changes in forecasts. / CED and ARD’s Programme Managers will rigorously reconcile these forecasts against (i) relevant data on Aries; (ii) work plans and budget; (iii) previous quarterly reports; and (iv) previous disbursements and past spending trend. Any discrepancies will be quickly raised with the Fund Administrator and necessary changes to forecasts will be agreed. The Lead Adviser will also be consulted on all financial issues identified as well as any changes to forecasts on Aries that need to be made. / Table 31: Annual breakdown of BRACED costs over first phase years (£ millions)
G. What is the assessment of financial risk and fraud? / The financial risk and that of fraud will be different for each component. For the Fund Administrator and Building, Evidence and Evaluation Manager we assess the risk to be low as we will subject the preferred bidders to a full due diligence. There is a higher financial risk and of fraud under Components A and B that provide grants to NGOs and their partners. NGOs leading the grant will again be subject to full due diligence and again the level of risk at this level is low. However, at the implementation level these NGOs will be working with a range of partners in different environments. Some of these will be challenging and in fragile states and areas of post-conflict. The financial risk and risk of fraud will be higher. We will be asking all recipients of grants to set out how they plan to manage and mitigate these risks, and what action they will take if any fraud is discovered.
H. How will expenditure be monitored, reported and accounted for? / Grant level / Each organisation selected for a grant must undergo a due diligence check before the grant is confirmed. These pre-grant due diligence procedures aim to ensure value-for-money by identifying potential risks and capacity building opportunities around governance, management and capacity within the partner NGOs. Pre-grant due diligence helps to reduce the risk of diverted funding and establishes an environment of accountability and transparency. The pre-grant due diligence assesses capacity to manage the proposed level of DFID support in the following areas: / • Governance: The focus on governance considers how the NGO is administered, its risk management processes and its ability to comply with key legislation such as the Bribery Act 2010. Key policies and procedures are also assessed, including those covering child protection, environmental risk management and conflict of interests. / • Financial Capacity: The financial focus includes assessing the financial position and stability of the organisation and its ability to effectively and efficiently manage the proposed level of DFID support. / • Operational Capacity: The operational capacity considers whether the organisation has the resources and systems in place to deliver the proposed outcomes. / • Value for Money and Results: In addition, the due diligence process assesses the organisation’s approach to value for money and its ability to measure and report the results of DFID’s grant. / If a due diligence finding highlights unmanageably high risk for DFID the grant offer will be withdrawn. Wherever possible DFID looks to put in place remedial actions that will allow the grant to go ahead. / Once the grants are agreed all grant holders are required to submit audited accounts annually for review. / In making grant payments the Fund Administrator is required to thoroughly check grant holder expenditure claims. This includes verification through requesting the supporting documentation for a random 15% of claims each month. The Fund Administrator will also conduct risk based and randomly selected audit and spot check visits to 5% of grant holders and project sites per year. / Fund level / The Fund Administrator will be required to open an account solely for the BRACED Programme. In order to keep account balances low, DFID will require, on a monthly basis, the Fund Administrator to provide DFID with a list of all claims received that month from fund recipients and a total figure for that month. This list would detail all of the actual expenditure being accounted for and the amount of advance funding requested for every individual project allowing for “just in time payments”. It will also achieve best value for money via a fund specific account through which all funds would be processed, resulting in a significant saving to DFID in transaction costs. / The list of claims would include an assurance statement from the Fund Administrator that all amounts claimed had been checked and verified by their finance team and that they were certifying the accuracy of the figures produced. They would also require fund recipients themselves to have certified the accuracy of all figures and that all advance amounts requested were appropriately justified. / DFID would review the claims list and, where satisfied that all the necessary assurances had been received, issue a payment to the project account. As part of the process we would undertake a fuller spot check of a small selection of payment requests from Approved Projects to ensure the accuracy and reliability of both the Fund Administrator and the Approved Project calculations.
I. Are there any accounting considerations arising from the project? / None

# Management Case

A. What are the Management Arrangements for implementing the intervention? / Overview / As set out in the Appraisal Case the option of Hybrid Management has been selected; strategic oversight functions will be carried out in-house by a dedicated advisory team in DFID, with fund administration functions contracted out to a third party management agent. BRACED will be managed by a competitively selected organisation which will take primary responsibility for ensuring the aims and objectives of the programme are achieved. This organisation will manage the selection of beneficiaries, administer the scheme and ensure compliance with DFID’s financial and management requirements. / DFID will focus on strategic oversight and will ensure BRACED interacts with other DFID programmes at both global and country level. However, DFID will retain a strong role in decision-making as the programme develops. DFID will also be involved in the monitoring and evaluation process to ensure compliance with the aims and objectives of the programme as set out in this business case. / BRACED DFID personnel requirements / BRACED will be managed by CED and ARD working closely with CHASE and ART, and with relevant country offices where BRACED has projects. DFID staffing resources will be higher for the initial management of BRACED in terms of management the procurement of the contracts for the Fund Administrator and the Building Evidence, Knowledge and Evaluation Manager, and also to run the call for concepts for the grants to NGOs. The expected staff resources are given below: / First six months / • CED and ARD three A1 Team Leaders @ 10% each. / • CED A2 Climate change and livelihood adviser (25% FTE), CED A2 results adviser (10% FTE), ARD A2L climate change adviser (25% FTE), ARD Policy Adviser (25% FTE) and Humanitarian adviser (25% FTE) / • B1 Programme managers – CED 50% FTE and ARD 50% / • Support from cadre 10% to help CED and ARD review project concepts – 30 person days. / Regular management of BRACED after first six months / • CED and ARD three A1 Team Leaders @ 5% each. / • CED A2 Climate change and livelihood adviser (10% FTE), CED A2 results adviser (15% FTE), ARD A2L climate change adviser (10% FTE), ARD Policy Adviser (10% FTE) and ARD Humanitarian adviser (10% FTE) / • B1 Programme managers – CED 15% FTE and ARD 15% / Management of Contracts / The Fund Administrator and the Building Evidence, Knowledge and Evaluation Manager would be procured through an Official Journal of the European Union competitive process. The Fund Administrator is responsible for the effective and efficient administration of BRACED to ensure operational effectiveness and be responsible for project verification. The Building Evidence, Knowledge and Evaluation manage is responsible to develop and share the evidence on DRR and adaptation. / The BRACED grant holders are responsible for implementing the agreed projects. Management arrangements vary between projects but all grant holders are required to have sufficient resources and capability in place for financial and programme management, managing risk and monitoring, evaluation and learning. This is assessed through the application process and the due diligence checks. / Where grant holders use implementing partners they are required to have a Memorandum of Understanding between them that incorporates all the conditions in the DFID grant. This increases DFID’s reach and assurance throughout the funding chain. / As BRACED is a demand driven fund supporting multiple projects in a range of countries it is not possible to meaningfully include beneficiaries in the fund level governance arrangements. However, all projects are required to have clear mechanisms in place to enable beneficiaries to participate in the design, management and implementation of the project. / Roles and responsibilities / The BRACED management process for Components A and B is given below. / Step 1: Funding competition to select projects for a provisional grant that meet the set criteria and are likely to deliver value for money results. / DFID CED and ARD role: Setting the criteria of BRACED, approving detailed guidelines, application forms and timeline; communicating information on call for concepts; agreeing concept notes to invite to proposal stage; engaging DFID country office and policy staff in reviewing shortlisted applications; and quality assuring Fund Administrator assessment. / Fund Administrator role: Setting appraisal methodology based on fund criteria for full proposals; producing guidelines and application forms; assessing concept notes and proposals and making clear funding recommendations to DFID; communications with applicants including detailed feedback on applications; additional support to applicants new to DFID funding including workshops on logframes, setting budgets and the application process; run helpline for applicants. / Step 2: Perform due diligence checks on provisional grantees to inform DFID’s decision about whether to award funding. / DFID role: Instructing the due diligence manager on which organisations to review. A system is in place to ensure that if an organisation has previously undergone a DFID due diligence check then any future checks are proportionate. Reviewing due diligence reports and making decisions about final funding awards or additional conditions to include in the grant agreement based on the findings. Decisions are risk-based. DFID has a low risk appetite for financial instability or weak financial controls. However, as far as possible organisations with critical findings are given time bound opportunities to address weaknesses. / Due Diligence manager role: Undertake pre-grant due diligence checks on all applicants offered a provisional grant. The due diligence procedures will identify potential risks and capacity building opportunities around governance, financial capacity, operational capacity and value for money and results. / Fund Administrator role: Include additional conditions in grant agreement on DFID instructions and track whether grant holders meet conditions. / Grant holder role: Implement DD findings where required. Provide management response to full DD report with first annual report / Step 3: Set up grant agreements between DFID successful applicants. Address any media queries. / DFID role: Quality assure Fund Administrator work and sign grant agreements / Fund Administrator role: Negotiate and agree budgets with grant holders; advise on and agree monitoring frameworks including logframe and baselines; produce grant agreements for DFID signature with standard clauses and conditions plus any arising from the due diligence process / Grant holders: Put in place an MoU with implementing partners that includes the same terms and conditions as the DFID grant. This helps ensure that DFID has standard assurances throughout the project delivery chain. / Step 4: Manage on-going grants (programme and financial management) / DFID role: Set standards; quality assure Fund Administrator work; take decisions on grant issues if the matter is escalated above the Fund Administrator. / Fund Administrator role: Assessing annual reports, project completion reports and independent evaluations and providing feedback; in year project monitoring including spot check monitoring visits; ensuring compliance with grant agreement; annual portfolio analysis; oversight of risk management process that is both embedded in day to day work and reviewed at a quarterly management meeting between DFID and Fund Administrator; ensuring the correct and proper close-down of projects in line with approved plans; agree any budget revisions throughout the life of the project for all approved grants based on an established criteria; issuing of revised grant arrangements for DFID signature; checking, verifying and authorising expenditure claims for fiduciary oversight; disbursement of project funds on a quarterly basis; review grantee annual audited accounts; monthly financial forecasting; reviewing and verify payments against end of year financial statement. / The Fund Administrator will apply a proactive management approach and closely monitor poor performing or at risk projects. Early action will be taken to put in place performance improvement plans that are monitored through engagement with the grant holder and where needed through in-country project visits. DFID maintains oversight in-year project monitoring through bi-weekly progress meetings with the Fund Administrator. Where a project is consistently performing poorly DFID and the Fund Administrator will take a decision to either suspend funding until the required action has been completed or close the project. / There is also a need for strong financial management. In addition to routine checking of grant holder expenditure claims the Fund Administrator will be required to verify grant holder expenditure claims through requesting the supporting documentation for a random 15% of claims each month. The Fund Administrator will also conduct risk based and randomly selected audit and spot check visits to 5% of grant holders and project sites. / Step 5: Close down projects / Fund Administrator role: Review Project Completion Reports and independent evaluations; follow procedures including returning of assets / Fund Administrator contract management: / DFID role: Writing terms of reference and running the OJEU process with DFID’s procurement group. Once the supplier is appointed contract management includes setting out DFID’s expectations; minuted bi-weekly meetings; minuted quarterly performance reviews and review of risk management process; monthly financial reports; six monthly reports from the Fund Administrator; annual review by DFID and annual portfolio analysis; annual survey of grant holders against Fund Administrator performance; quality assurance of Fund Administrator correspondence with grant holders.
B. What are the risks and how these will be managed? / There are a wide range of potential risks to the implementation and management of BRACED. These are summarised in Table 32 with the probability of their occurring and what steps are being taken to manage and reduce these risks. / Table 32: Implementation risks to BRACED and their mitigation / Risk Impact Probability Mitigation Measures / BRACED ends up simply funding a series of NGO community level interventions which deliver results but do not help shape the policy and institutional framework and therefore their impacts are not sustained High Low Criteria for project selection cover the policy and institutional linkages and sustainability / Component C to work across projects to share and learn lessons on scaling up and the policy changes needed to do this. / DRR and adaptation methods and approaches implemented by NGOs are not appropriate and/or deliver value for money High Low Assessment of proposals and use of project preparation grants to determine effectiveness of approaches to be used, and then monitoring of them during implementation with Component C working across projects to share and learn lessons on what works. / BRACED is unable to encourage local government engagement, meaning that the wider economic policy links cannot explored High Low Less of a risk in existing DFID programme countries where links with government already exist, to mitigate this risk partnership and engagement with local government is criteria for NGO grants, and the knowledge component will include a focus on learning and sharing evidence on this. / Methods and approaches implemented by NGOS do not help empower women High Low NGOS will be asked to under gender analysis and to make clear on how what they propose will benefit women. / All relevant indicators to be disaggregated by gender and performance monitored. / Fraud and misuse of DFID resources by BRACED grantees. High Medium Undertake due diligence of lead NGOs and ensure they have systems in place to manage these risks in difficult and sometimes fragile environments. / Fund Administrator performs poorly and grants and not adequately managed and monitored. High Low Rigorous criteria will be used in selecting the Fund Administrator, and their performance will be monitored by DFID staff and action will be taken if this is not up to standard and milestones not being met. / Specific to Sahel component A / The security situation in the Sahel deteriorates to a point where BRACED can no longer able to operate in one or more of the five Sahelian countries. High Medium Split funding between a variety of partners, including NGOs with an expertise in and history of operating in very fragile environments. / Work with the FCO and MOD on conflict prevention strategies in the Sahel. / Other critical interventions to sustain resilience over the medium to long-term that DFID cannot support are lacking or slow in achieving progress (including education and long-term macro-economic growth, and sustainable long-term health and water programmes). High Low to high depending upon country Targeted support to and influence of the multilateral system to generate coherent country and regional-level strategies, to ensure all priority interventions are covered. / Future shocks, including conflict are sufficiently large to overwhelm coping capacity to climate extreme events even with improved resilience, and/or take place in early stages of the programme. High Low to medium Retain flexible humanitarian funding to allow response to meet critical needs and protect the gains made so far through the resilience programmes / Specific to Component B / The security situation deteriorates to a point where BRACED can no longer able to operate in DFID focal countries. High Low Monitor security situation in countries BRACED is working in with relevant country offices, and if it deteriorates meet with grantees to assess what actions are needed to maintain operation / Specific to Component C / Components A and B do not deliver the lessons on how to scale up DRR and adaptation and no evidence is built up High Low Given the range of projects and the rigorous selection criteria and proof that methods and approaches work will ensure projects are implementing practices that will deliver. / Fund Administrator performs poorly and grants and not adequately managed and monitored. High Low Rigorous criteria will be used in selecting the Fund Administrator, and their performance will be monitored by DFID staff and action will be taken if this is not up to standard and milestones not being met.
C. What conditions apply (for financial aid only)? / Not applicable
D. How will progress and results be monitored, measured and evaluated? / M&E partners / There will be three groups of actors in the collection and reporting of monitoring information: / The consortia of NGO’s, local government, private sector and research organisations working at the grassroots level under Components A and B. / The Knowledge Manager under component C that will work with the alliances/consortia in components A and B to monitor and evaluate projects to identify what works in climate change adaptation and DRR. Component C will lead on the strategic evaluation of BRACED and will work in consultation with CED, ARD and ART, and DFID country offices. / The Building Evidence, Knowledge and Evaluation Programme Manager will coordinate an M&E Implementation Group with representatives from DFID and the Fund Administrator. The M&E Implementation Group will meet quarterly. / Monitoring Plan / The programme as a whole will be monitored against its logframe. This will be a living document and will be updated when a response is undertaken, and after each annual review as needed. Reporting for long term interventions will be on a six monthly basis. Programmes will aim to collect monitoring data against the key objectives of this work and where relevant indicators from both the ICF and DFID results frameworks. / Data collection / Responsibility for data collection and project level output monitoring and reporting against the logframe will lie with the grantees under components A and B. The group developed under component C will help manage this process ensuring that all agencies involved in each grantee have effective monitoring systems in place, and the necessary support and capacity to implement them, including by designing common indicator methodologies and providing technical assistance to implement them. They will also communicate the results of this work to DFID for central reporting processes (e.g. ICF, DRF, AR). / Baseline, milestone and target data will be obtained at project level by the grantee responsible for each projects delivery. The group developed under component C will support this work and will also monitor the overall process. Data will be sourced from project level management systems and national statistics in relevant countries. Where the required data is not available from these sources then independent data collection may need to be commissioned e.g. participatory monitoring under Component C by the Building Evidence, Knowledge and Evaluation Manager. / Where data is available publically and it is unreasonable to expect grantees to source data then the Manager of component C will obtain this data from public sources where possible. Monitoring and evaluation data will be disaggregated by gender, age and vulnerability wherever possible to allow effective tracking of who is benefitting from BRACED interventions. The Building Evidence, Knowledge and Evaluation manager will be expected to use and build partnerships with other work commissioned by DFID – for example the Tracking Adaptation and Measuring Development (TAMD) project of IIED, and the CHASE led work on Measuring Resilience.. / Monitoring budget / The monitoring activity of each programme under components A and B will be financed through the grants to NGOs and verification will be through the 2.5% management costs of the Fund Administrator. Technical assistance to monitoring approaches, for example design of indicator methodologies and coherence with portfolio logframe will be financed from component C as one of the main deliverables. / Planning and governance / At the stage of the final approval for each BRACED project DFID will play a quality assurance role in checking that a detailed monitoring plan including project baselines are in place, or that there are tangible plans in place for these to be established within six months of project start. / An element of flexibility will be built into the monitoring plan to allow changes to the logframe based on the experience of data collection and reporting under component C. When NGO projects are selected these will be used to update the logframe and indicators. Where changes are proposed these will need to be approved through the DFID M&E Implementation Group. / Evaluation Plan / The evaluation strategy will have two main strands. First to support a number of experimental technical evaluations through a sub-set of the projects – estimated at around 6. These will use experimental methods, RCTs where possible, and aim to assess the impact of the project on resilience in comparison to control sites, complemented with participatory survey methods. The knowledge manager under component C will carry these out in partnership with project grantees, and will select the subset to evaluate based on an evaluability assessment of the project proposals once received. The output will be an increase to the evidence base of the number of systematic cost-benefit analyses of DRR and adaptation interventions, and verification of the methods used for resilience measurement. The second strand of work will be to conduct up to 5 strategic evaluations to answer specific questions– see list below. The knowledge manager will finalise these questions following the evaluability assessment of the project proposals. / Project level evaluations / Under components A and B project level evaluations will be carried out over the course of each project where relevant. The decision on whether an evaluation is needed will be based on the size of the project and the nature of the work being carried out. / Project level evaluations will be embedded evaluations for the purpose of contributing to robust evidence of what works, the costs and benefits of the intervention in question, and the long term impact on resilience (including as a means to verify the measurements of resilience chosen) rather than to assess project performance overall, or to resolve any broader questions around how to achieve climate change adaptation and DRR outcomes. These evaluations will be undertaken by the knowledge manager under component C in conjunction with leading evaluation experts in the field of climate change adaptation and DRR, working with the project grantees. Experimental or quasai experimental methods will be deployed for these evaluations, including randomised control trial approaches where possible, supplemented with other methods where needed such as participatory survey methods. The number of project evaluations will be determined by the knowledge manager after an evaluability assessment of the project proposals but around 6 are anticipated, at an approximate cost of £400,000 each, totalling £2.4 million, though these costs can be supplemented by funding under the management/administration budget of components A and B / Strategic evaluations / Independent strategic evaluations that synthesise learning from the evaluation work of components A and B and other global work will be designed and managed under component C. All evaluation work at project or strategic level will also take into account and coordinate with any regional or ICF level evaluation work being planned. / Where possible these evaluations will be commissioned in conjunction with other donors to help ensure buy-in for the evaluation and greater likelihood that findings will be more widely adopted. The findings of these evaluations will be shared through the BRACED knowledge management component under component C. / Evaluation strategic level questions / Table 33 provides initials strategic evaluation questions. These will be developed and refined by Component C following an evaluability assessment of the full project proposals once received. The exact number will depend on this assessment but it is anticipated up to 5 evaluations will be conducted at a cost of around £450,000 each, totalling £2.25 million. The finalisation of evaluation questions will be done in consultation with DFID, and will be linked to the overall ICF Evaluation programme. / Table 33: Potential Strategic Evaluation Questions / How does combining climate change adaptation and DRR help build resilience to climate change? / What types of interventions are most successful and able to have a sustained impact on the resilience of climate vulnerable people? / Who are the best agents to work through to deliver climate change adaptation and risk reduction and what policy and institutional frameworks are need to sustain this? / What are the best DRR and adaptations that build women’s resilience to climate extreme events? / Are interventions are able to reach those who need it most? / What policy and institutional changes are needed to transform how we build resilience of people to climate extremes, including in Fragile States? / Planning and governance / At the stage of approval for each BRACED project (full bid selection) DFID will play a quality assurance role in checking that a detailed evaluation plan including baselines are in place, or that there are tangible plans in place for these to be established within six months of project start.
Logframe / The log frame for BRACED internal QUEST no is 4075217

# List of acronyms

ARD	Africa Regional Department (DFID)
AGIR	-Sahel	Alliance Globale pour I’initiative Résilience-Sahel
CBA	Cost Benefit Analysis
CED	Climate and Environment Department (DFID)
CGIAR	Consultative Group on International Agriculture Research
CHASE	Conflict Humanitarian and Security Department (DFID)
CSO	Civil Society Organisation
DRR	Disaster Risk Reduction
EWS	Early Warning System
FAO	Food and Agriculture Organisation
GFDRR	Global Facility for Disaster Reduction and Recovery
G-HAP	Global Humanitarian Action Programme
HEA	Household Economy Analysis
HERR	Humanitarian and Emergency Response Review
ICF	International Climate Fund.
IPCC	Intergovernmental Panel on Climate Change
NGO	Non Governmental Organisation
SRP	Structural Reform Plan
SMEs	Small to Medium –sized Enterprises
SREX	Special Report on Managing the Risks of Extreme Events and Disasters to Advance Climate Change Adaptation
UNDP	United Nations Development Programme
UNISDR	United Nations Office for Disaster Risk Reduction
UNFCCC	United Nations Framework Convention on Climate Change
WFP	World Food Programme
# Glossary of terms

Adaptation (IPCC SREX[152])
[152] IPCC SREX Extreme Events Report (2011)
In human systems, the process of adjustment to actual or expected climate and its effects, in order to moderate harm or exploit beneficial opportunities.

Climate change (IPCC SREX)
A change in the state of the climate that can be identified (e.g. by using statistical tests) by changes in the mean and/or the variability of its properties and that persists for an extended period, typically decades or longer. Climate change may be due to natural internal processes or external forcings, or to persistent anthropogenic changes in the composition of the atmosphere or in land use.

(Climate change) Impacts (IPCC AR4 synthesis report)
The effects of climate change on natural and human systems.
 Depending on the consideration of adaptation, one can distinguish between potential impacts and residual impacts:
– Potential impacts: all impacts that may occur given a projected change in climate, without considering adaptation.
– Residual impacts: the impacts of climate change that would occur after adaptation.

Climate extreme (extreme weather or climate event) (IPCC SREX)
The occurrence of a value of a weather or climate variable above (or below) a threshold value near the upper (or lower) ends of the range of observed values of the variable. For simplicity both extreme weather events and extreme climate events are referred to collectively as ‘climate extremes’.
Discussion of the term ‘climate extreme’ in the IPCC SREX Report
Several aspects of this definition can be clarified thus:

• The distinction between extreme weather events and extreme climate events is not precise, but is related to their specific time scales:
– An extreme weather event is typically associated with changing weather patterns, that is, within time frames of less than a day to a few weeks.
– An extreme climate event happens on longer time scales. It can be the accumulation of several (extreme or non-extreme) weather events (e.g., the accumulation of moderately below average rainy days over a season leading to substantially below average cumulated rainfall and drought conditions).
• What is called an extreme weather or climate event will vary from place to place in an absolute sense (e.g., a hot day in the tropics will be a different temperature than a hot day in the mid-latitudes), and possibly in time given some adaptation from society.
• Some climate extremes (e.g., droughts, floods) may be the result of an accumulation of moderate weather or climate events (this accumulation being itself extreme). Compound events, that is, two or more events occurring simultaneously, can lead to high impacts, even if the two single events are not extreme per se (only their combination). Not all extreme weather and climate events necessarily have extreme impacts.
• Definitions of thresholds vary, but values with less than 10, 5, 1%, or even lower chance of occurrence for a given time of the year (day, month, season, whole year) during a specified reference period (generally 1961-1990) are often used. In some circumstances, information from sources other than observations, such as model projections, can be used as a reference.
• Absolute thresholds (rather than these relative thresholds based on the range of observed values of a variable) can also be used to identify extreme events (e.g., specific critical temperatures for health impacts).

Co-benefits (IPCC AR4 synthesis report)
Co-benefits are the benefits of policies implemented for various reasons at the same time, for example policies designed to address greenhouse gas emissions have other, often at least equally important rationales related to objectives of development, sustainability and equity.

Disaster (UNISDR[153])
[153] United Nations International Strategy for Disaster Reduction. 2009 UNISDR Terminology on Disaster Risk Reduction, UNISDR, Geneva
A serious disruption of the functioning of a community or a society involving widespread human, material, economic or environmental losses and impacts, which exceeds the ability of the affected community or society to cope using its own resources.

Disaster Resilience (DFID approach paper)
The ability of countries, communities and households to manage change, by maintaining or transforming living standards in the face of shocks or stresses - such as earthquakes, drought or violent conflict – without compromising their long-term prospects

Hazard (IPCC SREX)
The potential occurrence of a natural or human-induced physical event that may cause loss of life, injury, or other health impacts, as well as damage and loss to property, infrastructure, livelihoods, service provision, and environmental resources.

Low Regrets (IPCC SREX)
Measures that provide benefits under current climate and a range of future climate change scenarios, they have the potential to offer benefits now and lay the foundation for addressing projected changes. Many of these low-regrets strategies help address other development goals such as improvements in livelihoods, human well-being and biodiversity conservation

Vulnerability (IPCC SREX[154])
[154] Quoted in Foresight ‘Reducing Risks of future Disasters’ 2012.
The characteristics and circumstances of a community, system or asset that make it susceptible to the damaging effects of a hazard

List of Boxes

Box 1: Definition of climate and weather extreme events
Box 2: What is Climate Resilience?
Box 3: Examples of indirect impacts of climate related disasters
Box 4: Example of success - Regreening the Sahel
Box 5: The potential of NGOs to build resilience to climate extremes
– evidence of feasibility and demand
Box 6: Estimating the number of people who will benefit from BRACED
Box 7: Criteria, eligibility, length and size of grants for Component A and B
Box 8: VFM review of activities similar to those in the BRACED programme
Box 9: Benefits and Costs of BRACED knowledge and evidence component
Box 10: WFP as a potential partner for BRACED delivery
Box 11: Delivery options for BRACED knowledge and evidence component
Box 12: Example of third party management agent: the South Asia Climate Resilience Alliance (SACRA)
Box 13: Example of an international agency as management option: the Adaptation for Smallholder Agriculture Programme (ASAP)
Box 14: Example of Hybrid option – the Global Poverty Action Fund (GPAF)

List of Figures

Figure 1 Global extreme events 1980 to 2011
Figure 2 Theory of Change
Appraisal section:
Figure 1: BRACED structure and decision making process
Figure 2: Flowchart of appraisal process for BRACED
Figure 3: Structure of the BRACED programme based on appraisal case recommendations

List of Tables

Table 1: No of people seriously affected by climate related disasters since 2000
Table 2: Numbers food insecure people in the Sahel 2013
Table 3: Why governments should be involved in building resilience to climate extremes
Table 4: Mapping of current NGO interventions in the Sahel
Table 5: Summary of options considered and assessment of evidence for appraisal
Table 6: Investment Options
Table 7: Climate change and environmental categories
Table 8: Critical Success Criteria
Table 9: Cost estimates – Option 1 Finance to Adaptation Multilateral Organisation
Table 10: Benefits estimates - Option 1 Finance to Adaptation Multilateral Organisation
Table 11: Cost estimates – Option 2 Direct provision of activities by DFID country offices
Table 12: Benefits estimates - Option 2 Direct provision of activities by DFID country offices
Table 13: Cost estimates – Option 3 Finance to NGOs and Partners
Table 14: Benefits estimates - Option 3 direct support to civil society organisations
Table 15: Multi-criteria analysis – BRACED delivery options
Table 16: BRACED management functions
Table 17: Management Options
Table 18: Critical Success Criteria
Table 19: Benefits estimates of management option 1 – NGO consortium
Table 20: Cost estimates of management option 1 – NGO consortium
Table 21: Benefit estimates of management option 2 – third party external agent
Table 22: Cost estimates of management option 2 –third party external agent
Table 23: Benefits estimates of management option 3 – international organisation
Table 24: Cost estimates of management option 3 – international organisation
Table 25: Benefits estimates of management option 4 – in house
Table 26: Cost estimates of management option 4 – in house
Table 27: Benefits estimates of management option 5 – hybrid option
Table 28: Cost estimates of management option 4 – hybrid option
Table 29: Multi-criteria analysis – BRACED management options
Table 30: Climate change and environmental categories of management options
Table 31: Annual breakdown of BRACED costs over first phase years (£ millions)
Table 32: Implementation risks to BRACED and their mitigation
Table 33: Potential Strategic Evaluation Questions

Annex A to economic appraisal

Annex D: Matrix of cost-benefit data for Management Options

# References and notes